## Budget Top Sheet (hidden)
ERA INFRA ENGINEERING LIMITED
APPROVAL OF BUDGET FOR MONTH OF July-2012
Project Code: 1059
Project Name: NTPC - JHAJJAR
S NO. | PARTICULARS | GREEN BOOK | [9 empty] | BUDGET | [9 empty] | ACTUALS | [5 empty] | DIFFERENCE
|  | AS PER ORIGINAL GREEN BOOK |  | AS PER ORIGINAL GREEN BOOK |  | AS PER ORIGINAL GREEN BOOK |  | AS PER ORIGINAL GREEN BOOK (Weighted Average) |  | AS PER LATEST GREEN BOOK |  | AS PER SCOPE BALANCE WORK |  | AS PER SCOPE/ SPREAD OF BALANCE WORK FOR THE MONTH |  | AS PER LATEST REVISED GREEN BOOK |  | AS PER BUDGET |  | AS PER PLANNING BUDGET |  | AS PER ACTUAL | [5 empty] | ACTUAL DIFF. FROM REVISED GREEN BOOK (WEIGTHED AVERAGE) | ACTUAL DIFF. FROM ORIGINAL GREEN BOOK
|  | Total Gross Value | % on Work done | Total gross work done as per GB upto date | % on Work done | Cummulative Up to date | % on Work done | Cummulative Up to date | % on Work done | Cummulative Up to date | % on Work done | Current Month | % of work done | Current Month | % of work done | Current Month | % on Work Done | Current Month | % on Work Done | Next month budget | % on Work Done | upto DEC '10 | % on Work done | m/o JAN '10 | % on Work done | Till m/o JAN '10 | % on Work done
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9=7 | 10 | 11=9 | 12 | 13=[3-7] | 14 | 15 | 16 | 17 | 18 | 19=17 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
A | Turnover
1 | Net Certified Work done | 28495.2037 |  | 24659.0998 |  | 24659.0998 |  | 24659.0998 |  | 24659.0998 |  | 3836.1038 |  | 0 |  | 622.9187 |  | 622.9187 |  | 552.4332 |  | 16153.741 |  | 594.6685 |  | 16748.4095
| ESCALATION | 2868.217 |  | 1470.63 |  | 1470.63 | 7% | 1470.63 |  | 1470.63 | [5 empty] | 49.8335 | 8% | 43.6043 | 7% | 38.6703 | 7%
| Gross work done | 31363.4206 |  | 26129.7298 |  | 26129.7298 |  | 26129.7298 |  | 26129.7298 |  | 3836.1038 |  | 0 |  | 672.7522 |  | 666.523 |  | 591.1036 |  | 16153.741 | 0 | 594.6685 | 0 | 16748.4095 | 0
2 | Add: WCT
3 | Add: Service Tax | [16 empty] | 12.8321 | 2.06% | 11.3801 | 2.06% | 275.232 |  | 12.2502 |  | 287.4822
4 | OTHER INCOME | [20 empty] | 170.7683 |  | 0 |  | 170.7683
1 | Gross Turnover | 31363.4206 | 100% | 26129.7298 | 100% | 26129.7298 | 100% | 26129.7298 | 100% | 26129.7298 | 100% | 3836.1038 | 100% | 0 | 100% | 672.7522 | 100% | 679.3551 | 100% | 602.4837 | 100% | 16599.7413 | 100% | 606.9187 | 100% | 17206.66 | 100%
2 | Hold / WIP
B | Deductions
1 | TDS | 703.7952 | 2.47% | 609.0483 | 2.47% | 609.0483 | 2.47% | 583.1104 | 2.365% | 557.1726 | 2.26% | 86.6768 | 2.26% |  |  | 14.0749 | 2.26% | 13.5871 | 2% | 12.0497 | 2% | 355.9627 | 2% | 12.1384 | 2% | 368.101 | 2%
2 | WCT | 1254.5368 | 4.403% | 1085.6476 | 4.403% | 1085.6476 | 4.403% | 1035.629 | 4.2% | 985.6104 | 3.997% | 153.3269 | 3.997% |  |  | 24.8977 | 3.997% | 13.5871 | 2% | 12.0497 | 2% | 644.6836 | 4% | 24.2767 | 4% | 668.9604 | 4%
3 | Service Tax Expenses | 646.0865 | 2.267% | 559.1085 | 2.267% | 559.1085 | 2.267% | 781.0248 | 3.167% | 1002.941 | 4.067% | 156.023 | 4.067% |  |  | 25.3355 | 4.067% | 27.9894 | 4.12% | 24.8223 | 4.12% | 592.0521 | 4.12% | 25.0051 | 4.12% | 617.0571 | 4.12%
4 | Labour cess | [6 empty] | 120.0057 | 0.4867% | 240.0113 | 0.9733% | 37.3375 | 0.9733% |  |  | 6.063 | 0.9733% | 6.7936 | 1% | 6.0248 | 1% | 158.8527 | 0% | 0 | 0% | 158.8527 | 0%
| Total Deduction | 2604.4184 | 9.14% | 2253.8044 | 8.625% | 2253.8044 | 8.625% | 2519.7698 | 9.643% | 2785.7353 | 10.66% | 433.3641 | 11.3% | 0 | #DIV/0! | 70.371 | 10.46% | 61.9572 | 9.12% | 54.9465 | 9.12% | 1751.5511 | 10.55% | 61.4202 | 10.12% | 1812.9713 | 10.54%
| Net Turnover | 28759.0022 | 91.7% | 23875.9255 | 91.37% | 23875.9255 | 91.37% | 23609.96 | 90.36% | 23343.9945 | 89.34% | 3402.7397 | 88.7% | 0 | #DIV/0! | 602.3812 | 89.54% | 617.3979 | 90.88% | 547.5372 | 90.88% | 14848.1901 | 89.45% | 545.4985 | 89.88% | 15393.6887 | 89.46% | 617.3979 | 15.0168
C | Expenditure
a | Material Consumption
4 | Material Consumed | 6387.5817 | 22.42% | 5527.6676 | 22.42% | 5677.6676 | 22.42% | 5644.6016 | 23.91% | 5611.5356 | 22.15% | 849.6262 | 22.15% | 0 | #DIV/0! | 45.2445 | 7.511% | 41.6591 | 6.688% | 37.9558 | 6.871% | 2676.696 | 16.12% | 19.2231 | 3.167% | 2695.919 | 15.67% | 41.6591 | -3.5854
b | Direct Expenses
b.1 | PC only with Labour Rate | 1896.4866 | 6.655% | 1641.1763 | 6.655% | 1791.1763 | 6.655% | 2125.4206 | 6.655% | 2459.6649 | 9.366% | 359.304 | 9.366% | 0 | #DIV/0! | 122.9257 | 19.73% | 133.6357 | 21.45% | 103.6942 | 18.77% | 3217.6089 | 19.38% | 72.8399 | 12% | 3290.4488 | 19.12% | 133.6357 | 10.71
b.2 | Specialised Agency/Back to Back | 11973.1407 | 42.02% | 10361.2831 | 42.02% | 10511.2831 | 42.02% | 9491.5322 | 42.02% | 8471.7813 | 33.75% | 1294.5816 | 33.75% | 0 | #DIV/0! | 235.7292 | 37.84% | 260.0337 | 41.74% | 245.1887 | 44.38% | 3107.1737 | 18.72% | 6.8355 | 1.126% | 3114.0091 | 18.1% | 260.0337 | 24.3045
| Dedeuct for material issued to sub-contractor | [26 empty] | 0 | 0
b.3 | Mustroll C - LOSS | 144.2322 | 0.5062% | 124.8153 | 0.5062% | 124.8153 | 0.5062% | 124.8153 | 0.5287% | 124.8153 | 0.5062% | 19.4169 | 0.5062% |  |  | 3.153 | 0.5062% | 3.8974 | 0.6313% | 3.8974 | 0.7055% | 148.5078 | 0.8946% | 14.3372 | 2.362% | 162.845 | 0.9464% | 3.8974 | 0.74442
b.4 | Mustroll D ( Cleaning) | [26 empty] | 0 | 0
| TOTAL | 14172.8225 | 49.28% | 12264.8376 | 51.37% | 12564.8376 | 52.63% | 11879.331 | 50.31% | 11193.8243 | 47.95% | 1694.7026 | 49.8% | 0 | #DIV/0! | 365.2829 | 60.64% | 397.5668 | 64.39% | 360.0014 | 65.75% | 6473.2903 | 39% | 94.0126 | 15.49% | 6567.3029 | 38.17% | 397.5668 | 32.2839
D | OVERHEADS | 3190.3937 | 11.2% | 2760.894 | 11.2% | 2925.5494 | 11.2% | 3054.6558 | 11.2% | 3183.7623 | 12.91% | 495.2834 | 12.91% | 0 | #DIV/0! | 80.4257 | 12.91% | 63.8887 | 10.35% | 56.6594 | 10.35% | 2060.2948 | 12.41% | 55.8476 | 9.202% | 2116.1423 | 12.3% | 63.8887 | -16.537
E.1 | RENTAL | 289.7341 | 1.017% | 250.7293 | 1.017% | 265.6824 | 1.017% | 842.4404 | 1.017% | 1419.1984 | 5.755% | 220.7782 | 5.755% | 0 | #DIV/0! | 35.8507 | 5.755% | 26.9189 | 4.36% | 23.8729 | 4.36% | 2926.0742 | 17.63% | 64.523 | 10.63% | 2990.5973 | 17.38% | 26.9189 | -8.9318
E.2 | RUNNING/ MAINT CHARGES FOR RENTAL | 20.481 | 0.07188% | 17.7238 | 0.07188% | 18.7808 | 0.07188% | 22.1162 | 0.07188% | 25.4517 | 0.1032% | 3.9594 | 0.1032% |  |  | 0.64294 | 0.1032% | 1.2 | 0.1944% | 1.0642 | 0.1944% | 34.3333 | 0.2068% | 0.20791 | 0.03426% | 34.5412 | 0.2007% | 1.2 | 0.55706
E.3 | Diesel & Fuel | 158.9629 | 0.5579% | 137.5629 | 0.5579% | 137.5629 | 0.5579% | 137.5629 | 0.5826% | 137.5629 | 0.5579% | 21.4 | 0.5579% |  |  | 3.475 | 0.5579% | 7.221 | 1.17% | 7.221 | 1.307% | 527.7448 | 3.179% | 0 | 0% | 527.7448 | 3.067%
F | TEMPORARY INFRASTRUCTURE | 78.8676 | 0.2768% | 68.2502 | 0.2768% | 72.3206 | 0.2768% | 78.2391 | 0.2768% | 84.1575 | 0.3413% | 13.092 | 0.3413% |  |  | 2.1259 | 0.3413% |  |  |  |  | 6.8161 | 0% | 1.0458 | 0% | 7.8619 | 0% | 0 | -2.1259
G | Total Expenditure | 24298.8435 | 84.49% | 21027.6654 | 93.81% | 21662.4013 | 93.81% | 21658.947 | 93.81% | 21655.4927 | 93.81% | 3298.8419 | 96.95% | 0 | #DIV/0! | 533.0476 | 88.49% | 538.4544 | 87.21% | 486.7747 | 88.9% | 14705.2495 | 88.59% | 234.86 | 38.7% | 14940.1095 | 86.83% | 538.4544 | 5.4068
H | Surplus/Deficit (-) | 4460.1586 | 15.51% | 2848.26 | 11.93% | 2213.5242 | 9.271% | 1951.013 | 8.264% | 1688.5018 | 7.233% | 103.8978 | 3.053% | 0 | #DIV/0! | 69.3335 | 11.51% | 78.9435 | 11.62% | 60.7625 | 11.1% | 142.9407 | 0.8611% | 310.6385 | 51.18% | 453.5792 | 2.636% | 78.9435

## Budget-4-Approval
ERA INFRA ENGINEERING LIMITED
PROJECT: -DDA KALKAJI [2005] | [13 empty] | DATE: 23/02/2010
BUDGET FOR APPROVAL
Rs. In Lacs
S. NO. | PARTICULAR | 2015-01-01 | [11 empty] | REMARKS, IF ANY | MONTH-II |  | MONTH-III
|  | AS PER ORIGINAL GREEN BOOK |  | AS PER REVISED GREEN BOOK MAY'13 |  | % | AS PER MONTHLY BUDGET | % | ORIGINAL GREEN BOOK VS BUDGET DIFFERENCE +/(-) | REVISED GREEN BOOK VS BUDGET DIFFERENCE +/(-) | BUDGET RECOMMENDED | ACTUAL FOR THE MONTH | APPROVAL OF ACTUALS |  | AS PER MONTHLY BUDGET | % on work done | AS PER MONTHLY BUDGET | % on work done
1 | 2 | 3 |  | 4 |  |  | 5 |  | 6 | 7 | 8 | 9 | 10 | 13 | 11 |  | 14 | 12
A | Turnover | 873.82 |  | 873.82 |  |  | 873.82
| Civil (Direct) | 0 |  | 0 |  |  |  |  | 0 | 0 |  |  |  |  | #REF! |  | #REF!
| Civil (Back to Back) | 0 |  | 0 |  |  |  |  | 0 | 0
| Civil Specialised Agency Works | 0 |  | 0 |  |  |  |  | 0 | 0
E & M Works
| Escalation, if any @ 6% | 59.562 |  | 59.562 |  | 6.816% | 52.4292 |  | 7.1328 | 7.1328 |  |  |  |  | #REF! |  | #REF!
| ORC @ 2 Lacks /Month | 2 |  | 2 |  |  | 0
Extra Items
| Other Income | 0
Less: Rebate, If Any
| Gross Work Done | 61.562 |  | 61.562 |  |  | 926.2492 |  | -864.6873 | -864.6873 |  | 0 | 0 |  | #REF! |  | #REF! | 0
Add: WCT
| Add: Service Tax @ 4.944% | 3.0436 |  | 3.0436 |  |  | 45.7938 |  | -42.7501 | 45.7938
| Add: Hold Items | [7 empty] | 0 | 0
| Add: Work In Progress (WIP) | [7 empty] | 0 | 0
| Add: Other Income | [7 empty] | 0 | 0
| Gross Turnover | 64.6056 | 104.9% | 64.6056 | 104.9% | 100% | 972.043 | 100% | -907.4374 | -818.8935 |  | 0 | 0 |  | #REF! |  | #REF! | 0
| Deductions: |  |  |  |  | 0% |  | 0%
| WCT (Income Tax) | 1.2921 | 2% | 1.2312 | 2% | 2% | 18.525 | 2% | -17.2329 | 18.4641 |  |  |  |  | #REF! | 4% | #REF! | 4%
| D Vat 4% | 3.0436 |  | 3.0436 | 0% | 4.944% | 37.05 | 4% | -34.0063 | 37.05 |  |  |  |  | #REF! | 4.25% | #REF! | 4.25%
| Add: Service Tax @ 4.944% | [5 empty] | 34.9316 | 4.944%
| Labour Cess |  | 0 | 0 |  | 0% | 9.2625 | 1% | -9.2625 | 9.2625 |  |  |  |  | #REF! | 1% | #REF! | 1%
| Escalation (to be Paid to Structural Agency) |  | 0 | 0 |  | 0% |  | 0%
| Total Deductions | 4.3357 |  | 4.2749 | 6.617% | 6.944% | 99.769 | 10.77% | -60.5017 | 64.7766 |  | 0 | 0 |  | #REF! |  | #REF!
| Net Turnover (A) | 60.2699 | 97.9% | 60.3307 | 93.38% | 93.38% | 872.274 | 89.74% | -812.0041 | -811.9432 |  | 0 | 0 |  | #REF! |  | #REF!
B | Expenditure |  |  |  |  | 0% |  | 0%
| Material Consumed | 32.2076 | 49.85% | 92.6856 | 150.6% | 143.5% | 513.5136 | 52.83% | -481.306 | -420.828 |  |  |  |  | #REF! | 16.69% | #REF! | 16.69%
| PC with Labour Rate | 10.7597 | 16.65% | 28.0281 | 45.53% | 43.38% | 69.8731 | 7.188% | -59.1134 | -41.845 |  |  |  |  | #REF! | 8.75% | #REF! | 8.657%
| Specialised Agency/ Back To Back | 4.6621 | 7.216% | 31.0539 | 50.44% | 48.07% | 0 | 0% | 4.6621 | 31.0539 |  |  |  |  | #REF! | 35.83% | #REF! | 38.84%
| Shuttering material rental req for this month | 0 | 0% | 0 | 0% | 0% | 0.72384 | 0.07447% | -0.72384 | -0.72384 |  |  |  |  | #REF! | 0.1804% | #REF! | 0.1368%
| Power, Fuel & Water Expenses | 0.11814 | 0.1829% | 1.9912 | 3.234% | 3.082% | 5.0635 | 0.5209% | -4.9454 | -3.0723 |  |  |  |  | #REF! | 0.938% | #REF! | 0.8728%
| Total | 47.7475 | 73.91% | 153.7587 | 238% | 238% | 589.174 | 60.61% | -541.4265
| Muster Roll Labour A | 0.2021 | 0.3128% | 0.7785 | 1.205% | 1.205% | 0.7785 | 0.08009% | -0.5764
| Muster Roll Labour B | 0.023595 | 0.03652% | 0 | 0% | 0% | 0 | 0%
| Total Muster Roll Labour A & B | 0.2257 |  | 0.7785 | 1.205% | 1.205% | 0.7785 | 0.08009%
| Watch and Ward | 0.092695 | 0.1435% | 0 | 0% | 0% | 0.5 | 0.05144%
| Staff Salary A | 1.2331 | 1.909% | 11.035 | 17.08% | 17.08% | 11.035 | 1.135%
| Staff Salary B |  | 0% | 0 | 0% | 0% |  | 0%
| Total Staff Salary A & B |  | 2.052% | 11.035 | 17.08% | 17.08% | 11.035 | 1.135%
Indirect Expenses / Overheads
1 | Labour Welfare | 0.064606 | 0.1% | 0.10714 | 0.174% | 0.1658% | 0.3 | 0.03086% | [10 empty] | 0
2 | Car Hiring Charges | 0.042134 | 0.06522% | 0.34475 | 0.56% | 0.5336% | 0 | 0% | 0.042134 | 0.34475 |  |  |  |  | #REF! | 0.0962% | #REF! | 0.08951% | 0
3 | Repair & Maintenance | 0.014045 | 0.02174% | 0.046171 | 0.075% | 0.07147% | 0.5 | 0.05144% | -0.48596 | -0.45383 |  |  |  |  | #REF! | 0.08017% | #REF! | 0.07459%
4 | Vehicle Running & Maint. | 0.0036516 | 0.005652% | 0 | 0% | 0% | 0 | 0% | 0.0036516 | 0 |  |  |  |  | #REF! | 0.004008% | #REF! | 0.00373%
5 | Local Conveyance | 0.014045 | 0.02174% | 0.018469 | 0.03% | 0.02859% | 0.08 | 0.00823% | -0.065955 | -0.061531 |  |  |  |  | #REF! | 0.02004% | #REF! | 0.01865%
6 | Travelling | 0.015449 | 0.02391% | 0.092343 | 0.15% | 0.1429% | 0 | 0% | 0.015449 | 0.092343 |  |  |  |  | #REF! | 0.02004% | #REF! | 0.01865%
7 | Rent Staff Quarters/Office | 0.084268 | 0.1304% | 0.35675 | 0.5795% | 0.5522% | 0.6 | 0.06173% | -0.51573 | -0.24325 |  |  |  |  | #REF! | 0.0334% | #REF! | 0.03108%
8 | Guest House Expenses | 0.012991 | 0.02011% | 0.057116 | 0.09278% | 0.08841% | 0.118 | 0.01214% | -0.10501 | -0.060884 |  |  |  |  | #REF! | 0.0147% | #REF! | 0.01368%
9 | Staff Welfare | 0.0084268 | 0.01304% | 0.092343 | 0.15% | 0.1429% | 0.26 | 0.02675% | -0.25157 | -0.16766 |  |  |  |  | #REF! | 0.06681% | #REF! | 0.06216%
10 | Client Entertainment | 0.0084268 | 0.01304% | 0.030781 | 0.05% | 0.04764% | 0.05 | 0.005144% | -0.041573 | -0.019219 |  |  |  |  | #REF! | 0.01336% | #REF! | 0.01243%
11 | Incentive Staff | 0 | 0% | 0 | 0% | 0% | 0 | 0% | 0 | 0 |  |  |  |  | #REF! | 0.01336% | #REF! | 0.01243%
12 | Medical Expenses | 0.014045 | 0.02174% | 0.1539 | 0.25% | 0.2382% | 0.12 | 0.01235% | -0.10596 | 0.033905 |  |  |  |  | #REF! | 0.006681% | #REF! | 0.006216%
13 | Insurance Premium | 0.18237 | 0.2823% | 0 | 0% | 0% | 0 | 0% | 0.18237 | 0 |  |  |  |  | #REF! | 0.342% | #REF! | 0.3183%
14 | Printing & Stationary | 0.0042134 | 0.006522% | 0.098499 | 0.16% | 0.1525% | 0.155 | 0.01595% | -0.15079 | -0.056501 |  |  |  |  | #REF! | 0.005344% | #REF! | 0.004973%
15 | Telephone & Fax | 0.026685 | 0.0413% | 0.072027 | 0.117% | 0.1115% | 0.11 | 0.01132% | -0.083315 | -0.037973 |  |  |  |  | #REF! | 0.0147% | #REF! | 0.01368%
16 | Postage & Telegram | 0.0042134 | 0.006522% | 0.024625 | 0.04% | 0.03812% | 0.01 | 0.001029% | -0.0057866 | 0.014625 |  |  |  |  | #REF! | 0.002672% | #REF! | 0.002486%
17 | Pooja Expenses | 0.0042134 | 0.006522% | 0.018469 | 0.03% | 0.02859% | 0.026 | 0.002675% | -0.021787 | -0.0075314 |  |  |  |  | #REF! | 0.002672% | #REF! | 0.002486%
18 | Testing Charges | 0.07951 | 0.1231% | 0.030781 | 0.05% | 0.04764% | 0.25 | 0.02572% | -0.17049 | -0.21922 |  |  |  |  | #REF! | 0.1136% | #REF! | 0.1057%
19 | Legal & Professional Charges | 0.018258 | 0.02826% | 0.032012 | 0.052% | 0.04955% | 0.022 | 0.002263% | -0.0037419 | 0.010012 |  |  |  |  | #REF! | 0.006681% | #REF! | 0.006216%
20 | Bank Charges & Commission | 0 | 0% | 0 | 0% | 0% | 0.04 | 0.004115% | -0.04 | -0.04 |  |  |  |  | #REF! | 0.306% | #REF! | 0.2847%
21 | Interest Paid | 0 | 0% | 0 | 0% | 0% | 0 | 0% | 0 | 0 |  |  |  |  | #REF! | 0.5678% | #REF! | 0.5284%
22 | Working Capital interest | 0 | 0% | 0 | 0% | 0% | 0 | 0%
23 | Charity and donation | 0.0028089 | 0.004348% | 0.061562 | 0.1% | 0.09529% | 0.015 | 0.001543%
24 | Misc Expences |  | 0.02609% | 0.080031 | 0.13% | 0.1239% | 0.07 | 0.007201% | [10 empty] | 0
| Total Indirect Expenses | 0.60436 | 0.9355% | 1.7178 | 2.659% | 2.659% | 2.726 | 0.2804% | -1.8041 | -0.87196 | 0 | 0 | 0 |  | #REF! |  | #REF!
| Muster Roll C | 0.023595 | 0.03652% | 0 | 0% | 0% | 0.6756 | 0.0695%
| Total Muster Roll, Staff salary and OH | 0.94635 | 1.465% | 13.5313 |  | 20.94% | 15.7151 | 1.617%
| H.O. Share 3% On Gross Work Done | 2.5842 | 4% | 8.9508 | 14.54% | 13.85% | 29.1613 | 3% | -26.5771 | -20.2105 |  |  |  |  | #REF! | 5% | #REF! | 5%
| Rental for plant & machinery | 0.1809 | 0.28% | 1.1602 | 1.885% | 1.796% | 3.4405 | 0.3539% | -3.2596 | -2.2803 |  |  |  |  | #REF! | 1.219% | #REF! | 1.109%
| Shuttering Material | 0 | 0% | 2.3388 | 3.799% | 3.62% | 36.9295 | 3.799% | -36.9295 | -34.5906 |  |  |  |  | #REF! | 0.2605% | #REF! | 0.2424%
| Hiring Charges of Plants and Machinery | 0 | 0% | 0.13933 | 0.2263% | 0.2157% | 2.2 | 0.2263%
| Machinery Rental EMD | 0 |  | 0 | 0% | 0% | 0 | 0% | 0 | 0 |  |  |  |  | #REF! | 3.207% | #REF! | 2.984%
| Interest On H.O Loan | 0 | 0% | 0 | 0% | 0% | 0 | 0% | 0 | 0 |  |  |  |  | #REF! | -0.9353% | #REF! | -0.8454%
| Temp Infra | 0.25842 | 0.4% | 0.82054 | 1.333% | 1.27% | 2.5 | 0.2572%
| M.O.H | 0.32303 | 0.5% | 2.2377 | 3.635% | 3.464% | 6.1167 | 0.6293% | -5.7937 | -3.879 |  |  |  |  | #REF! | 0.6681% | #REF! | 0.6216%
[9 empty] | 0 | 0 |  |  |  |  | #REF! | 0.2004% | #REF! | 0.1865%
| Total Expenditure (B) | 52.0404 | 80.55% | 182.9374 | 283.2% | 283.2% | 685.2372 | 70.49% | -74.3639 | -61.8324 | 0 | 0 | 0 |  | #REF! |  | #REF! | 0.089249
| Net Profit/Loss (A-B) | 8.2294 | 12.74% | -122.6067 | -189.8% | -189.8% | 187.0368 | 19.24% | -737.6402 | -750.1108 | 0 | 0 | 0 |  | #REF! |  | #REF! | -0.089249
Note on H34: Era: IN FLOW
Note on H87: Era: OUT FLOW

## OVER ALL SUMMRY (hidden)
Era Infra Engineering Limited
Execution Budget for the month of July- 2014
S. No. | Description | Amount
1 | Total Execution Budget as per BOQ (rate as per DSR-2012) | 873.82
2 | Total Contract Value | 2319242240
Since this is a Lum Sum contract and payment will be made on % basis as mention in the contract
3 | Payment will be done for completion upto Plinth level for all Clusters 15% of Rs. 231.92 crores | 347886336
Total RCC to be done upto plinth level = 9265 Cum
4 | Rate per Cum | 37548.4443
5 | RCC taken in Budget for the M/o- AUG- 2014 (2099 Cum) | 78814184.4861
6 | Our tentative amount for Budget (AUG-14) as per contract will be | 78814184.4861
Note: | The above budget may be achieved if our all requirements (Material, Staff, Manpower, Machinery, Fund etc) are full filled and all issues including clint issues are solved. The Liability upto 31st May-14 should be cleared immediately. The fund required immediately as mentioned to be arrange immediately.

## Overhead for Budget
ERA INFRA ENGINEERING LIMITED
BUDGET OVERHEAD JAN-15
S.No | Particulars | Total
|  | Amount | %
| work done | 873.82
1 | ## H O Share 3% | 26.2146 | 3%
2 | MOH | 4.3691 | 0.5%
3 | STAFF SALARY
3.1 | Staff Salary A | 11.035 | 1.263%
3.2 | Staff Salary B * | 0.7785 | 0.08909%
| TOTAL OF STAFF SALARY | 11.8135 | 1.352%
4 | Watch & Ward | 0.5 | 0.05722%
6 | MUSTER ROLL
6.1 | Mustor Roll Labour A | 0 | 0%
6.2 | Mustor Roll Labour B | 0 | 0%
| TOTAL OF MUSTROLL | 0 | 0%
7 | WATER & ELECTRICITY CHARGES
7.1 | Water Charges | 1.641 | 0.1878%
7.2 | Electricity Charges | 1.1 | 0.1259%
| TOTAL | 2.741 | 0.3137%
8 | VEHICLE RUNNING CHARGES
8.1 | Car Hiring Charges | 0 | 0%
8.2 | Vehical Running Maint. For Staff | 0 | 0%
8.3 | Diesel & Fuel | 2.3225 | 0.2658%
| TOTAL | 2.3225 | 0.2658%
9 | ADMINISTARTION CHARGES
9.1 | Stationary For Office | 0.155 | 0.01774%
9.2 | Telephone/Mob. & Fax | 0.11 | 0.01259%
9.3 | Postage & Telegram | 0.01 | 0.001144%
9.4 | Pooja Expenses | 0.026 | 0.002975%
| TOTAL | 0.301 | 0.03445%
10 | TRAVELLING CHARGES
10.1 | Local Conveyance | 0.08 | 0.009155%
10.2 | Travelling For Staff/Other | 0 | 0%
10.3 | Guest House Exp. | 0.118 | 0.0135%
10.4 | Rent Staff Qtr. | 0.6 | 0.06866%
| TOTAL OF TRAVELLING CHARGES | 0.798 | 0.09132%
11 | STAFF WELFARE & CLIENT WELFARE
11.1 | Staff Welfare/Canteen Exp. | 0.26 | 0.02975%
11.2 | Labour Welfare | 0.3 | 0.03433%
11.3 | Medical Expenses | 0.12 | 0.01373%
11.4 | Client Entertainment | 0.05 | 0.005722%
11.5 | Charity & Donation |  | 0%
| TOTAL | 0.73 | 0.08354%
12 | Special Incentive Fot Site Staff |  | 0%
13 | INSURANCE & OTHER REVENUE EXPENSES
13.1 | Insurance Premium | 0 | 0%
13.2 | Legal & Professional Charges | 0.022 | 0.002518%
| TOTAL | 0.022 | 0.002518%
14 | BANK GUARANTEE CHARGES & INTEREST
14.1 | Bank Charges & Comm. | 0.04 | 0.004578%
14.2 | Intt. Loaded |  | 0%
14.3 | Working Capital Interest |  | 0%
| TOTAL | 0.04 | 0.004578%
15 | MISC EXPENSES | 0.7 | 0.08011%
15.1 | Testing Charges | 0.25 | 0.02861%
16.1 | Misc MOH -Regular (for labour/ PF/local admin etc) | 5.2429 | 0.6%
16.2 | Misc MOH - Incidental(for labour/ PF/local admin etc) | 0.87382 | 0.1%
| Total | 7.0667 | 0.8087%
Total Expenditure |  | 56.9184 | 6.514%
Diesel & Fuel |  | 2.3225 | 0.2658%
## HO share : 5% if cement & steel free issue, 4% if only one of them is free issue & 3% if none of them is free issue
* Salary B is the temporary / local staff which is employed at project only.
# Green Book and Circular norms are described separately because the intial GBs are not based on these norms. Once the Rev GB would be on based on these norms, the column of "As per circular norms" shown here separately will merge in GB.

## Rental for Budget
ERA INFRA ENGINEERING LIMITED
RENTAL ANNEXURE FOR JAN-15 BUDGET
S.No | Particulars | Total
|  | Amount | %
| work done | 926.2492
1 | PLANT & MACHINARY
1.1 | Rental Charges Of Plant & Machinery (within Division) | 3.4405 | 0.3714%
1.2 | Rental For Plant & Machinery (EMD) | 1.25 | 0.135%
1.3 | Hire Charges Of Plant & Machinery (from Outside) | 2.25 | 0.2429%
| Total for plant & Machinary | 6.9405 | 0.7493%
2 | RUNNING / MAINT. CHARGES of MACHINARY
2.1 | Repair & Maint. Of Mach. | 0.5 | 0.05398%
| Total of Running . Maint. Charges | 0.5 | 0.05398%
3 | SHUTTERING MATERIAL
3.1 | Shuttering Material Rental (from Outside) | 0 | 0%
3.2 | Shuttering Material Rental (within company) | 1.656 | 0.1788%
3.2a | Wooden Material Rental | 0 | 0%
3.2b | Steel Material Rental | 0 | 0%
| Total for Shuttering | 1.656 | 0.1788%
4 | SCAFFOLDING MATERIAL
4.1 | Scaffolding Material Rental (from Outside) | 0 | 0%
4.2 | Scaffolding Material Rental (within company) | 0 | 0%
Total of Scaffolding Material
| Total of Rental including maintenance | 8.5966 | 0.9281%
| Total of Rental M/c Maint. | 0.5 | 0.05398%
| Theoritical Machinary Rental | 9.0966 | 0.9821%

## Business Plan (hidden)
ERA INFRA ENGINEERING LTD.
(EPC INFRA HYD-DIVISION)
PROJECTED PROFITABILITY (AS PER GREEN BOOK)
NAME OF SITE : BHEL CHENNAI
SITE CODE : 1335 | [16 empty] | (Rs. IN LACS)
S.NO. | DESCRIPTION | Cumulative Achieved | 2013-06-13 | 2013-07-13 | 2013-08-01 | 2013-09-01 | 2013-10-01 | 2013-11-01 | 2013-12-01 | [7 empty] | TOTAL F.Y 2012
A | GROSS TURNOVER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 5757.48
B | DEDUCTIONS | 1.684% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
I | NET TURNOVER (A-B) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 5757.48
EXPENDITURE
M | MATERIAL CONSUMED | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
L | LABOUR COST | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
| OTHER DIRECT EXPENDITURE | 4.193% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
II | TOTAL DIRECT EXPENSES | 4.193% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
III | OVERHEADS | 0.0428% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
IV | NOTIONAL COST. | 0.01633% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
V | TOTAL EXPENDITURE (II to IV) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
VI | PROFIT / LOSS (I - V) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 5757.48
VII | PROFIT / LOSS MARGIN |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 100%

## Power-n-Fuel (hidden)
DIESEL CONSUMPTION M/O - 42005 | [15 empty] | Expected
Description | MISC. SITE | EIEL / EMD MACHINERIES |  | HIRED VEHICLE & MACHINERIES | [11 empty] | Total Issue
|  | MISC OTHER | CONCRETE PUMP | SHREE DG(125 KVA) | SKY DG(125 KVA) | SKY JCB | NAKKIRAN WATER TANKER | NAKKIRAN TRACTOR TROLLY | NAKKIRAN TRUCK | BHARATH T.M. | BHARATH T.M. | RATHNA HYDRA | B.VIKRAM SUMO | RAMAKRISHNAN SUMO
Total Issue | 50 | 50 | 300 | 150 | 220 | 480 | 290 | 250 | 295 | 900 | 900 | 160 | 300 | 300 |  | 4645
Water Charge | [14 empty] | Total DIESEL AMOUNT @ 50.0 | 232250
Sl. No. | Agency Name/EIEL/EMD | Machinery Name/Sl. No | Total Availaibility as per WO (Hrs per day) | Total running is a month | Rate/ Hrs | Amount | Overtime
1 | GVS |  | 3 | 93 | 1000 | 93000 | 0
2 | NAKKIRAN |  | 3 | 93 | 700 | 65100 | 0
3 | ATT |  | 8 | 240 | 25 | 6000 | 0
|  |  |  | 0 |  | 0 | 0
| total |  |  |  |  | 164100
[15 empty] | DIESEL & FUEL | 232250
[15 empty] | WATER CHARGES | 164100
[15 empty] | MONTHLY ELECTRICITY CHARGES (EXPECTED) | 110000
[15 empty] | Total Amount: | 506350

## Hiring Details
ERA INFRA ENGINEERING LIMITED
EPC-Infra- 1
PROJECT: DDA Kalkaji (2005)
Summary of Machinery at site
| Sr. No. | Machinery | Agency | Rate | Yet to Be Mobilised | REMARKS | Unit
EMD
| 1 | EXCAVATOR | EMD | 125000
0
|  | TOTAL |  | 125000 | 0
LOCAL HIRING
| 1 | JCB | NISH Engineering | 70000
| 2 | DUMPER | CHARANJITH SINGH | 60000
| 3 | HYWA | CHARANJITH SINGH | 95000
|  | TOTAL |  | 225000 | 0
HO RENTAL
| 1 | BATCHING PLANT-01 | EIEL
| 2 | CONCRETE-PUMP NO=1 | EIEL
| 3 | DG SET (125 KVA) | EIEL
| 3 | BOLERO | EIEL
|  | TOTAL |  | 0 | 0
SERVICES
TOTAL
VEHICLE HIRING
| 1 | SUMO-1 |  | 0
| 2 | SUMO-2 |  | 0
|  | TOTAL |  | 0
|  | GRAND TOTAL |  | 350000 | 0

## Project Team Allocation
Name of Project: In Situ Rehabilitation at A-14, Kalkaji Extn | [6 empty] | Total cost of Civil Work (As per GB) |  |  |  | 1913909032
Expected Date of Completion: 24.01.2016 | [6 empty] | Total Builtup Area (Sqm) |  |  |  | 120415.95
Total Project Cost as per tender: 231.92 Cr. | [6 empty] | Rate per Sqm |  |  |  | 15894.1488
Revised tender cost: 231.92 Cr
S.No. | Project Head/ Project Incharge | SHIs | TLs | TMs | Cluster/ Tower | Area/ Chainage (Sqm) | Type of Work | Date of Start | Date of Completion | Duration to complete the work (in days) | Total tender cost/ Revised cost | Amount of work as per available scope | Amount of work for which scope to be cleared | Amount of work executed | Amount of balance work as per available scope | Budget for the current month | Balance work to be executed after this month as per available scope
[6 empty] | A | B | C | D | E | F | G | H=F-G | I | J=G-I | K | L=J-K
| ZAHIR MOHAMMAD | SHI - 1 MANOJ (Cluster- 4, 2) | GAURAV THAKUR TOWER-1,6 | BIJENDRA | CL-4 T-1,T-2 | 11624.88 | Civil Work | 2014-06-16 | 2015-08-15 | 425 | 184767572.9662 | 184767572.9662 | 0 |  | 184767572.9662 | 9467158.5966 | 175300414.3695
|  |  | RAJESH TOWER-2,3 | BIJENDRA | Cl-4, T-2 | 15576.08 | Civil Work | 2014-06-12 | 2015-08-11 | 425 | 247568533.8625 | 247568533.8625 | 0 |  | 247568533.8625 | 13948352.8059 | 233620181.0566
|  |  | ANKIT PRAJAPATI TOWER-4,5 | MUNEEM | Cl-4, T-4, 5 | 15309.98 | Civil Work | 2014-07-25 | 2015-08-21 | 392 | 243339100.8562 | 243339100.8562 | 0 |  | 243339100.8562 | 12393969.9528 | 230945130.9033
|  |  | RAHUL GOND CL-2 | MUNEEM | CL-2,T-1, 2 | 12289.17 | Civil Work | 2014-08-24 | 2015-08-22 | 363 | 195325897.099 | 195325897.099 | 0 |  | 195325897.099 | 9357861.3453 | 185968035.7537
|  | Total |  |  |  | 54800.11 |  |  |  | 0 | 871001104.7838 | 871001104.7838 | 0 | 0 | 675675207.6848 | 45167342.7007 | 639865726.3294
|  | SHI-2 R.K SHARMA (Cluster-3) | AMITH KUMAR | BRIJESH KUMAR | CL-3,T-1,2,6 | 16193.3 | Civil Work | 2014-09-01 | 2015-09-12 | 376 | 257378720.4094 | 257378720.4094 | 0 |  | 257378720.4094 | 13724787.9647 | 243653932.4447
|  |  | DANISH AHAMED | BRIJESH KUMAR | CL-3,T-3,4,5 | 16193.3 | Civil Work | 2014-09-09 | 2015-09-28 | 384 | 257378720.4094 | 257378720.4094 | 0 |  | 257378720.4094 | 11177147.2299 | 246201573.1795
|  | TOTAL |  |  |  | A: 32386.6; B: 0; F: 514757440.8189; G: 514757440.8189; J=G-I: 514757440.8189; K: 24901935.1946; L=J-K: 489855505.6243
|  | DHARMENDAR KUMAR | SANJAY(SURVEYOR) | RADHESHYAM | CL-1 | 32720.88 | Civil Work | 2014-10-11 | 2015-10-09 | 363 | 520070536.8931 | 520070536.8931 | 0 |  | 520070536.8931 | 17317944.803 | 502752592.0901
|  | Total |  |  |  | 32720.88 | 0 |  |  |  | 520070536.8931 | 520070536.8931 | 0 | 0 | 520070536.8931 | 17317944.803 | 502752592.0901
| Total |  |  |  |  | A: 119907.59; B: 0; F: 1905829082.4957; G: 1905829082.4957; J=G-I: 1710503185.3967; K: 87387222.6983; L=J-K: 1632473824.0437

## Mile Stone-PI-
Era Infra Engineering Limited | [23 empty] | 1
Work Detail with Completion Date
1018.225
S. No. | Desctiption | [11 empty] | CLUSTER-3 | [7 empty] | CLUSTER-2 | Total | Remarks
|  | CLUSTER-1 | [5 empty] | CLUSTER-3 | [5 empty] | CLUSTER-2 |  | CLUSTER-4
|  | T-1 | T-2 | T-3 | T-4 | T-5 | T- 6 | T-2 | T-3 | T-4 | T-1 | T-5 | T- 6 | T-1 | T-2 | T-1 | T-6 | T-2 | T-3 | T- 4 | T-5
1 | Excavation complete with dressing
| START DATE |  | 2014-12-01 | 2014-12-08 |  |  | 2014-12-15
| Comp. Date |  | 2014-12-08 | 2014-12-15 |  |  | 2014-12-22
| Qty |  | 1681.2 | 1251.2 |  |  | 1816.9 | [14 empty] | 4749.3
2 | PCC- 1:5:10
| START DATE |  | 2014-12-10 | 2014-12-17 |  |  | 2014-12-22 | [6 empty] | 2015-01-01
| Comp. Date |  | 2014-12-13 | 2014-12-20 |  |  | 2014-12-23 | [6 empty] | 2015-01-16
| Qty |  | 40.2472 | 45.04 |  |  | 45.04 | [6 empty] | 20.82 | [7 empty] | 151.1472
3 | R/f Steel Raft
| START DATE |  | 2014-12-15 | 2014-12-22 |  |  | 2014-12-24 | [6 empty] | 2015-01-02
| Comp. Date |  | 2014-12-20 | 2014-12-27 |  |  | 2014-12-29 | [6 empty] | 2015-01-18
| QTY KG |  | 13630 | 15160 |  |  | 15160 | [6 empty] | 3779 | [7 empty] | 47729
4 | Suttering of Raft
| START DATE |  | 2014-12-18 | 2014-12-25 |  |  | 2014-12-27 | [6 empty] | 2015-01-03
| Comp. Date |  | 2014-12-20 | 2014-12-27 |  |  | 2014-12-29 | [6 empty] | 2015-01-20
| Qty |  | 78.88 | 57.3 |  |  | 57.3 | [6 empty] | 62.94 | [7 empty] | 256.42
6 | RCC Raft
| START DATE |  | 2014-12-21 | 2014-12-28 |  |  | 2014-12-30 | [6 empty] | 2015-01-04
| Comp. Date |  | 2014-12-22 | 2014-12-29 |  |  | 2014-12-31 | [6 empty] | 2015-01-24
| Qty |  | 258.04 | 262.88 |  |  | 262.88 | [6 empty] | 75.72 | [7 empty] | 859.52
7 | Column Steel
| START DATE | 2015-01-01 | 2014-12-23 |  |  | 2015-01-01
| Comp. Date | 2015-01-07 | 2014-12-27 |  |  | 2015-01-08
| QTY KG | 14700 | 13860 |  |  | 11690 | [15 empty] | 40250
8 | Column Shuttering
| START DATE | 2015-01-03 | 2014-12-24 |  |  | 2015-01-03
| Comp. Date | 2015-01-09 | 2014-12-28 |  |  | 2015-01-10
| Qty | 323.34 | 348 |  |  | 260.13 | [15 empty] | 931.47
9 | Column RCC
| START DATE | 2015-01-04 | 2014-12-24 |  |  | 2015-01-04
| Comp. Date | 2015-01-10 | 2014-12-30 |  |  | 2015-01-10 | [16 empty] | 695.2982
| Qty | 40.8 | 43.3 |  |  | 32.45 | [15 empty] | 116.55
10 | PLINTH BEAM SHUTTERING
| START DATE | 2015-01-12 |  |  |  | 2015-01-12
| Comp. Date | 2015-01-22 |  |  |  | 2015-01-22
| Qty | 271.21 |  |  |  | 243.99 | [15 empty] | 515.2
11 | PLINTH BEAM STEEL
| START DATE | 2015-01-15 |  |  |  | 2015-01-15
| Comp. Date | 2015-01-25 |  |  |  | 2015-01-25
| QTY KG | 2890 |  |  |  | 2600 | [15 empty] | 5490
12 | PLINTH BEAM RCC
| START DATE | 2015-01-16 |  |  |  | 2015-01-16
| Comp. Date | 2015-01-26 |  |  |  | 2015-01-26
| Qty CUM | 22.191 |  |  |  | 19.964 | [15 empty] | 42.155
13 | R.WALL STEEL
| START DATE | [12 empty] | 2015-01-06
| Comp. Date | [12 empty] | 2015-01-22
| Qty CUM | [12 empty] | 3180 | [7 empty] | 3180
13 | R.WALL SHUTTERING
| START DATE | [12 empty] | 2015-01-08
| Comp. Date | [12 empty] | 2015-01-25
| Qty CUM | [12 empty] | 533.26 | [7 empty] | 533.26
13 | R.WALL RCC
| START DATE | [12 empty] | 2015-01-10
| Comp. Date | [12 empty] | 2015-01-30
| Qty CUM | [12 empty] | 56.88 | [7 empty] | 56.88
13 | BACK FILLING
| START DATE | 2015-01-27 |  |  |  | 2015-01-27
| Comp. Date | 2015-01-31 |  |  |  | 2015-01-31
| Qty CUM | 1500 |  |  |  | 1798.056 | [15 empty] | 3298.056
14 | STILT FLOOR COLUMN STEEL
| START DATE |  |  |  | 2015-01-01 |  |  |  |  | 2015-01-01 |  | 2015-01-01
| Comp. Date |  |  |  | 2015-01-07 |  |  |  |  | 2015-01-05 |  | 2015-01-06
| QTY KG |  |  |  | 5470 |  |  |  |  | 5160 |  | 7430 | [9 empty] | 18060
15 | STILT FLOOR COLUMN SHUTTERING
| START DATE |  |  |  | 2015-01-03 |  |  |  |  | 2015-01-03 |  | 2015-01-03
| Comp. Date |  |  |  | 2015-01-07 |  |  |  |  | 2015-01-05 |  | 2015-01-06
| Qty SQM |  |  |  | 144.5 |  |  |  |  | 130.0162 |  | 187.2226 | [9 empty] | 461.7388
16 | STILT FLOOR COLUMN RCC
| START DATE |  |  |  | 2015-01-03 |  |  |  |  | 2015-01-03 |  | 2015-01-03
| Comp. Date |  |  |  | 2015-01-08 |  |  |  |  | 2015-01-06 |  | 2015-01-08
| Qty CUM |  |  |  | 14.9 |  |  |  |  | 17.3355 |  | 24.963 | [9 empty] | 57.1985
17 | STILT FLOOR BEAM SLAB SHUTTERING
| START DATE |  |  |  | 2015-01-09 |  |  |  | 2015-01-01 | 2015-01-06 |  | 2015-01-09 |  | 2015-01-01 | 2015-01-01 | [5 empty] | 2015-01-01
| Comp. Date |  |  |  | 2015-01-16 |  |  |  | 2015-01-08 | 2015-01-13 |  | 2015-01-19 |  | 2015-01-08 | 2015-01-08 | [5 empty] | 2015-01-06
| Qty SQM |  |  |  | 491.2 |  |  |  | 600 | 415.576 |  | 598.427 |  | 626.387 | 655.24 | [5 empty] | 721.43 | 4108.26
18 | STILT FLOOR BEAM SLAB STEEL
| START DATE |  |  |  | 2015-01-11 |  |  |  | 2015-01-03 | 2015-01-08 |  | 2015-01-11 |  | 2015-01-03 | 2015-01-03 | [5 empty] | 2015-01-03
| Comp. Date |  |  |  | 2015-01-17 |  |  |  | 2015-01-09 | 2015-01-14 |  | 2015-01-21 |  | 2015-01-09 | 2015-01-09 | [5 empty] | 2015-01-07
| QTY KG |  |  |  | 7850 |  |  |  | 10690 | 7400 |  | 12440 |  | 10730 | 11230 | [5 empty] | 13001 | 73341
19 | STILT FLOOR BEAM SLAB RCC
| START DATE |  |  |  | 2015-01-18 |  |  |  | 2015-01-10 | 2015-01-15 |  | 2015-01-22 |  | 2015-01-10 | 2015-01-10 | [5 empty] | 2015-01-07
| Comp. Date |  |  |  | 2015-01-18 |  |  |  | 2015-01-10 | 2015-01-15 |  | 2015-01-22 |  | 2015-01-10 | 2015-01-10 | [5 empty] | 2015-01-08
| Qty CUM |  |  |  | 51.8 |  |  |  | 70.7 | 48.9696 |  | 70.5159 |  | 66.02 | 68.97 | [5 empty] | 74.31 | 451.2854
20 | 1ST FLOOR COLUMN STEEL
| START DATE |  |  |  | 2015-01-19 |  |  | 2015-01-01 | 2015-01-11 | 2015-01-16 |  | 2015-01-23 | 2015-01-01 | 2015-01-11 | 2015-01-11 |  |  |  |  | 2015-01-01 | 2015-01-09
| Comp. Date |  |  |  | 2015-01-25 |  |  | 2015-01-05 | 2015-01-15 | 2015-01-22 |  | 2015-01-29 | 2015-01-05 | 2015-01-17 | 2015-01-17 |  |  |  |  | 2015-01-05 | 2015-01-15
| QTY KG |  |  |  | 5470 |  |  | 5160 | 7450 | 5160 |  | 7430 | 7450 | 7480 | 7830 |  |  |  |  | 12201 | 8230 | 73861
21 | 1ST FLOOR COLUMN SHUTTERING
| START DATE |  |  |  | 2015-01-21 |  |  | 2015-01-03 | 2015-01-13 | 2015-01-18 |  | 2015-01-25 | 2015-01-03 | 2015-01-13 | 2015-01-13 |  |  |  |  | 2015-01-03 | 2015-01-11
| Comp. Date |  |  |  | 2015-01-25 |  |  | 2015-01-05 | 2015-01-15 | 2015-01-22 |  | 2015-01-29 | 2015-01-05 | 2015-01-17 | 2015-01-17 |  |  |  |  | 2015-01-05 | 2015-01-15
| Qty SQM |  |  |  | 144.5 |  |  | 130.0162 | 187.7141 | 130.0162 |  | 187.2226 | 187.7141 | 188.54 | 197.21 |  |  |  |  | 277.53 | 214.02 | 1844.4832
22 | 1ST FLOOR COLUMN RCC
| START DATE |  |  |  | 2015-01-21 |  |  | 2015-01-03 | 2015-01-13 | 2015-01-18 |  | 2015-01-25 | 2015-01-03 | 2015-01-13 | 2015-01-13 |  |  |  |  | 2015-01-03 | 2015-01-11
| Comp. Date |  |  |  | 2015-01-26 |  |  | 2015-01-06 | 2015-01-16 | 2015-01-23 |  | 2015-01-30 | 2015-01-06 | 2015-01-18 | 2015-01-18 |  |  |  |  | 2015-01-06 | 2015-01-16
| Qty CUM |  |  |  | 14.9 |  |  | 17.3355 | 25.0285 | 17.3355 |  | 24.963 | 25.0285 | 19.05 | 19.93 |  |  |  |  | 28.84 | 22.19 | 214.6011
23 | 1ST FLOOR ROOF BEAM SLAB SHUTTERING
| START DATE | [6 empty] | 2015-01-07 | 2015-01-17 | 2015-01-24 |  |  | 2015-01-07 | 2015-01-19 | 2015-01-19 |  |  |  | 2015-01-01 | 2015-01-07 | 2015-01-17
| Comp. Date | [6 empty] | 2015-01-14 | 2015-01-22 | 2015-01-30 |  |  | 2015-01-14 | 2015-01-26 | 2015-01-26 |  |  |  | 2015-01-06 | 2015-01-12 | 2015-01-22
| Qty SQM | [6 empty] | 415.576 | 600 | 415.576 |  |  | 600 | 626.387 | 655.24 |  |  |  | 918.36 | 914.27 | 721.43 | 5866.839
24 | 1ST FLOOR ROOF BEAM SLAB STEEL
| START DATE | [6 empty] | 2015-01-09 | 2015-01-19 | 2015-01-26 |  |  | 2015-01-09 | 2015-01-21 | 2015-01-21 |  |  |  | 2015-01-03 | 2015-01-09 | 2015-01-19
| Comp. Date | [6 empty] | 2015-01-14 | 2015-01-25 | 2015-01-30 |  |  | 2015-01-15 | 2015-01-27 | 2015-01-27 |  |  |  | 2015-01-07 | 2015-01-13 | 2015-01-23
| QTY KG | [6 empty] | 7400 | 10690 | 7400 |  |  | 10690 | 10730 | 11230 |  |  |  | 16640 | 16200 | 13001 | 103981
25 | 1ST FLOOR ROOF BEAM SLAB RCC
| START DATE | [6 empty] | 2015-01-15 | 2015-01-26 | 2015-01-31 |  |  | 2015-01-16 | 2015-01-28 | 2015-01-28 |  |  |  | 2015-01-08 | 2015-01-14 | 2015-01-24
| Comp. Date | [6 empty] | 2015-01-16 | 2015-01-26 | 2015-01-31 |  |  | 2015-01-16 | 2015-01-28 | 2015-01-28 |  |  |  | 2015-01-09 | 2015-01-15 | 2015-01-24
| Qty CUM | [6 empty] | 48.9696 | 70.7 | 48.9696 |  |  | 70.7 | 66.02 | 68.97 |  |  |  | 107.26 | 106.19 | 74.31 | 662.0891
26 | 2 ND FLOOR COLUMN STEEL
| START DATE | [6 empty] | 2015-01-17 | 2015-01-27 |  | 2015-01-01 |  | 2015-01-17 |  |  | 2015-01-01 | 2015-01-01 |  | 2015-01-10 | 2015-01-16 | 2015-01-25
| Comp. Date | [6 empty] | 2015-01-21 | 2015-01-30 |  | 2015-01-04 |  | 2015-01-23 |  |  | 2015-01-06 | 2015-01-06 |  | 2015-01-15 | 2015-01-22 | 2015-01-31
| QTY KG | [6 empty] | 5160 | 7450 |  | 7430 |  | 7450 |  |  | 7230 | 7230 |  | 11610 | 12201.05 | 8230 | 73991.05
27 | 2ND FLOOR COLUMN SHUTTERING
| START DATE | [6 empty] | 2015-01-19 | 2015-01-29 |  | 2015-01-03 |  | 2015-01-19 |  |  | 2015-01-02 | 2015-01-02 |  | 2015-01-11 | 2015-01-18 | 2015-01-27 |  | 362712
| Comp. Date | [6 empty] | 2015-01-21 | 2015-01-30 |  | 2015-01-04 |  | 2015-01-23 |  |  | 2015-01-07 | 2015-01-07 |  | 2015-01-16 | 2015-01-22 | 2015-01-31
| Qty SQM | [6 empty] | 130.0162 | 187.7141 |  | 187.2226 |  | 187.7141 |  |  | 190.53 | 190.53 |  | 287.97 | 277.53 | 214.02 | 1853.247
28 | 2 ND FLOOR COLUMN RCC
| START DATE | [6 empty] | 2015-01-19 | 2015-01-29 |  | 2015-01-03 |  | 2015-01-19 |  |  | 2015-01-02 | 2015-01-02 |  | 2015-01-11 | 2015-01-18 | 2015-01-27
| Comp. Date | [6 empty] | 2015-01-22 | 2015-01-31 |  | 2015-01-05 |  | 2015-01-24 |  |  | 2015-01-07 | 2015-01-07 |  | 2015-01-16 | 2015-01-23 | 2015-02-01
| Qty CUM | [6 empty] | 17.3355 | 25.0285 |  | 24.963 |  | 25.0285 |  |  | 19.71 | 19.71 |  | 29.88 | 28.84 | 22.19 | 212.6856
29 | 2 ND FLOOR ROOF BEAM SLAB SHUTTERING
| START DATE | [6 empty] | 2015-01-23 |  |  | 2015-01-06 |  | 2015-01-25 |  |  | 2015-01-08 | 2015-01-08 |  | 2015-01-17 | 2015-01-24
| Comp. Date | [6 empty] | 2015-01-30 |  |  | 2015-01-13 |  | 2015-02-01 |  |  | 2015-01-13 | 2015-01-13 |  | 2015-01-22 | 2015-01-29
| Qty SQM | [6 empty] | 415.576 |  |  | 598.427 |  | 600 |  |  | 651.88 | 651.88 |  | 918.36 | 914.27 |  | 4750.393
30 | 2 ND FLOOR ROOF BEAM SLAB STEEL
| START DATE | [6 empty] | 2015-01-25 |  |  | 2015-01-08 |  | 2015-01-27 |  |  | 2015-01-10 | 2015-01-10 |  | 2015-01-19 | 2015-01-26
| Comp. Date | [6 empty] | 2015-01-30 |  |  | 2015-01-15 |  | 2015-02-02 |  |  | 2015-01-14 | 2015-01-14 |  | 2015-01-23 | 2015-01-30
| QTY KG | [6 empty] | 7400 |  |  | 12440 |  | 10690 |  |  | 11585 | 11585 |  | 16640 | 16200 |  | 86540
31 | 2 ND FLOOR ROOF BEAM SLAB RCC
| START DATE | [6 empty] | 2015-01-30 |  |  | 2015-01-16 |  | 2015-02-03 |  |  | 2015-01-15 | 2015-01-15 |  | 2015-01-24 | 2015-01-31
| Comp. Date | [6 empty] | 2015-01-31 |  |  | 2015-01-16 |  | 2015-02-03 |  |  | 2015-01-15 | 2015-01-15 |  | 2015-01-24 | 2015-01-31
| Qty CUM | [6 empty] | 48.9696 |  |  | 70.5159 |  | 70.7 |  |  | 69.05 | 69.05 |  | 107.26 | 106.19 |  | 541.7354
32 | 3RD FLOOR COLUMN STEEL
| START DATE | [9 empty] | 2015-01-17 |  |  |  |  | 2015-01-16 | 2015-01-16 |  | 2015-01-25
| Comp. Date | [9 empty] | 2015-01-20 |  |  |  |  | 2015-01-21 | 2015-01-21 |  | 2015-01-30
| QTY KG | [9 empty] | 7430 |  |  |  |  | 7230 | 7230 |  | 11610 |  |  | 33500
33 | 3RD FLOOR COLUMN SHUTTERING
| START DATE | [9 empty] | 2015-01-19 |  |  |  |  | 2015-01-17 | 2015-01-17 |  | 2015-01-26
| Comp. Date | [9 empty] | 2015-01-20 |  |  |  |  | 2015-01-22 | 2015-01-22 |  | 2015-01-31
| Qty SQM | [9 empty] | 187.2226 |  |  |  |  | 190.53 | 190.53 |  | 287.97 |  |  | 856.2526
34 | 3RD FLOOR COLUMN RCC
| START DATE | [9 empty] | 2015-01-19 |  |  |  |  | 2015-01-17 | 2015-01-17 |  | 2015-01-26
| Comp. Date | [9 empty] | 2015-01-21 |  |  |  |  | 2015-01-22 | 2015-01-22 |  | 2015-01-31
| Qty CUM | [9 empty] | 24.963 |  |  |  |  | 19.71 | 19.71 |  | 29.88 |  |  | 94.263
35 | 3RD FLOOR ROOF BEAM SLAB SHUTTERING
| START DATE | [9 empty] | 2015-01-22 |  |  |  |  | 2015-01-23 | 2015-01-23 | 2015-01-01
| Comp. Date | [9 empty] | 2015-01-29 |  |  |  |  | 2015-01-28 | 2015-01-28 | 2015-01-04
| Qty SQM | [9 empty] | 598.427 |  |  |  |  | 651.88 | 651.88 | 721.4 |  |  |  | 2623.587
36 | 3RD FLOOR ROOF BEAM SLAB STEEL
| START DATE | [9 empty] | 2015-01-24 |  |  |  |  | 2015-01-25 | 2015-01-25 | 2015-01-05
| Comp. Date | [9 empty] | 2015-01-30 |  |  |  |  | 2015-01-29 | 2015-01-29 | 2015-01-10
| QTY KG | [9 empty] | 12440 |  |  |  |  | 11585 | 11585 | 13001 |  |  |  | 48611
37 | 3RD FLOOR ROOF BEAM SLAB RCC
| START DATE | [9 empty] | 2015-01-31 |  |  |  |  | 2015-01-30 | 2015-01-30 | 2015-01-06
| Comp. Date | [9 empty] | 2015-01-31 |  |  |  |  | 2015-01-30 | 2015-01-30 | 2015-01-10
| Qty CUM | [9 empty] | 70.5159 |  |  |  |  | 69.05 | 69.05 | 74.31 |  |  |  | 282.9259
38 | 4TH FLOOR COLUMN STEEL
| START DATE | [16 empty] | 2015-01-11
| Comp. Date | [16 empty] | 2015-01-15
| QTY KG | [16 empty] | 8230 |  |  |  | 8230
39 | 4TH FLOOR COLUMN SHUTTERING
| START DATE | [16 empty] | 2015-01-12
| Comp. Date | [16 empty] | 2015-01-17
| Qty SQM | [16 empty] | 214.02 |  |  |  | 214.02
40 | 4TH FLOOR COLUMN RCC
| START DATE | [16 empty] | 2015-01-12
| Comp. Date | [16 empty] | 2015-01-17
| Qty CUM | [16 empty] | 22.19 |  |  |  | 22.19
41 | 4TH FLOOR ROOF BEAM SLAB SHUTTERING
| START DATE | [16 empty] | 2015-01-18
| Comp. Date | [16 empty] | 2015-01-23
| Qty SQM | [16 empty] | 721.4 |  |  |  | 721.4
42 | 4TH FLOOR ROOF BEAM SLAB STEEL
| START DATE | [16 empty] | 2015-01-19
| Comp. Date | [16 empty] | 2015-01-24
| QTY KG | [16 empty] | 13001 |  |  |  | 13001
43 | 4TH FLOOR ROOF BEAM SLAB RCC
| START DATE | [16 empty] | 2015-01-24
| Comp. Date | [16 empty] | 2015-01-24
| Qty CUM | [16 empty] | 74.31 |  |  |  | 74.31
44 | 5 TH FLOOR COLUMN STEEL
| START DATE | [16 empty] | 2015-01-25
| Comp. Date | [16 empty] | 2015-01-30
| QTY KG | [16 empty] | 7670 |  |  |  | 7670
45 | 5 TH FLOOR COLUMN SHUTTERING
| START DATE | [16 empty] | 2015-01-26
| Comp. Date | [16 empty] | 2015-01-31
| Qty SQM | [16 empty] | 214.02 |  |  |  | 214.02
46 | 5 TH FLOOR COLUMN RCC
| START DATE | [16 empty] | 2015-01-26
| Comp. Date | [16 empty] | 2015-01-31
| Qty CUM | [16 empty] | 22.19 |  |  |  | 22.19
47 | 5 TH FLOOR ROOF BEAM SLAB SHUTTERING
START DATE
Comp. Date
| Qty SQM | [20 empty] | 0
48 | 5 TH FLOOR ROOF BEAM SLAB STEEL
START DATE
Comp. Date
| QTY KG | [20 empty] | 0
49 | 5 TH FLOOR ROOF BEAM SLAB RCC
START DATE
Comp. Date
| Qty CUM | [20 empty] | 0
50 | BLOCK WORK IN 1ST FLOOR
| START DATE | [9 empty] | 2015-01-16
| Comp. Date | [9 empty] | 2015-01-31
| Qty CUM | [9 empty] | 112.216 | [6 empty] | 119.28 |  |  |  | 231.496
51 | BLOCK WORK IN 2ND FLOOR
START DATE
Comp. Date
| Qty CUM | [16 empty] | 119.28 |  |  |  | 119.28
52 | DOOR,WINDOW FRAME&SHUTTER FIXING IN 1ST FLOOR
START DATE
Comp. Date
| Qty CUM | [20 empty] | 0
53 | DOOR,WINDOW FRAME &SHUTTER FIXINGFRAME FIXING IN 2ND FLOOR
START DATE
Comp. Date
| Qty CUM | [20 empty] | 0
Formulas:
T-3 = +[T-2, row below]
T-3 = +[T-3, row above]+7
T- 6 = +[T-3, row below]
T- 6 = +[T- 6, row above]+7
T-2 = +[T-2, row above]+7
T-2 = +[T-2, row above]
CLUSTER-2 = +[CLUSTER-2, row above]+15
CLUSTER-2 = +[CLUSTER-2, row above]
CLUSTER-1 = +[CLUSTER-1, row above]+6
T-5 = +[T-5, row above]+7
T-5 = +[T-5, row above]
T-4 = +[T-4, row above]+6
T-4 = +[T-4, row above]
CLUSTER-3 = +[CLUSTER-3, row above]+4
CLUSTER-3 = +[CLUSTER-3, row above]
T- 4 = +[T- 4, row above]+4
T- 4 = +[T- 4, row above]
T-1 = +[T-1, row above]+3
T-1 = +[T-1, row above]
CLUSTER-4 = +[CLUSTER-4, row above]+5
CLUSTER-4 = +[CLUSTER-4, row above]
T-6 = +[T-6, row above]+5
T-6 = +[T-6, row above]

## PI BUDGET (JAN-15)
4
|  |  |  | 0 | 87382002.8991 |  | 87382002.8991 | #REF!
PROJECT INCHARGE - SH K.K.VERMA
BUDEGT FOR M/O JAN 2015
DDA KALKAJI |  |  | PROJECT INCHAGE: Mr. ZAHIR KHAN |  |  | ALL CLUSTER
SI. No. | Description | Unit | QUANTITY | BOQ Rate | AMOUNT | QTY | AMOUNT
| SUB-HEAD - I: EARTH WORK |  |  |  |  | 0 | 0
2.7 | Earth work in excavation by mechanical means (Hydraulic excavator) / manual means in over areas (exceeding 30cm in depth 1.5m in width or 10 sqm on plan) including disposal of excavated earth, lead upto 50 m and lift upto 1.50m, disposed earth to be levelled and neatly dressed. |  |  |  |  | 0 | 0
2.7.1 | Ordinary rock | Cum | 4749.3 | 88.4292 | 419976.8248 | 4749.3 | 419976.8248
|  |  | 0 |  | 0 | 0 | 0 | #REF!
2.25 | Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundation etc. in layers not exceeding 20 cm in depth: consolidating each deposited layer by ramming and watering, lead upto 50 m and lift upto 1.5 m | Cum | 3180 | 44.2146 | 140602.4365 | 3180 | 140602.4365 | #REF!
[5 empty] | 0 | 0 | 0 | #REF!
2.26 | Extra for every additional lift of 1.5 m or part thereof in excavation /banking excavated or stacked materials. All kinds of soil. |  |  |  | 0 | 0 | 0 | #REF!
2.26.2 | Ordinary or hard rock. | cum | 2849.58 | 22.1073 | 62996.5237 | 2849.58 | 62996.5237 | #REF!
[5 empty] | 0 | 0 | 0 | #REF!
2.27 | Supplying and filling in plinth with Jamuna sand under floors including, watering, ramming consolidating and dressing complete. | Cum |  |  | 0 | 0 | 0 | #REF!
[5 empty] | 0 | 0 | 0 | #REF!
NS (DSR Based 23.2) | Supplying & stacking of good earth by mechanical transport including loading, unloading and stacking all leads including filling, inlayers not exceeding 20 cm in depth consolidating each deposited layer by ramming and watering any lead. | Cum |  | 295 | 0 | 0 | 0 | #REF!
[5 empty] | 0 | 0 | 0 | #REF!
| SUB-HEAD - II: PCC WORK |  |  |  | 0 | 0 | 0 | #REF!
| Providing & laying in position cement concrete of specified grade excluding the cost of centering and shuttering - All work upto plinth level. |  |  |  | 0 | 0 | 0 | #REF!
4.1.8 | 1:4:8 (1 Cement : 4 coarse sand : 8 graded stone aggregate 40 mm nominal size) | Cum |  |  | 0 | 0 | 0 | #REF!
[5 empty] | 0 | 0 | 0 | #REF!
4.1.10 | 1:5:10 (1cement: 5 coarse sand: 10 stone aggregate 40mm nominal size) | Cum | 151.1472 | 4011.7383 | 606362.9084 | 151.1472 | 606362.9084 | #REF!
[5 empty] | 0 | 0 | 0 | #REF!
N.S. (Based on DSR 4.17) | Making plinth protection 50mm thick of M-20 concrete over 75mm thick bed of dry brick ballast 40 mm nominal size, well rammed and consolidated and grouted with fine sand including finishing the top smooth. | Sqm |  |  | 0 | 0 | 0 | #REF!
| SUB-HEAD - III: RCC WORK |  |  |  | 0 | 0 | 0 | #REF!
[5 empty] | 0 | 0 | 0 | #REF!
5.9 | Centring and shuttering including strutting, propping etc. and removal of form for : |  |  |  | 0 | 0 | 0 | #REF!
5.9.1 | Foundations, footings, bases of columns, etc. for mass concrete. | Sqm | 256.42 | 316.8713 | 81252.1436 | 256.42 | 81252.1436 | #REF!
5.9.2 | Walls (any thickness) i/c attached pilasters, butteresses, plinth and string courses etc. | Sqm | 533.26 | 300 | 159978 | 533.26 | 159978 | #REF!
5.9.3 | Suspended floors, roofs, landings, balconies and access platform. | Sqm | 18070.4789 | 300 | 5421143.6584 | 18070.4789 | 5421143.6584 | #REF!
5.9.4 | Shelves (Cast-in -situ) | Sqm |  |  | 0 | 0 | 0 | #REF!
5.9.5 | Lintels, beams, plinth beams, girders, bressumers and cantilevers. | Sqm | 515.2 | 280.0258 | 144269.3008 | 515.2 | 144269.3008 | #REF!
5.9.6 | Columns, Pillars, Piers, Abutments, Posts and Struts | Sqm | 6375.2316 | 365.6 | 2330784.6621 | 6375.2316 | 2330784.6621 | #REF!
5.9.7 | Stairs, (excluding landings) except spiral stair-cases | Sqm |  |  | 0 | 0 | 0 | #REF!
5.9.16 | Edges of slabs and breaks in floors and walls. |  |  |  | 0 | 0 | 0 | #REF!
5.9.16.1 | Under 20 cm wide | Mtr |  |  | 0 | 0 | 0 | #REF!
[5 empty] | 0 | 0 | 0 | #REF!
| Providing precast cement concrete Jali 1:2:4 (1 cement : 2 coarse sand: 4 graded stone aggregate 6 mm nominal size), reinforced with 1.6 mm dia mild steel wire, including centering and shuttering, roughening cleaning, fixing and finishing in cement mortar 1:3 (1 cement: 3 fine sand) etc. complete, excluding plastering of the jambs, sills and soffits. |  |  |  | 0 | 0 | 0 | #REF!
5.18.2 | 40 mm thick | Sqm |  |  | 0 | 0 | 0 | #REF!
[5 empty] | 0 | 0 | 0 | #REF!
5.22 | Steel reinforcement for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete up to plinth level. |  |  |  | 0 | 0 | 0 | #REF!
5.22.6 | Thermo-Mechanically Treated bars | Kg | 96649 | 81.2075 | 7848622.4004 | 96649 | 7848622.4004 | #REF!
[5 empty] | 0 | 0 | 0 | #REF!
5.22A | Steel reinforcement for for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete above plinth level. |  |  |  | 0 | 0 | 0 | #REF!
5.22A.6 | Thermo-Mechanically Treated bars | Kg | 540786.05 | 81.2075 | 43915876.0656 | 540786.05 | 43915876.0656 | #REF!
[5 empty] | 0 | 0 | 0 | #REF!
NS | Providing and fixing sheet covering over expansion joints with iron screws as per design. |  |  |  | 0 | 0 | 0 | #REF!
(Based on DSR 5.29.1) | Non-absestos fibre cement board 6 mm thick as per IS : 148862 - 350 mm wide | mtr |  |  | 0 | 0 | 0 | #REF!
[5 empty] | 0 | 0 | 0 | #REF!
(Based on DSR 5.29.2) | Aluminium fluted stips 3.15 mm thick 350 mm wide | mtr |  |  | 0 | 0 | 0 | #REF!
[5 empty] | 0 | 0 | 0 | #REF!
5.34 | Extra for providing richer mixes at all floor levels. Note:- Excess/less cement over the specified cement content used is payable /recoverable separately. |  |  |  | 0 | 0 | 0 | #REF!
5.34.1 | Providing M-30 grade concrete instead of M-25 grade BMC/RMC. (Note:- Cement content considered in M-30 is @ 340 kg/cum). | cum | 739.6782 | 751.6482 | 555977.8281 | 739.6782 | 555977.8281 | #REF!
[5 empty] | 0 | 0 | 0 | #REF!
5.37 | Providing & laying in position ready mixed M-25 grade concrete for reinforced cement concrete work, using cement content as per approved mix design manufactured in fully automatic batching plant and transported to site of work in transit mixer for all leads having continuous agitated mixer, manufactured as per mix design of specified grade for reinforced cement concrete work including pumping of RMC from transit mixer to site of laying, excluding the cost of centering, shuttering finishing and reinforcement including cost of admixtures in recommended proportions as per IS:9103 to accelerate/ retard setting of concrete, improve workability without impairing strength and durability as per direction of the Engineer-in-charge. Cement content is considered in this item is @ 330 kg/cum. Excess/less cement used as per design mix is payable/recoverable separately). |  |  |  | 0 | 0 | 0 | #REF!
5.37.1 | All works up to plinth level | Cum | 1075.105 | 6296.012 | 6768874.0212 | 1075.105 | 6768874.0212 | #REF!
| All works above plinth upto floor V level | Cum | 2635.4741 | 6296.012 | 16592976.5014 | 2635.4741 | 16592976.5014 | #REF!
[5 empty] | 0 | 0 | 0 | #REF!
5.38 | Extra for R.C.C./ B.M.C/ R.M.C. work above floor V level for each four floors or part thereof. | Cum |  |  | 0 | 0 | 0 | #REF!
[5 empty] | 0 | 0 | 0 | #REF!
NS (Based on DSR 5.43) | Providing and fixing in position Stainless steel Grade 304 plate-1.0 mm thick as per design for expansion joints. | mtr |  |  | 0 | 0 | 0 | #REF!
N.S. (DSR Based) | Providing & laying Autoclaved Areatd Cement blocks masonary with 200mm thick AAC Blocks in super structure above plinth level upto floor V level in Cement mortar 1:4 (1 cement : 4 coarse sand) | Cum | 350.776 | 6649 | 2332309.624
[5 empty] | 0 | 0 | 0 | #REF!
| FINAL AMOUNT- BOQ |  |  |  | 0 | 0 | 0 | #REF!
0
[5 empty] | 87382002.8991 |  | 87382002.8991 | #REF!

## Cumulative DPR
1
[14 empty] | DATE : | 2015-01-01
BUDGET v/s ACHIEVEMENT ON DAILY/ MONHTLY BASIS | [5 empty] | PROJECT : In Situ Rehabilitation at A-14, Kakalkaji Extn. New Delhi- 19
LOCATION : New Delhi
TEAM NAME: Zahir Mohmmad
S. No. | Item/ Acitvity | Unit | Rate | Quantity | Amount | BUDGETED QUANTITY | [5 empty] | ACHIEVED QUANTITY |  |  | % Achieved as per the revised budget | % achieved as per actual monthly budget | Budget for next day
[6 empty] | Upto Previous | For current day | Cumulative upto date | Revised budget upto previous day | Revised budget for today | Cumulative revised upto date | Upto previous date | For today | Cumulative upto date |  |  | Quantity | Amount
|  |  | A |  |  | B | C | B+C = R | H | D | H+D=Z | E | F | E+F=Y | Y/Z | Y/R | G | G*A
SUB-HEAD - I: EARTH WORK
2.7 | Earth work in excavation by mechanical means (Hydraulic excavator) / manual means in over areas (exceeding 30cm in depth 1.5m in width or 10 sqm on plan) including disposal of excavated earth, lead upto 50 m and lift upto 1.50m, disposed earth to be levelled and neatly dressed. |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
2.7.1 | Ordinary rock | Cum | 88.4292 | 4749.3 | 419976.8248 |  | 158.31 | 158.31 |  |  | 0 |  |  | 0 | #DIV/0! | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
2.25 | Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundation etc. in layers not exceeding 20 cm in depth: consolidating each deposited layer by ramming and watering, lead upto 50 m and lift upto 1.5 m | Cum | 44.2146 | 3180 | 140602.4365 |  | 106 | 106 |  |  | 0 |  |  | 0 | #DIV/0! | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
2.26 | Extra for every additional lift of 1.5 m or part thereof in excavation /banking excavated or stacked materials. All kinds of soil. |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
2.26.2 | Ordinary or hard rock. | cum | 22.1073 | 2849.58 | 62996.5237 |  | 94.986 | 94.986 |  |  | 0 |  |  | 0 | #DIV/0! | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
2.27 | Supplying and filling in plinth with Jamuna sand under floors including, watering, ramming consolidating and dressing complete. | Cum |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
|  |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
NS (DSR Based 23.2) | Supplying & stacking of good earth by mechanical transport including loading, unloading and stacking all leads including filling, inlayers not exceeding 20 cm in depth consolidating each deposited layer by ramming and watering any lead. | Cum | 295 | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
|  |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
| SUB-HEAD - II: PCC WORK |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
| Providing & laying in position cement concrete of specified grade excluding the cost of centering and shuttering - All work upto plinth level. |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
4.1.8 | 1:4:8 (1 Cement : 4 coarse sand : 8 graded stone aggregate 40 mm nominal size) | Cum |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
|  |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
4.1.10 | 1:5:10 (1cement: 5 coarse sand: 10 stone aggregate 40mm nominal size) | Cum | 4011.7383 | 151.1472 | 606362.9084 |  | 5.0382 | 5.0382 |  |  | 0 |  |  | 0 | #DIV/0! | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
N.S. (Based on DSR 4.17) | Making plinth protection 50mm thick of M-20 concrete over 75mm thick bed of dry brick ballast 40 mm nominal size, well rammed and consolidated and grouted with fine sand including finishing the top smooth. | Sqm |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
| SUB-HEAD - III: RCC WORK |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
|  |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
5.9 | Centring and shuttering including strutting, propping etc. and removal of form for : |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
5.9.1 | Foundations, footings, bases of columns, etc. for mass concrete. | Sqm | 316.8713 | 256.42 | 81252.1436 |  | 8.5473 | 8.5473 |  |  | 0 |  |  | 0 | #DIV/0! | 0 |  | 0
5.9.2 | Walls (any thickness) i/c attached pilasters, butteresses, plinth and string courses etc. | Sqm | 300 | 533.26 | 159978 |  | 17.7753 | 17.7753 |  |  | 0 |  |  | 0 | #DIV/0! | 0 |  | 0
5.9.3 | Suspended floors, roofs, landings, balconies and access platform. | Sqm | 300 | 18070.4789 | 5421143.6584 |  | 602.3493 | 602.3493 |  |  | 0 |  |  | 0 | #DIV/0! | 0 |  | 0
5.9.4 | Shelves (Cast-in -situ) | Sqm |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
5.9.5 | Lintels, beams, plinth beams, girders, bressumers and cantilevers. | Sqm | 280.0258 | 515.2 | 144269.3008 |  | 17.1733 | 17.1733 |  |  | 0 |  |  | 0 | #DIV/0! | 0 |  | 0
5.9.6 | Columns, Pillars, Piers, Abutments, Posts and Struts | Sqm | 365.6 | 6375.2316 | 2330784.6621 |  | 212.5077 | 212.5077 |  |  | 0 |  |  | 0 | #DIV/0! | 0 |  | 0
5.9.7 | Stairs, (excluding landings) except spiral stair-cases | Sqm |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
5.9.16 | Edges of slabs and breaks in floors and walls. |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
5.9.16.1 | Under 20 cm wide | Mtr |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
|  |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
| Providing precast cement concrete Jali 1:2:4 (1 cement : 2 coarse sand: 4 graded stone aggregate 6 mm nominal size), reinforced with 1.6 mm dia mild steel wire, including centering and shuttering, roughening cleaning, fixing and finishing in cement mortar 1:3 (1 cement: 3 fine sand) etc. complete, excluding plastering of the jambs, sills and soffits. |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
5.18.2 | 40 mm thick | Sqm |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
|  |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
5.22 | Steel reinforcement for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete up to plinth level. |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
5.22.6 | Thermo-Mechanically Treated bars | Kg | 81.2075 | 96649 | 7848622.4004 |  | 3221.6333 | 3221.6333 |  |  | 0 |  |  | 0 | #DIV/0! | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
5.22A | Steel reinforcement for for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete above plinth level. |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
5.22A.6 | Thermo-Mechanically Treated bars | Kg | 81.2075 | 540786.05 | 43915876.0656 |  | 18026.2017 | 18026.2017 |  |  | 0 |  |  | 0 | #DIV/0! | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
NS | Providing and fixing sheet covering over expansion joints with iron screws as per design. |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
(Based on DSR 5.29.1) | Non-absestos fibre cement board 6 mm thick as per IS : 148862 - 350 mm wide | mtr |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
|  |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
(Based on DSR 5.29.2) | Aluminium fluted stips 3.15 mm thick 350 mm wide | mtr |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
|  |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
5.34 | Extra for providing richer mixes at all floor levels. Note:- Excess/less cement over the specified cement content used is payable /recoverable separately. |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
5.34.1 | Providing M-30 grade concrete instead of M-25 grade BMC/RMC. (Note:- Cement content considered in M-30 is @ 340 kg/cum). | cum | 751.6482 | 739.6782 | 555977.8281 |  | 24.6559 | 24.6559 |  |  | 0 |  |  | 0 | #DIV/0! | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
5.37 | Providing & laying in position ready mixed M-25 grade concrete for reinforced cement concrete work, using cement content as per approved mix design manufactured in fully automatic batching plant and transported to site of work in transit mixer for all leads having continuous agitated mixer, manufactured as per mix design of specified grade for reinforced cement concrete work including pumping of RMC from transit mixer to site of laying, excluding the cost of centering, shuttering finishing and reinforcement including cost of admixtures in recommended proportions as per IS:9103 to accelerate/ retard setting of concrete, improve workability without impairing strength and durability as per direction of the Engineer-in-charge. Cement content is considered in this item is @ 330 kg/cum. Excess/less cement used as per design mix is payable/recoverable separately). |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
5.37.1 | All works up to plinth level | Cum | 6296.012 | 1075.105 | 6768874.0212 |  | 35.8368 | 35.8368 |  |  | 0 |  |  | 0 | #DIV/0! | 0 |  | 0
| All works above plinth upto floor V level | Cum | 6296.012 | 2635.4741 | 16592976.5014 |  | 87.8491 | 87.8491 |  |  | 0 |  |  | 0 | #DIV/0! | 0 |  | 0
|  |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
5.38 | Extra for R.C.C./ B.M.C/ R.M.C. work above floor V level for each four floors or part thereof. | Cum |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
|  |  |  | 0 | 0 |  | 0 |  |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
NS (Based on DSR 5.43) | Providing and fixing in position Stainless steel Grade 304 plate-1.0 mm thick as per design for expansion joints. | mtr |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
N.S. (DSR Based) | Providing & laying Autoclaved Areatd Cement blocks masonary with 200mm thick AAC Blocks in super structure above plinth level upto floor V level in Cement mortar 1:4 (1 cement : 4 coarse sand) | Cum | 6649 | 350.776 | 2332309.624 |  |  | 0 |  |  | 0 |  |  | 0 | #DIV/0! | #DIV/0! |  | 0
[5 empty] | 87382002.8991 | [12 empty] | 0
TOTAL WORK | [5 empty] | 0 | 2834989.7758 | 2834989.7758 |  | 0 | 0 |  | 0 | 0 |  |  |  | 0
TOTAL RESOURCE EXPENDITURE
20% expenditure loaded against overheads and misc
TOTAL Expenditure
NET SURPLUS/ DEFICIT
% surplus/ deficit
Total Manpower
Note: | 1. Shuttering Material required urgent for 04 towers.
2. Labour Rate not final till date.
3. Agency required with shuttering material.
4. Excavator breakdown
5. Electrical agency urgent required

## Mat & Labour cost
|  |  | 2015-01-01 | [9 empty] | 2
DD KALKA JI
SI. No. | Description | Unit | BUDGET QTY |  | RATE |  |  |  | BUDGET AMOUNT | AMOUNT
|  |  |  | Basic Rate | BOQ Rate | lab Rate | New Mat Rate | party Rate. |  | LABOUR AMOUNT | MATERIAL AMOUNT | PARTY AMOUNT
SUB-HEAD - I: EARTH WORK
2.7 | Earth work in excavation by mechanical means (Hydraulic excavator) / manual means in over areas (exceeding 30cm in depth 1.5m in width or 10 sqm on plan) including disposal of excavated earth, lead upto 50 m and lift upto 1.50m, disposed earth to be levelled and neatly dressed. | [8 empty] | 0 | 0 | 0
2.7.1 | Ordinary rock | Cum | 4749.3 | 60 | 88.4292 | 60 |  |  | 419976.8248 | 284958 | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
2.25 | Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundation etc. in layers not exceeding 20 cm in depth: consolidating each deposited layer by ramming and watering, lead upto 50 m and lift upto 1.5 m | Cum | 3180 | 30 | 44.2146 | 30 |  |  | 140602.4365 | 95400 | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
2.26 | Extra for every additional lift of 1.5 m or part thereof in excavation /banking excavated or stacked materials. All kinds of soil. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
2.26.2 | Ordinary or hard rock. | cum | 2849.58 | 15 | 22.1073 | 15 |  |  | 62996.5237 | 42743.7 | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
2.27 | Supplying and filling in plinth with Jamuna sand under floors including, watering, ramming consolidating and dressing complete. | Cum |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
NS (DSR Based 23.2) | Supplying & stacking of good earth by mechanical transport including loading, unloading and stacking all leads including filling, inlayers not exceeding 20 cm in depth consolidating each deposited layer by ramming and watering any lead. | Cum | 0 |  | 295 | 30 | 250 |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
| SUB-HEAD - II: PCC WORK |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
| Providing & laying in position cement concrete of specified grade excluding the cost of centering and shuttering - All work upto plinth level. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
4.1.8 | 1:4:8 (1 Cement : 4 coarse sand : 8 graded stone aggregate 40 mm nominal size) | Cum |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
4.1.10 | 1:5:10 (1cement: 5 coarse sand: 10 stone aggregate 40mm nominal size) | Cum | 151.1472 | 2722 | 4011.7383 | 275 | 2447 |  | 606362.9084 | 41565.4731 | 369857.1374 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
N.S. (Based on DSR 4.17) | Making plinth protection 50mm thick of M-20 concrete over 75mm thick bed of dry brick ballast 40 mm nominal size, well rammed and consolidated and grouted with fine sand including finishing the top smooth. | Sqm |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
| SUB-HEAD - III: RCC WORK |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
5.9 | Centring and shuttering including strutting, propping etc. and removal of form for : |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
5.9.1 | Foundations, footings, bases of columns, etc. for mass concrete. | Sqm | 256.42 | 215 | 316.8713 | 90 | 125 |  | 81252.1436 | 23077.8 | 32052.5 | 0
5.9.2 | Walls (any thickness) i/c attached pilasters, butteresses, plinth and string courses etc. | Sqm | 533.26 | 0 | 300 |  |  |  | 159978 | 0 | 0 | 0
5.9.3 | Suspended floors, roofs, landings, balconies and access platform. | Sqm | 18070.4789 | 235 | 300 | 110 | 125 |  | 5421143.6584 | 1987752.6747 | 2258809.8577 | 0
5.9.4 | Shelves (Cast-in -situ) | Sqm |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
5.9.5 | Lintels, beams, plinth beams, girders, bressumers and cantilevers. | Sqm | 515.2 | 190 | 280.0258 | 100 | 90 |  | 144269.3008 | 51520 | 46368 | 0
5.9.6 | Columns, Pillars, Piers, Abutments, Posts and Struts | Sqm | 6375.2316 | 230 | 365.6 | 100 | 130 |  | 2330784.6621 | 637523.157 | 828780.1041 | 0
5.9.7 | Stairs, (excluding landings) except spiral stair-cases | Sqm |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
5.9.16 | Edges of slabs and breaks in floors and walls. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
5.9.16.1 | Under 20 cm wide | Mtr |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
| Providing precast cement concrete Jali 1:2:4 (1 cement : 2 coarse sand: 4 graded stone aggregate 6 mm nominal size), reinforced with 1.6 mm dia mild steel wire, including centering and shuttering, roughening cleaning, fixing and finishing in cement mortar 1:3 (1 cement: 3 fine sand) etc. complete, excluding plastering of the jambs, sills and soffits. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
5.18.2 | 40 mm thick | Sqm |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
5.22 | Steel reinforcement for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete up to plinth level. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
5.22.6 | Thermo-Mechanically Treated bars | Kg | 96649 | 55.1 | 81.2075 | 3.6 | 51.5 |  | 7848622.4004 | 347936.4 | 4977423.5 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
5.22A | Steel reinforcement for for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete above plinth level. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
5.22A.6 | Thermo-Mechanically Treated bars | Kg | 540786.05 | 55.1 | 81.2075 | 3.6 | 51.5 |  | 43915876.0656 | 1946829.78 | 27850481.575 | 0
|  |  |  | 0 | 0 |  |  |  |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
NS | Providing and fixing sheet covering over expansion joints with iron screws as per design. |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
(Based on DSR 5.29.1) | Non-absestos fibre cement board 6 mm thick as per IS : 148862 - 350 mm wide | mtr |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
(Based on DSR 5.29.2) | Aluminium fluted stips 3.15 mm thick 350 mm wide | mtr |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
5.34 | Extra for providing richer mixes at all floor levels. Note:- Excess/less cement over the specified cement content used is payable /recoverable separately. |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0
5.34.1 | Providing M-30 grade concrete instead of M-25 grade BMC/RMC. (Note:- Cement content considered in M-30 is @ 340 kg/cum). | cum | 739.6782 | 3728.04 | 751.6482 | 300 | 3428.04 |  | 555977.8281 | 221903.4628 | 2535646.4888 | 0
|  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
5.37 | Providing & laying in position ready mixed M-25 grade concrete for reinforced cement concrete work, using cement content as per approved mix design manufactured in fully automatic batching plant and transported to site of work in transit mixer for all leads having continuous agitated mixer, manufactured as per mix design of specified grade for reinforced cement concrete work including pumping of RMC from transit mixer to site of laying, excluding the cost of centering, shuttering finishing and reinforcement including cost of admixtures in recommended proportions as per IS:9103 to accelerate/ retard setting of concrete, improve workability without impairing strength and durability as per direction of the Engineer-in-charge. Cement content is considered in this item is @ 330 kg/cum. Excess/less cement used as per design mix is payable/recoverable separately). |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
5.37.1 | All works up to plinth level | Cum | 1075.105 | 3281.25 | 6296.012 | 300 | 2981.25 |  | 6768874.0212 | 322531.5 | 3205156.7812 | 0
| All works above plinth upto floor V level | Cum | 2635.4741 | 3281.25 | 6296.012 | 300 | 2981.25 |  | 16592976.5014 | 790642.2226 | 7857007.0869 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
5.38 | Extra for R.C.C./ B.M.C/ R.M.C. work above floor V level for each four floors or part thereof. | Cum | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0
NS (Based on DSR 5.43) | Providing and fixing in position Stainless steel Grade 304 plate-1.0 mm thick as per design for expansion joints. | mtr | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
N.S. (DSR Based) | Providing & laying Autoclaved Areatd Cement blocks masonary with 200mm thick AAC Blocks in super structure above plinth level upto floor V level in Cement mortar 1:4 (1 cement : 4 coarse sand) | Cum | 350.776 | 4512 | 6649 | 550 | 3962 |  | 2332309.624 | 192926.8 | 1389774.512
| FINAL AMOUNT | [7 empty] | 873.82 | 69.8731 | 513.5136 | 0
6649.8762
1 | AS PER GREEN BOOK BASIC AMT OF BUILD WORK | [8 empty] | 12395 | Lacs
2 | AS PER CLIENT MILE STONE AMT OF BUILD WORK | [8 empty] | 18268
| % of above on Basic | [8 empty] | 1.4738
A- | Material :
S.NO. | Descriptions | Unit | Total required | Available AT SITE | Net Required | Rate | TOTAL material Amount
1 | Cement | Bag | 22763.3175 |  | 22763.3175 | 265 | 6032279.1262
2 | C/ Sand | MT | 2494.0525 |  | 2494.0525 | 988.68 | 2465819.8416
3 | Agg- 10 mm | MT | 1359.3573 |  | 1359.3573 | 1030.28 | 1400518.6274
4 | Agg- 20 mm | MT | 2041.9026 |  | 2041.9026 | 1030.28 | 2103731.3624
5 | Agg- 40 mm | MT | 0 |  | 0 | 1030.28 | 0
6 | Admixture | Kg | 7496.8639 |  | 7496.8639 | 39.25 | 294251.9062
7 | Inihabitaor Solution | Kg | 12099.5877 |  | 12099.5877 | 27 | 326688.8679
8 | BRICKS 2ND QUALITY | NOS. | 30000 |  | 30000 | 4 | 120000
9 | TMT Steel |  |  |  | 0 |  | 0
10 | TMT STEEL MS 8 MM | KG | 144995.9123 |  | 144995.9123 | 51.119 | 7412046.0404
11 | TMT STEEL MS 10 MM | KG | 18423.0888 |  | 18423.0888 | 51.119 | 941769.8754
12 | TMT STEEL MS 12 MM | KG | 30807.6646 |  | 30807.6646 | 51.119 | 1574857.0065
13 | TMT STEEL MS 16 MM | KG | 80329.3141 |  | 80329.3141 | 51.119 | 4106354.206
14 | TMT STEEL MS 20 MM | KG | 109027.0686 |  | 109027.0686 | 51.119 | 5573354.7194
15 | TMT STEEL MS 25 MM | KG | 106155.2432 |  | 106155.2432 | 51.119 | 5426549.8784
16 | MS PIPE 40 MM (6 MTR LONG) | NOS. | 200 |  | 200 | 65 | 13000
17 | MS ANGLE 50*50*5 FOR COLUMN | KG | 4000 |  | 4000 | 55 | 220000
18 | Binding Wire | kg | 4407.6446 |  | 4407.6446 | 65 | 286496.9006
18 | GI SHEET | NOS. | 1000 |  | 1000 | 750 | 750000
[5 empty] | 0 |  | 39047718.3582

## GB SUMM(UP2013) (hidden)
ERA INFRA ENGINEERING LIMITED
PROJECT NAME : BHEL - CHENNAI(T.N.) (1335 )
GREEN BOOK (REVISED) MAY'13
MAY'13
|  | 11.44% |  | -1.28% | [8 empty] | 16.18% |  | 1.932%
S. No. | Description | %age as per initial GB | W/D upto FEB'13 | % upto MAY'13 | 2013-06-13 | 2013-07-13 | 2013-08-01 | 2013-09-01 | 2013-10-01 | 2013-11-01 | 2013-12-01 | Balance Work Done | %age on Balance Work | Gross Work | %age on Gross Work
A | Total works |  | 4514.2815 |  | 186.6932 | 180.4908 | 183.7422 | 184.1982 | 122.2878 | 56.6694 | 16.9531 | 931.0346 |  | 5445.3161 |  | 544531609.2967 | 5445.3161
rebate 5.38%
| Total Work Done |  | 4514.2815 |  | 186.6932 | 180.4908 | 183.7422 | 184.1982 | 122.2878 | 56.6694 | 16.9531 | 931.0346 |  | 5445.3161
| Exclation Bills (33%) |  | 949.1678 | 21.03% | 61.6087 | 59.562 | 60.6349 | 60.7854 | 40.355 | 18.7009 | 5.5945 | 307.2414 |  | 1256.4093
| Service Tax |  | 250.8322 | 5.556% | 9.2301 | 8.9235 | 9.0842 | 9.1068 | 6.0459 | 2.8017 | 0.83816 | 46.0304 |  | 296.8626 |  | 8340176.5 | 83.4018
| ORC @ 2 Lacks/Month |  | 44 | 0.9747% | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 14 |  | 58 |  | 459768325.5 | 4597.6833
| Other Income |  | 1.29 | 0.02858% | [7 empty] | 0 |  | 1.29 |  | 84763283.7967
| Total amount | 100% | 5759.5715 |  | 259.532 | 250.9762 | 255.4613 | 256.0904 | 170.6886 | 80.172 | 25.3858 | 1298.3064 | 100% | 7057.8779 | 100%
B | Deductions |  |  | 0% | [8 empty] | 0% |  | 0% | 84.43%
| Service Tax Expenses | 4.203% | 250.8322 | 4.355% | 9.2301 | 8.9235 | 9.0842 | 9.1068 | 6.0459 | 2.8017 | 0.83816 | 46.0304 | 3.545% | 296.8626 | 4.206%
| TDS | 2.047% | 98.8226 | 1.716% | 3.7339 | 3.6098 | 3.6748 | 3.684 | 2.4458 | 1.1334 | 0.33906 | 18.6207 | 1.434% | 117.4433 | 1.664% | 114246165.1173
| WCT 2.1% (Work Contract tax) | 2.047% | 96.9645 | 1.684% | 3.7339 | 3.6098 | 3.6748 | 3.684 | 2.4458 | 1.1334 | 0.33906 | 18.6207 | 1.434% | 115.5852 | 1.638%
| Total Deduction |  | 446.6192 | 7.754% | 16.6978 | 16.1431 | 16.4339 | 16.4747 | 10.9374 | 5.0685 | 1.5163 | 83.2717 | 6.414% | 529.891 | 7.508%
| Net Inflow | 94.73% | 5312.9523 | 92.25% | 242.8342 | 234.8331 | 239.0274 | 239.6157 | 159.7512 | 75.1035 | 23.8695 | 1215.0346 | 93.59% | 6527.9869 | 92.49%
C | Expenses |  |  | 0% | [8 empty] | 0% |  | 0%
I | Material Landed |  |  | 0% | [7 empty] | 0 | 0% |  | 0%
a | Material Consumed | 49.85% | 2534.4197 | 44% | 103.8391 | 97.268 | 88.1466 | 83.5994 | 42.682 | 11.7013 | 3.7053 | 430.9415 | 33.19% | 2965.3612 | 42.01%
b | Shuttering Ply & Batton |  | 0 | 0% | 4.6763 | 3.8918 | 0 | 0.71316 | 0.5094 | 0 | 0 | 9.7907 | 0.7541% | 9.7907 | 0.1387%
c | Tools And Tackles | 0.3128% |  | 0% | 0.77561 | 0.77561 | 0 | 0 | 0 | 0 | 0 | 1.5512 | 0.1195% | 1.5512 | 0.02198%
II | Labour Cost |  | 0 | 0% | [7 empty] | 0 | 0% | 0 | 0%
a | Labour Charges | 16.65% | 1068.7197 | 18.56% | 33.0391 | 29.4138 | 26.163 | 32.7072 | 20.2056 | 8.4017 | 1.5613 | 151.4918 | 11.67% | 1220.2114 | 17.29%
b | P/C With Material | 7.216% | 193.1741 | 3.354% | 25.4438 | 32.5892 | 46.4815 | 34.404 | 36.2027 | 27.6964 | 10.5352 | 213.3529 | 16.43% | 406.5269 | 5.76%
c | Mustor Roll Labour | 0.3128% | 48.3021 | 0.8386% | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 8.4 | 0.647% | 56.7021 | 0.8034%
III | Water Charges | 0.1087% | 93.1981 | 1.618% | 1.32 | 1.32 | 1.32 | 1.32 | 1.32 | 1.32 | 1.32 | 9.24 | 0.7117% | 102.4381 | 1.451%
iv | Electricity Charges | 0.3261% |  |  | 0.9 | 0.9 | 0.9 | 0.45 | 0.45 | 0.45 | 0.3 | 4.35 | 0.3351% | 4.35 | 0.06163%
| Diesel & Fuel | 0.1829% |  |  | 2.0896 | 2.0896 | 1.6796 | 1.3916 | 1.2916 | 1.2916 | 1.2916 | 11.1252 | 0.8569% | 11.1252 | 0.1576%
| Machinary Rental-EMD |  | 51.6356 | 0% | [7 empty] | 0 | 0% | 51.6356
| Hiring Charges Of Plant & Mach. | 0.08696% | 225.2379 | 3.911% | 4.595 | 4.595 | 3.645 | 2.895 | 2.5575 | 2.465 | 2.465 | 23.2175 | 1.788% | 248.4554 | 3.52%
| Total | 75.05% | 4214.687 | 73.18% | 177.8785 | 174.043 | 169.5357 | 158.6804 | 106.4188 | 54.526 | 22.3784 | 863.4608 | 66.51% | 5078.1479 | 71.95%
V | Over Heads |  |  | 0% | [7 empty] | 0 | 0% |  | 0%
1 | Staff Salary | 1.909% | 272.2704 | 4.727% | 5.33 | 5.33 | 4.74 | 4.675 | 4.465 | 4.195 | 4.195 | 32.93 | 2.536% | 305.2004 | 4.324%
2 | Labour Welfare | 0.1% | 23.4595 | 0.4073% | 0.17788 | 0.17404 | 0.16954 | 0.15868 | 0.10642 | 0.054526 | 0.022378 | 0.86346 | 0.06651% | 24.323 | 0.3446%
3 | Car Hiring Charges | 0.06522% | 20.827 | 0.3616% | 0.56 | 0.56 | 0.56 | 0.28 | 0.28 | 0.28 | 0.28 | 2.8 | 0.2157% | 23.627 | 0.3348%
4 | Repair & Maint. Of Mach. | 0.02174% | 5.5789 | 0.09686% | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.525 | 0.04044% | 6.1039 | 0.08648%
5 | Vehical Running Maint. For Staff | 0.005652% | 0.15238 | 0.002646% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0.15238 | 0.002159%
7 | Local Conveyance | 0.02174% | 3.0231 | 0.05249% | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.21 | 0.01617% | 3.2331 | 0.04581%
8 | Travelling For Staff/Other | 0.02391% | 4.5983 | 0.07984% | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 1.05 | 0.08087% | 5.6482 | 0.08003%
9 | Guest House Exp. | 0.02011% | 9.2483 | 0.1606% | 0.092778 | 0.092778 | 0.092778 | 0.092778 | 0.092778 | 0.092778 | 0.092778 | 0.64944 | 0.05002% | 9.8978 | 0.1402%
10 | Rent Staff Qtr. | 0.1304% | 23.9791 | 0.4163% | 0.5795 | 0.5795 | 0.5795 | 0.4275 | 0.4275 | 0.4275 | 0.4275 | 3.4485 | 0.2656% | 27.4276 | 0.3886%
11 | Staff Welfare/Canteen Exp. | 0.01304% | 14.3789 | 0.2497% | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 1.05 | 0.08087% | 15.4289 | 0.2186%
12 | Medical Expenses | 0.02174% | 3.5639 | 0.06188% | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 1.75 | 0.1348% | 5.3139 | 0.07529%
13 | Staff/Client Entertainment | 0.01304% | 0 | 0% | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.35 | 0.02696% | 0.35 | 0.004959%
14 | Special Incentive Fot Site Staff |  | 0.086 | 0.001493% | [7 empty] | 0 | 0% | 0.086 | 0.001218%
15 | Insurance Premium | 0.2823% | 5.1669 | 0.08971% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 5.1669 | 0.07321%
16 | Stationary For Office | 0.006522% | 2.0499 | 0.03559% | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 1.12 | 0.08627% | 3.17 | 0.04491%
17 | Telephone/Mob. & Fax | 0.0413% | 4.5366 | 0.07877% | 0.117 | 0.117 | 0.117 | 0.112 | 0.112 | 0.107 | 0.107 | 0.789 | 0.06077% | 5.3256 | 0.07546%
18 | Postage & Telegram | 0.006522% | 0.74532 | 0.01294% | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.28 | 0.02157% | 1.0253 | 0.01453%
19 | Watch & Ward | 0.1435% | 13.8523 | 0.2405% | 0.545 | 0.545 | 0.545 | 0.545 | 0.545 | 0.545 | 0.545 | 3.815 | 0.2938% | 17.6673 | 0.2503%
20 | Pooja Expenses | 0.006522% | 2.049 | 0.03558% | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.21 | 0.01617% | 2.259 | 0.03201%
21 | Testing Charges | 0.1231% | 3.0156 | 0.05236% | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.35 | 0.02696% | 3.3656 | 0.04769%
22 | Legal & Professional Carges | 0.02826% | 1.4505 | 0.02518% | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.052 | 0.364 | 0.02804% | 1.8145 | 0.02571%
23 | Intt. Loaded |  | 40.3089 | 0.6999% | [7 empty] | 0 | 0% | 40.3089 | 0.5711%
24 | Bank Charges & Comm. |  | 24.1546 | 0.4194% | [7 empty] | 0 | 0% | 24.1546 | 0.3422%
25 | Charity & Donation | 0.004348% | 0 | 0% | 0.1 | 0.1 | 0.1 | 0.1 | 0.05 | 0.05 | 0.05 | 0.55 | 0.04236% | 0.55 | 0.007793%
26 | Other (Site Direct Expences) |  | 18.6461 | 0.3237% | 0.64297 | 0.64297 | 0.64297 | 0.64297 | 0.64297 | 0.64297 | 0.64297 | 4.5008 | 0.3467% | 23.1469 | 0.328%
27 | Mustor (Misc.Labour) | 0.03652% | 0 | 0% | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 2.8 | 0.2157% | 2.8 | 0.03967%
28 | Misc. Expence | 0.02609% | 2.4652 | 0.0428% | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.91 | 0.07009% | 3.3752 | 0.04782%
| Total | 4.38% | 499.6067 | 8.674% | 9.7121 | 9.7083 | 9.1138 | 8.6009 | 8.2887 | 7.9618 | 7.9296 | 61.3152 | 4.723% | 560.9219 | 7.947%
| H O Share | 4% | 272.8138 | 4.737% | 9.7134 | 9.3933 | 9.5611 | 9.5846 | 6.39 | 3.0041 | 0.95478 | 48.6014 | 3.743% | 321.4152 | 4.554%
| Moh | 0.5% | 6.8 | 0.1181% | 2.4283 | 2.3483 | 2.3903 | 2.3962 | 1.5975 | 0.75103 | 0.2387 | 12.1503 | 0.9359% | 18.9503 | 0.2685%
| Rental For Plant & Mach.,Lab.Equip. | 0.28% | 308.2223 | 5.351% | 1.2176 | 1.2176 | 1.2176 | 1.2176 | 8.5232 | 0 | 0 | 13.3936 | 1.032% | 321.6159 | 4.557%
| Intrest on HO Loan |  | 83.5812 | 1.451% | [7 empty] | 0 | 0% | 83.5812 | 1.184%
| Temp. Infrastucture | 0.4% | 0.94048 | 0.01633% | 0.86111 | 0.86111 | 0.86111 | 0.86111 | 0.86111 | 0.86111 | 0.86111 | 6.0278 | 0.4643% | 6.9683 | 0.09873%
| Total | 5.18% | 672.3577 | 11.67% | 14.2204 | 13.8204 | 14.0301 | 14.0595 | 17.3719 | 4.6163 | 2.0546 | 80.1731 | 6.175% | 752.5308 | 10.66%
| Net total out flow | 83.29% | 5386.6515 | 93.53% | 201.811 | 197.5717 | 192.6796 | 181.3408 | 132.0794 | 67.1041 | 32.3626 | 1004.9491 | 77.4% | 6391.6006 | 90.56%
| Net Surplus/Deficit | 11.44% | -73.6992 | -1.28% | 41.0231 | 37.2615 | 46.3478 | 58.2749 | 27.6718 | 7.9994 | -8.493 | 210.0855 | 16.18% | 136.3863 | 1.932%

## TM & TL BUD-OCT-14
Project: DDA Kalkaji (2005) | [29 empty] | 5
SI. No. | Description | Unit | Rate | SHI-1 ,DHARMENDAR KUMAR (DM) | [5 empty] | SHI-1 | SHI-2, RAJ KUMAR SHARMA (DM) | [5 empty] | SHI-2 | SHI-3, MANOJ KUMAR | [7 empty] | SHI-3 | PI BUDGET
|  |  |  | TL-1,SANJAY MALIK(SURVEYOR) | [5 empty] | BUDGET | TL-2, DANESH KHAN(GET) |  |  | TL-3, AMITH KUMAR(AE) |  |  | BUDGET | TL-4, RAHUL KUMAR GOND |  | TL-5, GAURAV THAKUR |  | TL-6, RAJESH KUMAR |  | TL-7 ,ANKIT KUMAR |  | BUDGET | ZAHIR
|  |  |  | TM-1 JAGDISH (SP) | [6 empty] | TM-2, RADHESHYAM (SP) |  |  | TM-3,BRIJESH (FM) |  |  |  | TM-4, BIJENDAR |  | TM-4, BIJENDAR |  | TM-5, MUNEER (SP) |  | TM-5, MUNEER (SP) |  |  | QTY | AMOUNT
|  |  |  | CL-1,T-1 | CL-1,T-2 | CL-1,T-3 | CL-1,T-4 | CL-1,T-5 | CL-1,T-6 |  | CL-3, T-2 | CL-3, T-3 | CL-3, T-4 | CL-3, T-1 | CL-3, T-5 | CL-3, T-6 |  | CL-2,T-1 | CL-2,T-2 | CL-4, T-1 | CL-4,T-6 | CL-4, T-2 | CL-4, T-3 | CL-4, T-4 | CL-4, T-5
SUB-HEAD - I: EARTH WORK
2.7 | Earth work in excavation by mechanical means (Hydraulic excavator) / manual means in over areas (exceeding 30cm in depth 1.5m in width or 10 sqm on plan) including disposal of excavated earth, lead upto 50 m and lift upto 1.50m, disposed earth to be levelled and neatly dressed. | [23 empty] | 0
2.7.1 | Ordinary rock | Cum | 88.4292 | 0 | 1681.2 | 1251.2 | 0 | 0 | 1816.9 | 4749.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4749.3 | 419976.8248
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
2.25 | Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundation etc. in layers not exceeding 20 cm in depth: consolidating each deposited layer by ramming and watering, lead upto 50 m and lift upto 1.5 m | Cum | 44.2146 | 1500 | 0 | 0 | 0 | 1798.056 | 0 | 3298.056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3298.056 | 145822.2356
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
2.26 | Extra for every additional lift of 1.5 m or part thereof in excavation /banking excavated or stacked materials. All kinds of soil. | [8 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
2.26.2 | Ordinary or hard rock. | cum | 22.1073 | 0 | 1008.72 | 750.72 | 0 | 0 | 1090.14 | 2849.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2849.58 | 62996.5237
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
2.27 | Supplying and filling in plinth with Jamuna sand under floors including, watering, ramming consolidating and dressing complete. | Cum | [7 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
NS (DSR Based 23.2) | Supplying & stacking of good earth by mechanical transport including loading, unloading and stacking all leads including filling, inlayers not exceeding 20 cm in depth consolidating each deposited layer by ramming and watering any lead. | Cum | 295 | [6 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
| SUB-HEAD - II: PCC WORK | [8 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
| Providing & laying in position cement concrete of specified grade excluding the cost of centering and shuttering - All work upto plinth level. | [8 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
4.1.8 | 1:4:8 (1 Cement : 4 coarse sand : 8 graded stone aggregate 40 mm nominal size) | Cum | [7 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
4.1.10 | 1:5:10 (1cement: 5 coarse sand: 10 stone aggregate 40mm nominal size) | Cum | 4011.7383 | 0 | 40.2472 | 45.04 | 0 | 0 | 45.04 | 130.3272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.82 | 151.1472 | 606362.9084
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
N.S. (Based on DSR 4.17) | Making plinth protection 50mm thick of M-20 concrete over 75mm thick bed of dry brick ballast 40 mm nominal size, well rammed and consolidated and grouted with fine sand including finishing the top smooth. | Sqm | [7 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
| SUB-HEAD - III: RCC WORK | [8 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
5.9 | Centring and shuttering including strutting, propping etc. and removal of form for : | [8 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
5.9.1 | Foundations, footings, bases of columns, etc. for mass concrete. | Sqm | 316.8713 | 0 | 78.88 | 57.3 | 0 | 0 | 57.3 | 193.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.94 | 256.42 | 81252.1436
5.9.2 | Walls (any thickness) i/c attached pilasters, butteresses, plinth and string courses etc. | Sqm | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 533.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 533.26 | 533.26 | 159978
5.9.3 | Suspended floors, roofs, landings, balconies and access platform. | Sqm | 300 | 0 | 0 | 0 | 491.2 | 0 | 0 | 491.2 | 831.152 | 1200 | 831.152 | 1196.8539 | 598.427 | 1200 | 5857.5849 | 1252.774 | 1310.48 | 1303.76 | 1303.76 | 1442.8 | 1836.72 | 1828.54 | 1442.86 | 11721.694 | 18070.4789 | 5421143.6584
5.9.4 | Shelves (Cast-in -situ) | Sqm | [7 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
5.9.5 | Lintels, beams, plinth beams, girders, bressumers and cantilevers. | Sqm | 280.0258 | 271.21 | 0 | 0 | 0 | 243.99 | 0 | 515.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515.2 | 144269.3008
5.9.6 | Columns, Pillars, Piers, Abutments, Posts and Struts | Sqm | 365.6 | 323.34 | 348 | 0 | 289 | 260.13 | 0 | 1220.47 | 260.0324 | 375.4282 | 260.0324 | 374.4452 | 374.4452 | 375.4282 | 2019.8116 | 188.54 | 197.21 | 381.06 | 381.06 | 428.04 | 575.94 | 555.06 | 428.04 | 3134.95 | 6375.2316 | 2330784.6621
5.9.7 | Stairs, (excluding landings) except spiral stair-cases | Sqm | [7 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
5.9.16 | Edges of slabs and breaks in floors and walls. | [8 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
5.9.16.1 | Under 20 cm wide | Mtr | [7 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
| Providing precast cement concrete Jali 1:2:4 (1 cement : 2 coarse sand: 4 graded stone aggregate 6 mm nominal size), reinforced with 1.6 mm dia mild steel wire, including centering and shuttering, roughening cleaning, fixing and finishing in cement mortar 1:3 (1 cement: 3 fine sand) etc. complete, excluding plastering of the jambs, sills and soffits. | [8 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
5.18.2 | 40 mm thick | Sqm | [7 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
5.22 | Steel reinforcement for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete up to plinth level. | [8 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
5.22.6 | Thermo-Mechanically Treated bars | Kg | 81.2075 | 17590 | 27490 | 15160 | 0 | 14290 | 15160 | 89690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6959 | 96649 | 7848622.4004
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
5.22A | Steel reinforcement for for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete above plinth level. | [8 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0 | 490
5.22A.6 | Thermo-Mechanically Treated bars | Kg | 81.2075 | 0 | 0 | 0 | 18790 | 0 | 0 | 18790 | 25120 | 36280 | 25120 | 39740 | 27300 | 36280 | 189840 | 28940 | 30290 | 37630 | 37630 | 41902 | 56500 | 56802.05 | 42462 | 332156.05 | 540786.05 | 43915876.0656
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
NS | Providing and fixing sheet covering over expansion joints with iron screws as per design. | [8 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
(Based on DSR 5.29.1) | Non-absestos fibre cement board 6 mm thick as per IS : 148862 - 350 mm wide | mtr | [7 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
(Based on DSR 5.29.2) | Aluminium fluted stips 3.15 mm thick 350 mm wide | mtr | [7 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
5.34 | Extra for providing richer mixes at all floor levels. Note:- Excess/less cement over the specified cement content used is payable /recoverable separately. | [8 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
5.34.1 | Providing M-30 grade concrete instead of M-25 grade BMC/RMC. (Note:- Cement content considered in M-30 is @ 340 kg/cum). | cum | 751.6482 | 40.8 | 43.3 | 0 | 29.8 | 32.45 | 0 | 146.35 | 34.671 | 50.0571 | 34.671 | 49.926 | 49.926 | 50.0571 | 269.3082 | 19.05 | 19.93 | 39.42 | 39.42 | 44.38 | 59.76 | 57.68 | 44.38 | 324.02 | 739.6782 | 555977.8281
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
5.37 | Providing & laying in position ready mixed M-25 grade concrete for reinforced cement concrete work, using cement content as per approved mix design manufactured in fully automatic batching plant and transported to site of work in transit mixer for all leads having continuous agitated mixer, manufactured as per mix design of specified grade for reinforced cement concrete work including pumping of RMC from transit mixer to site of laying, excluding the cost of centering, shuttering finishing and reinforcement including cost of admixtures in recommended proportions as per IS:9103 to accelerate/ retard setting of concrete, improve workability without impairing strength and durability as per direction of the Engineer-in-charge. Cement content is considered in this item is @ 330 kg/cum. Excess/less cement used as per design mix is payable/recoverable separately). | [8 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
5.37.1 | All works up to plinth level | Cum | 6296.012 | 62.991 | 301.34 | 262.88 | 0 | 52.414 | 262.88 | 942.505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132.6 | 1075.105 | 6768874.0212
| All works above plinth upto floor V level | Cum | 6296.012 | 0 | 0 | 0 | 81.6 | 0 | 0 | 81.6 | 132.6101 | 191.4571 | 132.6101 | 190.9578 | 120.4419 | 191.4571 | 959.5341 | 151.09 | 157.87 | 177.52 | 177.52 | 193 | 274.28 | 270.06 | 193 | 1594.34 | 2635.4741 | 16592976.5014
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
5.38 | Extra for R.C.C./ B.M.C/ R.M.C. work above floor V level for each four floors or part thereof. | Cum | [7 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
[10 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
NS (Based on DSR 5.43) | Providing and fixing in position Stainless steel Grade 304 plate-1.0 mm thick as per design for expansion joints. | mtr | [7 empty] | 0 | [6 empty] | 0 | [7 empty] | 0 | 0 |  | 0
N.S. (DSR Based) | Providing & laying Autoclaved Areatd Cement blocks masonary with 200mm thick AAC Blocks in super structure above plinth level upto floor V level in Cement mortar 1:4 (1 cement : 4 coarse sand) | Cum | 6649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112.216 | 0 | 0 | 112.216 | 0 | 0 | 0 | 0 | 238.56 | 0 | 0 | 0 | 238.56 | 350.776 | 2332309.624
[17 empty] | 0 | [8 empty] | 0
[25 empty] | 0 |  |  | 0
| FINAL AMOUNT- BOQ |  |  | 2116179.8468 | 4646832.4505 | 3212285.5793 | 2315060.7786 | 1757772.5068 | 3269813.641 | 17317944.803 | 3245320.7912 | 4686505.6474 | 3245320.7912 | 5709062.2592 | 3329220.0581 | 4686505.6474 | 24901935.1946 | 5423910.8216 | 3933950.5237 | 4733579.2983 | 4733579.2983 | 6826761.4519 | 7121591.354 | 7107899.7482 | 5286070.2046 | 45167342.7007 | 0 | 87387222.6983
| TEAM LEADER BUDGET |  |  | 17317944.803 | [6 empty] | 11177147.2299 |  |  | 13724787.9647 |  |  |  | 9357861.3453 |  | 9467158.5966 |  | 13948352.8059 |  | 12393969.9528

## BUDGET WEEKLY BASIS
WEEKLY BUDGET FOR M/O JAN 2015 | [6 empty] | 17041934.255 |  | 23769120.277 |  | 24468219.9799 |  | 22038737.1872 |  |  | 3
DDA KALKA JI |  |  | MONTHLY |  |  | WEEK 1 |  | WEEK 2 |  | WEEK 3 |  | WEEK 4
SI. No. | Description | Unit | QTY | BOQ Rate | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT
SUB-HEAD - I: EARTH WORK
2.7 | Earth work in excavation by mechanical means (Hydraulic excavator) / manual means in over areas (exceeding 30cm in depth 1.5m in width or 10 sqm on plan) including disposal of excavated earth, lead upto 50 m and lift upto 1.50m, disposed earth to be levelled and neatly dressed. |  |  |  | 0
2.7.1 | Ordinary rock | Cum | 4749.3 | 88.4292 | 419976.8248 | 949.86 | 83995.365 | 1329.804 | 117593.511 | 1282.311 | 113393.7427 | 1187.325 | 104994.2062 | 4749.3 | 0
|  |  | 0 |  | 0 | 0 | [5 empty] | 0 |  | 0 | 0
2.25 | Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundation etc. in layers not exceeding 20 cm in depth: consolidating each deposited layer by ramming and watering, lead upto 50 m and lift upto 1.5 m | Cum | 3180 | 44.2146 | 140602.4365 | 636 | 28120.4873 | 890.4 | 39368.6822 | 858.6 | 37962.6578 | 795 | 35150.6091 | 3180 | 0
|  |  | 0 |  | 0 | [8 empty] | 0 | 0
2.26 | Extra for every additional lift of 1.5 m or part thereof in excavation /banking excavated or stacked materials. All kinds of soil. |  | 0 |  | 0 | [8 empty] | 0 | 0
2.26.2 | Ordinary or hard rock. | cum | 2849.58 | 22.1073 | 62996.5237 | 569.916 | 12599.3047 | 797.8824 | 17639.0266 | 769.3866 | 17009.0614 | 712.395 | 15749.1309 | 2849.58 | 0
|  |  | 0 |  | 0
2.27 | Supplying and filling in plinth with Jamuna sand under floors including, watering, ramming consolidating and dressing complete. | Cum | 0 |  | 0
|  |  | 0 |  | 0
NS (DSR Based 23.2) | Supplying & stacking of good earth by mechanical transport including loading, unloading and stacking all leads including filling, inlayers not exceeding 20 cm in depth consolidating each deposited layer by ramming and watering any lead. | Cum | 0 | 295 | 0
|  |  | 0 |  | 0
| SUB-HEAD - II: PCC WORK |  | 0 |  | 0
| Providing & laying in position cement concrete of specified grade excluding the cost of centering and shuttering - All work upto plinth level. |  | 0 |  | 0
4.1.8 | 1:4:8 (1 Cement : 4 coarse sand : 8 graded stone aggregate 40 mm nominal size) | Cum | 0 |  | 0
|  |  | 0 |  | 0
4.1.10 | 1:5:10 (1cement: 5 coarse sand: 10 stone aggregate 40mm nominal size) | Cum | 151.1472 | 4011.7383 | 606362.9084 | 30.2294 | 121272.5817 | 42.3212 | 169781.6144 | 40.8097 | 163717.9853 | 37.7868 | 151590.7271 | 151.1472 | 0
|  |  | 0 |  | 0 | [8 empty] | 0 | 0
N.S. (Based on DSR 4.17) | Making plinth protection 50mm thick of M-20 concrete over 75mm thick bed of dry brick ballast 40 mm nominal size, well rammed and consolidated and grouted with fine sand including finishing the top smooth. | Sqm | 0 |  | 0 | [8 empty] | 0 | 0
| SUB-HEAD - III: RCC WORK |  | 0 |  | 0 | [8 empty] | 0 | 0
|  |  | 0 |  | 0 | [8 empty] | 0 | 0
5.9 | Centring and shuttering including strutting, propping etc. and removal of form for : |  | 0 |  | 0 | [8 empty] | 0 | 0
5.9.1 | Foundations, footings, bases of columns, etc. for mass concrete. | Sqm | 256.42 | 316.8713 | 81252.1436 | 51.284 | 16250.4287 | 71.7976 | 22750.6002 | 69.2334 | 21938.0788 | 64.105 | 20313.0359 | 256.42 | 0
5.9.2 | Walls (any thickness) i/c attached pilasters, butteresses, plinth and string courses etc. | Sqm | 533.26 | 300 | 159978 | 213.304 | 63991.2 | 213.304 |  | 106.652 | 31995.6 |  |  | 533.26 | 0
5.9.3 | Suspended floors, roofs, landings, balconies and access platform. | Sqm | 18070.4789 | 300 | 5421143.6584 | 3614.0958 | 1084228.7317 | 5059.7341 | 1517920.2243 | 4879.0293 | 1463708.7878 | 4517.6197 | 1355285.9146 | 18070.4789 | 0
5.9.4 | Shelves (Cast-in -situ) | Sqm | 0 |  | 0 | [8 empty] | 0 | 0
5.9.5 | Lintels, beams, plinth beams, girders, bressumers and cantilevers. | Sqm | 515.2 | 280.0258 | 144269.3008 | 103.04 | 28853.8602 | 144.256 | 40395.4042 | 139.104 | 38952.7112 | 128.8 | 36067.3252 | 515.2 | 0
5.9.6 | Columns, Pillars, Piers, Abutments, Posts and Struts | Sqm | 6375.2316 | 365.6 | 2330784.6621 | 1275.0463 | 466156.9324 | 1785.0648 | 652619.7054 | 1721.3125 | 629311.8588 | 1593.8079 | 582696.1655 | 6375.2316 | 0
5.9.7 | Stairs, (excluding landings) except spiral stair-cases | Sqm | 0 |  | 0 | [8 empty] | 0 | 0
5.9.16 | Edges of slabs and breaks in floors and walls. |  | 0 |  | 0 | [8 empty] | 0 | 0
5.9.16.1 | Under 20 cm wide | Mtr | 0 |  | 0 | [8 empty] | 0 | 0
|  |  | 0 |  | 0 | [8 empty] | 0 | 0
| Providing precast cement concrete Jali 1:2:4 (1 cement : 2 coarse sand: 4 graded stone aggregate 6 mm nominal size), reinforced with 1.6 mm dia mild steel wire, including centering and shuttering, roughening cleaning, fixing and finishing in cement mortar 1:3 (1 cement: 3 fine sand) etc. complete, excluding plastering of the jambs, sills and soffits. |  | 0 |  | 0 | [8 empty] | 0 | 0
5.18.2 | 40 mm thick | Sqm | 0 |  | 0
|  |  | 0 |  | 0
5.22 | Steel reinforcement for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete up to plinth level. |  | 0 |  | 0
5.22.6 | Thermo-Mechanically Treated bars | Kg | 96649 | 81.2075 | 7848622.4004 | 19329.8 | 1569724.4801 | 27061.72 | 2197614.2721 | 26095.23 | 2119128.0481 | 24162.25 | 1962155.6001 | 96649 | 0
|  |  | 0 |  | 0 | [8 empty] | 0 | 0
5.22A | Steel reinforcement for for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete above plinth level. |  | 0 |  | 0 | [8 empty] | 0 | 0
5.22A.6 | Thermo-Mechanically Treated bars | Kg | 540786.05 | 81.2075 | 43915876.0656 | 108157.21 | 8783175.2131 | 151420.094 | 12296445.2984 | 146012.2335 | 11857286.5377 | 135196.5125 | 10978969.0164 | 540786.05 | 0
|  |  | 0 |  | 0 | [8 empty] | 0 | 0
NS | Providing and fixing sheet covering over expansion joints with iron screws as per design. | [12 empty] | 0 | 0
(Based on DSR 5.29.1) | Non-absestos fibre cement board 6 mm thick as per IS : 148862 - 350 mm wide | mtr | [11 empty] | 0 | 0
[14 empty] | 0 | 0
(Based on DSR 5.29.2) | Aluminium fluted stips 3.15 mm thick 350 mm wide | mtr | [11 empty] | 0 | 0
[14 empty] | 0 | 0
5.34 | Extra for providing richer mixes at all floor levels. Note:- Excess/less cement over the specified cement content used is payable /recoverable separately. | [12 empty] | 0 | 0
5.34.1 | Providing M-30 grade concrete instead of M-25 grade BMC/RMC. (Note:- Cement content considered in M-30 is @ 340 kg/cum). | cum | 739.6782 | 751.6482 | 555977.8281 | 147.9356 | 111195.5656 | 207.1099 | 155673.7919 | 199.7131 | 150114.0136 | 184.9196 | 138994.457 | 739.6782 | 0
[14 empty] | 0 | 0
5.37 | Providing & laying in position ready mixed M-25 grade concrete for reinforced cement concrete work, using cement content as per approved mix design manufactured in fully automatic batching plant and transported to site of work in transit mixer for all leads having continuous agitated mixer, manufactured as per mix design of specified grade for reinforced cement concrete work including pumping of RMC from transit mixer to site of laying, excluding the cost of centering, shuttering finishing and reinforcement including cost of admixtures in recommended proportions as per IS:9103 to accelerate/ retard setting of concrete, improve workability without impairing strength and durability as per direction of the Engineer-in-charge. Cement content is considered in this item is @ 330 kg/cum. Excess/less cement used as per design mix is payable/recoverable separately). | [12 empty] | 0 | 0
5.37.1 | All works up to plinth level | Cum | 1075.105 | 6296.012 | 6768874.0212 | 215.021 | 1353774.8042 | 301.0294 | 1895284.7259 | 290.2784 | 1827595.9857 | 268.7763 | 1692218.5053 | 1075.105 | 0
| All works above plinth upto floor V level | Cum | 2635.4741 | 6296.012 | 16592976.5014 | 527.0948 | 3318595.3003 | 737.9327 | 4646033.4204 | 711.578 | 4480103.6554 | 658.8685 | 4148244.1254 | 2635.4741 | 0
|  |  | 0 |  | 0 | [8 empty] | 0 | 0
5.38 | Extra for R.C.C./ B.M.C/ R.M.C. work above floor V level for each four floors or part thereof. | Cum | 0 |  | 0 | [8 empty] | 0 | 0
|  |  | 0 |  | 0 | [8 empty] | 0 | 0
NS (Based on DSR 5.43) | Providing and fixing in position Stainless steel Grade 304 plate-1.0 mm thick as per design for expansion joints. | mtr | 0 |  | 0 | [8 empty] | 0 | 0
N.S. (DSR Based) | Providing & laying Autoclaved Areatd Cement blocks masonary with 200mm thick AAC Blocks in super structure above plinth level upto floor V level in Cement mortar 1:4 (1 cement : 4 coarse sand) | cum | 350.776 | 6649 | 2332309.624 |  |  |  |  | 228.0044 | 1516001.2556 | 122.7716 | 816308.3684
[5 empty] | 87382002.8991 |  | 17041934.255 |  | 23769120.277 |  | 24468219.9799 |  | 22038737.1872 | 0 | 0
[5 empty] | 87382002.8991 |  | 17041934.255 |  | 23769120.277 |  | 24468219.9799 |  | 22038737.1872 | 87318011.6991

## Shuttering
ERA INFRA ENGINEERING LIMITED
370-371/2,SAHI HOSPITAL ROAD,JANGPURA,BHOGAL,NEW DELHI-110014
Shuttering Detail M/O- JAN- 2014
PROJECT CODE:-2005
PROJECT NAME:-DDA Kalkaji
S.NO | DESCRIPTION | UNIT | NET REQ | AVILABAL .QTY | RATE | AMOUNT | REMARKS
1 | CHALLIES MS | EACH | 200 | 50 | 9 | 450
2 | SCAFFOLDING VERTICAL MS 2.00 MTR | EACH | 1500 | 1000 | 7.5 | 7500
3 | SCAFFOLDING VERTICAL MS 3.00 MTR | EACH | 2000 | 500 | 11.25 | 5625
4 | SCAFFOLDING VERTICAL MS 1.50 MTR | EACH | 1000 | 500 | 0 | 0
5 | SCAFFOLDING HORIZONTAL MS 1.00 MTR | EACH |  | 1000 | 3.75 | 3750
6 | SCAFFOLDING HORIZONTAL MS 1.25 MTR | EACH |  | 100 | 5.25 | 525
7 | SCAFFOLDING HORIZONTAL MS 1.50 MTR | EACH | 3500 | 1200 | 5.25 | 6300
8 | SCAFFOLDING HORIZONTAL MS 3.0 MTR | EACH | 500 | 0
9 | SCAFFOLDING HORIZONTAL MS 2.0 MTR | EACH | 4000 | 1100 | 7.5 | 8250
10 | MS PIPE 40 MM B CLASS | RMT |  | 2340 | 2.4 | 5616
11 | SHUTTERING PLATES MS 600 X 900 MM | EACH | 1500 | 37 | 10.05 | 371.85
12 | SHUTTERING PLATES MS 1220 X 450 MM | EACH | 3000 | 1500 | 9 | 13500
13 | SHUTTERING PLATE MS 1250X500MM | EACH | 1200 | 1000 | 15.625 | 15625
14 | SHUTTERING PLATE MS 1250X600MM | EACH | 500 | 0 | 0 | 0
15 | SHUTTERING PLATE MS | KG |  | 1846 | 0.64 | 1181.44
16 | U HEAD JACK MS 250 MM LONG | EACH | 675 | 82
17 | BASE PLATE MS WITH JACK | EACH | 675 | 124
18 | COLUM FRAME ALL SIZE | EACH |  | 78 |  | 0
19 | COUPLER MS FIXED 40 MM | EACH |  | 64 | 0.9 | 57.6
20 | COUPLER MS SWIVEL 40 MM | EACH |  | 1036 | 0.9 | 932.4
21 | SPIGOT PIN | EACH |  | 320 |  | 0
22 | PROPS MS 2x2MTR | EACH | 7000 | 3000 | 0.9 | 2700
| TOTAL AMOUNT |  |  |  |  | 72384.29
SHUTTERING MATERIAL REQUIRED IN THIS MONTH
S.NO. | ITEM DESCRIPTION | UNIT | TOTAL REQ | AVILABLE QTY | RATE | AMOUNT | REMARKS
A | WOODEN MATERIALS
1 | PLY | NO | 750 | 200 | 1755 | 1316250
2 | BATTON 3''*2''*10' | CFT | 2500 | 1498 | 646.624 | 1616560
3 | BATTON 4''*3''*8' | CFT | 700 | 596 | 646.624 | 452636.8
4 | SHUTTERING OIL | LTR | 500 |  | 58 | 29000
5 | NAILS | KG | 500 |  | 62 | 31000
6 | MS ANGLE 50*50*5 | KG | 4500 |  | 55 | 247500
| TOTAL (a) |  |  |  |  | 3692946.8

## Rental Details
ERA GROUP
H.O. STORES CORPORATE INFRA - 1
INTERNAL DEBIT NOTE FOR RENTAL
CSS RENTAL DEBIT NOTE NO: |  |  | CORPORATE-INFRA-1/13-14/0001
From | H.O. STORES |  | To - DDA FLAT KALKA JI
C-56/41, SECTOR - 62
NOIDA - 201301
Code:2005
DEBIT NOTE FOR THE PERIOD |  |  | 2015-01-01
SL. | ITEM CODE | ITEM NAME | UOM | QTY. | RATE | TOTAL CHARGES
1 | 1400101002 | CUBE TESTING MACHINE 200 TON | EACH | 1 | 600 | 600
2 | 1400101003 | CUBE TESTING MACHINE 100 TONNES (1000 KN ) ELECTRICALY CUM | EACH | 1 | 500 | 500
3 | 1416601001 | ELECTRONIC TOTAL STATION MACHINE | SET | 1 | 4000 | 4000
4 | 1500303001 | CHALLIES MS | EACH | 50 | 9 | 450
5 | 1500501003 | SCAFFOLDING VERTICAL MS 1.00 MTR | EACH | 20 | 2.5 | 50
6 | 1500501005 | SCAFFOLDING VERTICAL MS 1.50 MTR | EACH | 1309 | 5 | 6545
7 | 1500501007 | SCAFFOLDING VERTICAL MS 2.00 MTR | EACH | 1588 | 7.5 | 11910
8 | 1500501008 | SCAFFOLDING VERTICAL MS 2.50 MTR | EACH | 814 | 9.25 | 7529.5
9 | 1500501009 | SCAFFOLDING VERTICAL MS 3.00 MTR | EACH | 1580 | 11.25 | 17775
10 | 1500601003 | SCAFFOLDING HORIZONTAL MS 1.00 MTR | EACH | 1160 | 3.75 | 4350
11 | 1500601004 | SCAFFOLDING HORIZONTAL MS 1.25 MTR | EACH | 120 | 5.25 | 630
12 | 1500601005 | SCAFFOLDING HORIZONTAL MS 1.50 MTR | EACH | 1916 | 5.25 | 10059
13 | 1500601007 | SCAFFOLDING HORIZONTAL MS 2.0 MTR | EACH | 1716 | 7.5 | 12870
14 | 1500601010 | SCAFFOLDING HORIZONTAL MS 1.20 MTR | EACH | 7 | 5.25 | 36.75
15 | 1501501005 | PROPS JACK 2X2 MTR | EACH | 1495 | 13.5 | 20182.5
16 | 1501501003 | PROPS MS 2 MTR X 3 MTR | EACH | 260 | 15 | 3900
17 | 1500701002 | MS PIPE 40 MM B CLASS | RMT | 2340 | 2.4 | 5616
18 | 1901101004 | PIPE MS 40 MM | KG | 12000 | 0.69 | 8280
19 | 1500801020 | SHUTTERING PLATES MS 600 X 900 MM | EACH | 37 | 10.05 | 371.85
20 | 1500801327 | SHUTTERING PLATES MS 1220 X 450 MM | EACH | 50 | 9 | 450
21 | 1500801119 | SHUTTERING PLATE MS 1250X500MM | EACH | 2306 | 16 | 36896
22 | 1500801135 | SHUTTERING PLATES MS 1400 X 450 MM | EACH | 2
23 | 1500801139 | SHUTTERING PLATES MS 1500 X 450 MM | EACH | 9
24 | 1500801140 | SHUTTERING PLATES MS 1500 X 830 MM | EACH | 1
25 | 1500801141 | SHUTTERING PLATES MS 1525 X 450 MM | EACH | 1
26 | 1500801144 | SHUTTERING PLATES MS 1800 X 450 MM | EACH | 2
27 | 1500801158 | SHUTTERING PLATES MS 1890 X 150 MM | EACH | 3
28 | 1500801163 | SHUTTERING PLATES MS 2000 X 350 MM | NOS | 1
29 | 1500801203 | SHUTTERING PLATES MS 1890 X 730MM | EACH | 1
30 | 1500801249 | SHUTTERING PLATES MS 2000 X 410MM | EACH | 2
31 | 1500801268 | SHUTTERING PLATES MS 1200 X 760MM | EACH | 1
32 | 1500801283 | SHUTTERING PLATES MS 2060 X 300MM | EACH | 1
33 | 1500801387 | SHUTTERING PLATES MS 300 X 3000 MM | EACH | 7
34 | 1500801402 | SHUTTERING PLATE MS 1750X920 MM | NOS | 1
35 | 1500801375 | SHUTTERING PLATE MS | KG | 11786 | 0.64 | 7543.04
36 | 1503703030 | COLUM FRAME ALL SIZE | EACH | 78 |  | 0
37 | 1501201001 | COUPLER MS FIXED 40 MM | EACH | 772 | 0.83 | 640.76
38 | 1501202001 | COUPLER MS SWIVEL 40 MM | EACH | 1036 | 0.9 | 932.4
39 | 1500901001 | BASE PLATE MS WITH JACK | EACH | 707 | 2.08 | 1470.56
40 | 1501001001 | U HEAD JACK MS 250 MM LONG | EACH | 163 | 2.08 | 339.04
41 | 1501001002 | U HEAD JACK MS 300 MM LONG | EACH | 143 | 2.08 | 297.44
42 | 1501001004 | U HEAD JACK MS 350MM | EACH | 305 | 2.08 | 634.4
43 | 1501101001 | SPIGOT PIN | EACH | 354 | 2.1 | 743.4
165602.64
44 | 1600101001 | CONCRETE MIXER ELECTRIC WITH HOPPER | EACH | 2 | 1500 | 3000
45 | 1601201001 | WELDING MACHINE AIR COOLED 350 AMP | EACH | 1 | 200 | 200
46 | 1601201011 | WELDING MACHINE AIR COOLED 400 AMP | EACH | 1 | 200 | 200
47 | 1601501049 | D G SET 7.5 KVA | EACH | 1 | 500 | 500
48 | 1601501013 | D G SET 125 KVA | EACH | 1 | 6770 | 6770
49 | 1601501003 | D G SET 15 KVA | EACH | 1 | 1562 | 1562
50 | 1603701003 | BATCHING PLANT 30 CUM | EACH | 1 | 37500 | 37500
51 | 1600701001 | TRACTOR | EACH | 1 | 6000 | 6000
52 | 1600801001 | TRACTOR TROLLY HYDRAULIC | EACH | 1 | 2400 | 2400
53 | 1602901002 | BOLERO | EACH | 1 | 18000 | 18000
54 | 1600401001 | EARTH COMPACTER ELE | EACH | 5 | 400 | 2000
55 | 1611701001 | BAR CUTTING MACHINE | EACH | 5 | 3000 | 15000
56 | 1611601001 | BAR BENDING MACHINE | EACH | 4 | 1563 | 6252
57 | 1600301001 | VIBRATER ORDINERY ELECTRICAL | EACH | 8 | 250 | 2000
58 | 1602801002 | MOTOR CYCLE HERO HONDA | EACH | 1 |  | 0
59 | 1604001001 | TRANSIT MIXER | EACH | 3 | 26190 | 78570
60 | 1601101001 | WEIGHT BATCHER HORIZONTAL SCALE TYPE 500 KGS BATCH CAPACIT | EACH | 1
61 | 1603501001 | MOBILE TOWER CRANE MTC -2418 | EACH | 1 | 17468 | 17468
62 | 1611301005 | HYDRAULIC EXCAVATOR 20 TON CAPACITY(POKLANE) | EACH | 1
63 | 0515501010 | WATER STORAGE TANK 5000 LTR | EACH | 1
64 | 1603901001 | CONCRITE PUMP 49 cum | EACH | 2 | 18750 | 37500
G. Total | [5 empty] | 234922
Rupees in Words: Three Lac Ninty Nine Thousand Five Hundred Twenty Four Only.

## Overheads-MAIN
ERA INFRA ENGINEERING LIMITED
370-371/2,SAHI HOSPITAL ROAD,JANGPURA,BHOGAL,NEW DELHI-110014
OVERHEADS M/O -JAN- 2015
S. No. | Description | Unit | Quantity | Rate | Amount | Remarks
A | Staff Salary
B | Incentive Staff
| STAFF & OTHERS (FOR NIGHT WORK) | L.S. | 1 | 0 | 0
| Total - B |  |  |  | 0
C | Labour Welfare
| CANTEEN EXPENSES | L.S. | 1 | 30000 | 30000
| Total - C |  |  |  | 30000
D | Testing Charges
| WATER TEST | L.S. | 1 | 5000 | 5000
| UT & RT TESTING | L.S. | 0 | 20000 | 20000
| Total - D |  |  |  | 25000
E | Car Hiring Charges
| SUMO-1 | Nos | 1
| SUMO-2 | Nos | 1
| Total - E |  |  |  | 0
F | Repair & Maintenance
| MOTOR REPAIR | L.S. |  |  | 15000
| BATCHING PLANT REPAIR | L.S. |  |  | 15000
| TRACTOR REPAIR | L.S. |  |  | 0
| CONC. PUMP REPAIR | L.S. |  |  | 15000
| OTHERS | L.S. |  |  | 5000
| Total - F |  |  |  | 50000
G | Local Conveyance (STAFF)
| HR |  |  |  | 0
| PURCHASE |  |  |  | 5000
| OTHERS STAFF |  |  |  | 3000
| Total - G |  |  |  | 8000
H | Travelling
| STAFF | L.S. | 0 | 5000 | 0
| OTHERS | L.S. | 0 | 2000 | 0
| PC | Nos | 0 | 20000 | 0
| Total - H |  |  |  | 0
I | Rent Staff Quarters/Office
| GUEST HOUSE NO -01 | Nos | 1 | 10000 | 10000
| GUEST HOUSE NO -02 | Nos | 1 | 10000 | 10000
| GUEST HOUSE NO -03 | Nos | 1 | 20000 | 20000
| GUEST HOUSE NO -04 | Nos | 1 | 20000 | 20000
| Labour Colony - Land Lease | Nos | 1 |  | 0
| Total - I |  |  |  | 60000
J | Guest House Expenses
| CLEANING EXPENSES | L.S. | 1 | 1500 | 1500
| DISH/CABLE CHARGES | L.S. | 1 | 800 | 800
| WATER/ELECTRIC CHARGES | L.S. | 1 | 6000 | 6000
| NEWS PAPER & MAGZINE | L.S. | 1 | 500 | 500
| MATRESS & QUILTS | L.S. | 1 | 3000 | 3000
| Total - J |  |  |  | 11800
K | Staff Welfare
| TEA EXPENSES (STAFF 30X10X30) | L.S. | 1 | 9000 | 9000
| OFFICE TEA EXPENSES FOR GUEST & OTHER | L.S. | 1 | 2000 | 2000
| NIGHT FOODING (LABOUR) | L.S. | 1 | 15000 | 15000
| SNACKS AFTER 8 O'CLOCK | L.S. | 1 | 0 | 0
| Total - K |  |  |  | 26000
L | Client Entertainment
| REFRESHMENT | L.S. |  |  | 5000
| Total - L |  |  |  | 5000
M | Medical Expenses
| LABOUR TREATMENT (EXCLUDING MAJOR ACCIDENT & INCLUDING P/C M/s MRL LABOUR) | L.S. |  |  | 12000
| Total - M |  |  |  | 12000
N | Insurance Premium
| WC & CAR POLICY | L.S. |  |  | 0
| Total - N |  |  |  | 0
O | Printing & Stationary
| OFFICE STATIONERY (PEN, PENCIL, FILES, A4 PAPER ETC) |  |  |  | 8000
| COMPUTER PERIPHERELS |  |  |  | 5500
| PHOTOCOPY |  |  |  | 2000
| Total - O |  |  |  | 15500
P | Telephone & Fax
1 | MOBILE EXPENSES AS PER CIRCULAR & APPROVAL |  |  |  | 8500
2 | INTERNET & SITE PHONE |  |  |  | 2500
| Total - P |  |  |  | 11000
Q | Postage & Telegram
| COURIER CHARGE |  |  |  | 1000
| Total - Q |  |  |  | 1000
R | Vehicle Running & Maint.
| Store | L.S. | 0 | 750 | 0
| Billing/Planning | L.S. | 0 | 750 | 0
| HR/IR | L.S. | 0 | 500 | 0
| Site | L.S. | 0 | 1000 | 0
| Total - R |  |  |  | 0
S | Watch & Ward
| KORE SEC. (4 GUARD, 1 SUP.) |  |  |  | 50000
| Total - S |  |  |  | 50000
T | Pooja Expenses
| TUESDAY, | L.S. |  |  | 2100
| SITE POOJA EXPENSES | L.S. |  |  | 500
| Total - T |  |  |  | 2600
U | Legal & Professional Charges
| REVENUE STAMP | L.S. |  |  | 100
| STAMP PAPER | L.S. |  |  | 100
| DRAWING CHARGE | L.S. |  |  | 2000
| Total - U |  |  |  | 2200
V | Bank Charges & Commission
| Bank Charges (BG, LC, TT, ETC) | L.S. |  |  | 4000
| Total - V |  |  |  | 4000
W | Interest Paid
| INT. ON MOB. | L.S. |  |  | 0
| Total - W |  |  |  | 0
X | Books, Periodicals & Journal
| NEWS PAPERS & MAGZINE | L.S. | 2 | 250 | 500
| Total - X |  |  |  | 500
Y | OTHER EXPENSES
| ADMN./DEPTT. EXP. | L.S. |  |  | 7000
| CLIENT WELFARE | L.S. |  |  | 0
| Total - Y |  |  |  | 7000
Z | CHARITY & DONATION
| LOCAL FESTIVALS |  |  |  | 1000
| OTHERS |  |  |  | 500
| Total - Z |  |  |  | 1500
TOTAL OVERHEAD EXPENSES : |  |  |  |  | 323100

## HR Salary
MANPOWER LIST DDA KALKAJI ( PERMANENT STAFF )
S.No | Code | Employee Name | Designation | Department | Grade | Join Date | CTC | Remarks
TECHNICAL DEPARTMENT
1 | E14843 | MR ZAHIR KHAN | AGM | TECHNICAL | S12 |  | 135000
2 | E06574 | MANOJ KUMAR | ASSISTANT MANAGER | TECHNICAL | S07 | 2009-04-01 | 59733
3 | E14311 | R.K SHARMA | DPM | TECHNICAL |  |  | 70000
4 | E02153 | BRIJENDAR KUMAR SHARMA | SITE ENGINEER | TECHNICAL | S05 | 2005-06-21 | 42407
5 | E10401 | MD ASIF ALI | ASSISTANT ENGINEER | TECHNICAL | S04 | 2011-03-07 | 29014
6 | E13754 | MOHIT THAKUR | ASSISTANT ENGINEER | TECHNICAL | S04 | 2013-07-22 | 23708
7 | E14550 | T S N BALAJI KUMAR | POST GRADUATE ENGINEER TRAINEE | TECHNICAL | S04 | 2014-06-30 | 25015
8 | E14558 | DANISH AHMAD KHAN | GRADUATE ENGINEER TRAINEE | TECHNICAL | S03 | 2014-06-30 | 15807
9 | E14795 | RAHUL KUMAR GOND | DIPLOMA ENGINEER TRAINEE | TECHNICAL | S03 | 2014-07-28 | 12009
10 | E03783 | BRIJESH KUMAR SINGH | FOREMAN | TECHNICAL | G04 | 2007-07-31 | 20188
11 | E05718 | ASHISH GHOSH | SUPERVISOR | TECHNICAL | G04 | 2008-09-07 | 20831
12 | E14679 | YOGENDRA KUMAR GUPTA | CONSULTANT | TECHNICAL | S08 | 2014-07-22 | 60139
13 |  | AMITH KUMAR | ASSISTANT ENGINEER | TECHNICAL | S04 | 2013-05-13 | 25000
15 | E14867 | RAJESH KUMAR | JUNIOR ENGINEER | TECHNICAL | S03 | 2014-08-12 | 16097
16 | E14488 | GAURAV THAKUR | GRADUATE ENGINEER TRAINEE | TECHNICAL | S03 | 2014-06-23 | 15835
17 | E14497 | ANKIT KUMAR | GRADUATE ENGINEER TRAINEE | TECHNICAL | S03 | 2014-06-23 | 15835
18 | E14961 | BIJENDRA SINGH | SR. SUPERVISOR | TECHNICAL | G05 | 2014-09-02 | 24897
19 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 |  | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862 | E14176 | DINESH KUMAR | ASSISTANT ENGINEER | QUALITY CONTROL | S04 | 2014-03-05 | 26862
20 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 |  | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000 | E14997 | RANJAN MANDAL | LAB TECHNICIAN | QUALITY CONTROL | G04 | 2014-09-19 | 15000
22 |  | AJEET K GOSWAMI |  | TECHNICAL |  |  | 40000
23 | E05919 | MUNIB AHMAD | SUPERVISOR | TECHNICAL |  |  | 20000
|  | RADHESHYAM | SUPERVISOR | TECHNICAL |  |  | 20000
EXECUTION DEPARTMENT | [6 empty] | 733377
BILLING & PLANNING
24 | E14198 | SAURABH PANWAR | ASSISTANT ENGINEER | TECHNICAL | S04 | 2014-03-15 | 30239
BILLING & PLANNING | [6 empty] | 30239
CONSULTANT
25 | E14679 | MR YOGENDAR KUMAR | CONSULTANT | CONSULTANT |  | 22/7/2014 | 50000
PURCHASE DEPARTMENT
26 | E01285 | KHEEMA NAND TIWARI | PURCHASE OFFICER | PURCHASE | S04 | 2002-02-01 | 25039
PURCHASE DEPARTMENT | [6 empty] | 25039
STORE DEPARTMENT
27 | E02491 | DHIRENDERA KUMAR SINGH | STORE KEEPER | STORES | S03 | 2006-03-21 | 16781
28 | E04182 | DHARMENDRA SINGH | ASSISTANT STORE KEEPER | STORES | S02 | 2007-12-18 | 13669
29 | E14880 | MD IRFAN HUSAIN | MATERIAL RECEIVER | STORES | S01 | 2014-08-18 | 11000
STORE DEPARTMENT | [6 empty] | 41450
P & A DEPARTMENT
30 | E01285 | KHEEMANAND TIWARI | ASSISTANT PURCHASE OFFICER | PURCHASE | S04 | 2002-02-01 | 28800
P&A DEPARTMENT | [6 empty] | 28800
F & A DEPARTMENT
31 | E05909 | LALIT KUMAR JHA | JR. OFFICER | FINANCE AND ACCOUNTS | S04 | 2008-11-10 | 27793
F&A DEPARTMENT | [6 empty] | 27793
IT DEPARTMENT
20 | E14173 | PREM PRAKASH MANDOLIA | COMPUTER OPERATOR | IT | S02 | 2014-03-04 | 16375
IT DEPARTMENT | [6 empty] | 16375
SURVEY DEPARTMENT
32 | E05986 | SANJAY KUMAR | SURVEYER | SURVEY | S05 | 2008-12-09 | 33827
SURVEY DEPARTMENT | [6 empty] | 33827
MAINTENANCE DEPARTMENT
33 | E14509 | VIRENDRA | JR.CONCRETE PUMP OPERATOR | MAINTENANCE | H03 | 2014-06-27 | 13031
34 | E11069 | CHANDRA BHUSHAN KUMAR | BATCHING PLANT OPERATOR | MAINTENANCE | H03 | 2011-06-16 | 13636
35 | E08102 | RAJVEER SINGH | CRANE OPERATOR | MAINTENANCE | H03 | 2010-01-01 | 11435
36 | E15009 | UMESH DIXIT | BATCHING PLANT OPERATOR | MAINTENANCE | H03 | 2014-09-22 | 15008
37 | E08395 | SHIV SHYAM MISHRA | SCRAPER OPERATOR | MAINTENANCE | H02 | 2010-03-04 | 10523
38 | E02137 | GAMBHIR SINGH | TRACTOR DRIVER | MAINTENANCE | H02 | 2005-05-28 | 9900
39 | E05022 | MANJEET SINGH | ASSISTANT FOREMAN | MAINTENANCE | G04 | 2008-05-01 | 25133
40 | E14500 | JAGDISH CHANDRA | SR. SUPERVISOR | MAINTENANCE | G04 | 2014-06-26 | 18546
41 | E14524 | SAROJ KUMAR SINGH | SR. ELECTRICIAN | MAINTENANCE | G03 | 2014-06-30 | 13021
42 | E15080 | SURJEET SINGH | MECHANIC | MAINTENANCE | G02 | 2014-10-16 | 11050
43 | E06878 | DEVENDRA YADAVA | ELECTRICIAN | MAINTENANCE | G02 | 2009-06-24 | 10317
45 |  | MOHIT | GET | MAINTENANCE | S03 |  | 15000
MAINTENANCE DEPARTMENT | [6 empty] | 166600
SUB TOTAL | [6 empty] | 1103500

## Daily-Dist.-ERP (hidden)
BOILER / BUNKER / TG AREA [DHANANJAY TIWARI WITH SAURABH CHAUDHARY] | [15 empty] | 2012-09-12
S. NO. | BOQ CODE | Activities | UNIT | Qty | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
[36 empty] | TOTAL | DIFF.
1 | 1(a) | In soil (All types) | Cum | #REF! | 8 | 6 | 6 | 8 | 8 | 3 | 6 | 6 | 8 | 8 | 6 | 6 | 3 | 6 | 8 | 8 | 6 | 6 | 8 |  | 8 | 8 | 6 | 8 | 8 | 6 | 4 | 6 | 8 | 7 | 7 | 200 | #REF!
3 | 7(a) | M 7.5 (with graded agg. of nominal size 40 mm) nominal mix | Cum | #REF! | 4 | 5 | 5 | 4 | 5 | 2 | 5 | 4 | 4 | 5 | 4 | 5 | 2 | 4 | 4 | 5 | 4 | 6 | 5 |  | 4 | 5 | 5 | 4 | 5 | 4 | 2 | 4 | 4.5 | 5.5 | 5 | 130 | #REF!
4 | 7c | M 15 (with graded agg. of nominal size 40 mm) nominal mix | Cum | #REF! | 4 | 3 | 3 | 4 | 4 | 1 | 3 | 4 | 2 | 2 | 4 | 3 | 1 | 4 | 4 | 3 | 4 | 3 | 3 |  | 4 | 3 | 4 | 2 | 3 | 4 | 1 | 2 | 3 | 2 | 3 | 90 | #REF!
4 | 7d | M 20 (with graded agg. of nominal size 12.5 mm) nominal mix | Cum | #REF! | 2 | 1.5 | 1.5 | 2 | 2 | 0.75 | 1.5 | 1.5 | 2 | 2 | 1.5 | 1.5 | 0.75 | 1.5 | 2 | 2 | 1.5 | 1.5 | 2 |  | 1.25 | 2 | 1.5 | 2 | 2 | 1.5 | 1.5 | 1.5 | 2 | 2 | 1.75 | 50 | #REF!
4 | 8(a) | For all works below ground level | Cum | #REF! | 8 | 6 | 6 | 8 | 8 | 3 | 6 | 6 | 8 | 8 | 6 | 6 | 3 | 6 | 8 | 8 | 6 | 6 | 8 |  | 8 | 8 | 6 | 8 | 8 | 6 | 4 | 6 | 8 | 7 | 7 | 200 | #REF!
5 | 8(b) | For all works above ground lvl.(except top deck) | Cum | #REF! | 8 | 6 | 6 | 8 | 8 | 3 | 6 | 6 | 8 | 8 | 6 | 6 | 3 | 6 | 8 | 8 | 6 | 6 | 8 |  | 8 | 8 | 6 | 8 | 8 | 6 | 4 | 6 | 8 | 7 | 7 | 200 | #REF!
6 | 8(c)(i) | M 35 for deck of MDBFP & TDBFP,ID,PA AND FD Fans Supported on vibration isolation system | Cum | #REF! | [5 empty] | 8 | 4 | 8 | 8 | 8 | 7 | 7 | 10 | 4 | 9 | 10 | 12 | 11 | 9 |  | 5 | 9 | 10 | 12 | 12 | 10 | 10 | 4 | 8 | 12 |  | 207 | #REF!
7 | 8(d) | Extra over item no.(c), (i) & (c ) (ii) above for controlling of temperature | Cum | #REF! | [5 empty] | 8 | 4 | 8 | 8 | 8 | 7 | 7 | 10 | 4 | 9 | 10 | 12 | 11 | 9 |  | 5 | 9 | 10 | 12 | 12 | 10 | 10 | 4 | 8 | 12 |  | 207 | #REF!
8 | 9 | Providing & mixing as cement concrete admixtures - super plasticizers | Per bag (50 kg) of cement | #REF! | 56 | 56 | 60 | 52 | 52 | 16 | 68 | 68 | 56 | 56 | 48 | 48 | 16 | 60 | 60 | 52 | 52 | 44 | 44 |  | 52 | 52 | 48 | 48 | 60 | 52 | 16 | 56 | 56 | 48 | 48 | 1500 | #REF!
9 | 11(a) | For works below ground level | MT | #REF! | 1.6 | 1.2 | 1.2 | 1.6 | 1.6 | 0.6 | 1.2 | 1.2 | 1.6 | 1.6 | 1.2 | 1.2 | 0.6 | 1.2 | 1.6 | 1.6 | 1.2 | 1.2 | 1.6 |  | 1.4 | 1.6 | 1.2 | 1.6 | 1.6 | 1.2 | 0.8 | 1.2 | 1.6 | 1.6 | 1.4 | 40 | #REF!
10 | 11(b)(ii) | High Strength deformed TMT bars | MT | #REF! | 0.8 | 0.6 | 0.6 | 0.8 | 0.8 | 0.3 | 0.6 | 0.6 | 0.8 | 0.8 | 0.6 | 0.6 | 0.3 | 0.6 | 0.8 | 0.8 | 0.6 | 0.6 | 0.8 |  | 0.7 | 0.8 | 0.6 | 0.8 | 0.8 | 0.6 | 0.4 | 0.6 | 0.8 | 0.8 | 0.7 | 20 | #REF!
11 | 12(a) | For works below ground level | Sqm | #REF! | 10 | 14 | 12 | 10 | 10 | 4 | 10 | 8 | 12 | 12 | 10 | 10 | 4 | 8 | 8 | 10 | 10 | 12 | 4 |  | 10 | 10 | 8 | 12 | 12 | 14 | 4 | 14 | 12 | 12 | 14 | 300 | #REF!
12 | 12(b) | For works above ground level | Sqm | #REF! | 60 | 64 | 54 | 58 | 62 | 28 | 64 | 58 | 58 | 60 | 62 | 62 | 28 | 60 | 60 | 62 | 58 | 58 | 64 |  | 62 | 56 | 58 | 56 | 62 | 64 | 28 | 58 | 60 | 60 | 56 | 1700 | #REF!
13 | 13(b)(ii) | For TDBFP & MDBFP deck | Sqm | #REF! | [5 empty] | 12 | 6 | 10 | 10 | 12 | 10 | 12 | 14 | 5 | 12 | 10 | 14 | 18 | 15 |  | 10 | 15 | 15 | 12 | 10 | 10 | 12 | 6 | 14 | 15 |  | 279 | #REF!
14 | 15(a) | MS pipes of all diameters | Quintal | #REF! | 1 | 1.4 | 1.2 | 1 | 1 | 0.4 | 1 | 0.8 | 1.2 | 1.2 | 1 | 1 | 0.4 | 0.8 | 0.8 | 1 | 1 | 1.2 | 0.4 |  | 1 | 1 | 0.8 | 1.2 | 1.2 | 1.4 | 0.4 | 1.4 | 1.2 | 1.2 | 1.4 | 30 | #REF!
15 | 15(b) | PVC conduits of all sizes | Quintal | #REF! | 0.25 | 0.5 | 0.25 | 0.3 | 0.4 |  | 0.25 | 0.25 | 0.4 | 0.4 | 0.2 | 0.25 |  | 0.2 | 0.25 | 0.25 | 0.2 | 0.2 | 0.25 |  | 0.25 | 0.3 | 0.4 | 0.5 | 0.3 | 0.3 |  | 0.25 | 0.2 | 0.4 | 0.3 | 8 | #REF!
16 | 18a | Cement sand grout | cu.dm | #REF! | 80 | 60 | 70 | 80 | 80 | 30 | 60 | 60 | 80 | 80 | 60 | 80 | 30 | 60 | 80 | 80 | 60 | 60 | 80 |  | 60 | 80 | 60 | 80 | 80 | 60 | 30 | 60 | 80 | 80 | 60 | 2000 | #REF!
17 | 20a | PVC water stop ribbed with central bulb 225 x6mm | Rmt | #REF! | 2 | 1.5 | 1.5 | 2 | 2 | 0.75 | 1.5 | 1.5 | 2 | 2 | 1.5 | 1.5 | 0.75 | 1.5 | 2 | 2 | 1.5 | 1.5 | 2 |  | 1.25 | 2 | 1.5 | 2 | 2 | 1.5 | 1.5 | 1.5 | 2 | 2 | 1.75 | 50 | #REF!
18 | 23a | chipping of RCC/PCC i/c disposal upto 2km beyond the plant boundary | cu.dm | #REF! | 80 | 60 | 70 | 80 | 80 | 30 | 60 | 60 | 80 | 80 | 60 | 80 | 30 | 60 | 80 | 80 | 60 | 60 | 80 |  | 60 | 80 | 60 | 80 | 80 | 60 | 30 | 60 | 80 | 80 | 60 | 2000 | #REF!
19 | I.25a | S/F/INS Bolts, | MT | [32 empty] | 0 | 0
|  | Fabrication 65% | MT | #REF! | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 2 | #REF!
|  | Erection 10% | MT | #REF! | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 2 | #REF!
|  | Alignment10% | MT | #REF! | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 2 | #REF!
|  | Handed Over 10% | MT | #REF! | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 2 | #REF!
|  | Material reconcilation 5% | MT | #REF! | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 2 | #REF!
20 | J.36ai | Burnt Clay Brick work in 1:6 | cum | #REF! | 4 | 5 | 6 | 4 | 6 | 1 | 6 | 3 | 4 | 4 | 3 | 3 | 1 | 3 | 4 | 4 | 3 | 3 | 5 |  | 2 | 4 | 3 | 4 | 4 | 2 | 1 | 4 | 5 | 4 | 5 | 110 | #REF!
21 | 38a | 18mm CM 1:4 (Cement : fine sand) | Sqm | #REF! | 16 | 12 | 12 | 16 | 16 | 6 | 12 | 12 | 16 | 16 | 12 | 12 | 6 | 12 | 16 | 16 | 12 | 12 | 16 |  | 16 | 16 | 12 | 16 | 16 | 12 | 8 | 12 | 16 | 14 | 14 | 400 | #REF!
22 | 38b | 12mm thick Cement Plaster in fine sand | Sqm | #REF! | 4 | 3 | 2 | 2 | 2 | 0.5 | 3 | 2.5 | 2.5 | 3 | 2 | 2.5 | 0.5 | 2.5 | 3.5 | 2.5 | 3 | 3 | 4 |  | 3 | 2.5 | 2.5 | 3 | 3 | 4 | 0.5 | 4 | 2.5 | 2.5 | 4.5 | 80 | #REF!
23 | 41a | OBD | Sqm | #REF! | 60 | 60 | 54 | 54 | 58 | 30 | 60 | 60 | 52 | 52 | 54 | 54 | 30 | 48 | 58 | 56 | 56 | 48 | 58 |  | 58 | 60 | 56 | 52 | 52 | 50 | 30 | 58 | 58 | 60 | 64 | 1600 | #REF!
22 | 49a | mineral wool insulation 50 mm th with framed strips | Cum | #REF! | 16 | 12 | 12 | 16 | 16 | 6 | 12 | 12 | 16 | 16 | 12 | 12 | 6 | 12 | 16 | 16 | 12 | 12 | 16 |  | 16 | 16 | 12 | 16 | 16 | 12 | 8 | 12 | 16 | 14 | 14 | 400 | #REF!
23 | 51b | Matalic hardner topping | sqm | #REF! | 40 | 30 | 35 | 40 | 40 | 15 | 30 | 30 | 40 | 40 | 30 | 40 | 15 | 30 | 40 | 40 | 30 | 30 | 40 |  | 30 | 40 | 30 | 40 | 40 | 30 | 15 | 30 | 40 | 40 | 30 | 1000 | #REF!
24 | 51h | 18-20mm the Granite stone flooring | sqm | #REF! | 16 | 12 | 12 | 16 | 16 | 6 | 12 | 12 | 16 | 16 | 12 | 12 | 6 | 12 | 16 | 16 | 12 | 12 | 16 |  | 16 | 16 | 12 | 16 | 16 | 12 | 8 | 12 | 16 | 14 | 14 | 400 | #REF!
25 | 52 | Acid proof seamless Epoxy flooring 300 mcr | Sqm | #REF! | 10 | 14 | 12 | 10 | 10 | 4 | 10 | 8 | 12 | 12 | 10 | 10 | 4 | 8 | 8 | 10 | 10 | 12 | 4 |  | 10 | 10 | 8 | 12 | 12 | 14 | 4 | 14 | 12 | 12 | 14 | 300 | #REF!
26 | 53 | P/f pressed steel door frame sheet 1.25mm th. | Rmt | #REF! | 0.8 | 0.6 | 0.6 | 0.8 | 0.8 | 0.3 | 0.6 | 0.6 | 0.8 | 0.8 | 0.6 | 0.6 | 0.3 | 0.6 | 0.8 | 0.8 | 0.6 | 0.6 | 0.8 |  | 0.7 | 0.8 | 0.6 | 0.8 | 0.8 | 0.6 | 0.4 | 0.6 | 0.8 | 0.8 | 0.7 | 20 | #REF!
27 | 57 | fire door metal double sheet shutter | Sqm | #REF! | 0.25 | 0.5 | 0.25 | 0.3 | 0.4 |  | 0.25 | 0.25 | 0.4 | 0.4 | 0.2 | 0.25 |  | 0.2 | 0.25 | 0.25 | 0.2 | 0.2 | 0.25 |  | 0.25 | 0.3 | 0.4 | 0.5 | 0.3 | 0.3 |  | 0.25 | 0.2 | 0.4 | 0.3 | 8 | #REF!
28 | 58 | aluminium work for door, windows, ventilators etc. | kg | #REF! | 20 | 14 | 16 | 16 | 18 | 6 | 16 | 16 | 18 | 18 | 14 | 14 | 6 | 16 | 20 | 20 | 16 | 16 | 18 |  | 18 | 20 | 18 | 20 | 20 | 18 | 6 | 22 | 22 | 20 | 18 | 500 | #REF!
29 | 68aii | 100mm to 150mm nominal bore | Quintal | #REF! | 0.8 | 0.6 | 0.6 | 0.8 | 0.8 | 0.3 | 0.6 | 0.6 | 0.8 | 0.8 | 0.6 | 0.6 | 0.3 | 0.6 | 0.8 | 0.8 | 0.6 | 0.6 | 0.8 |  | 0.7 | 0.8 | 0.6 | 0.8 | 0.8 | 0.6 | 0.4 | 0.6 | 0.8 | 0.8 | 0.7 | 20 | #REF!
30 | 70b | Providing the toilet block with all fixtures ang fittings | Nos | #REF! | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 2 | #REF!
31 | 73b | 200 mm dia LA class | M | #REF! | 0.8 | 0.6 | 0.6 | 0.8 | 0.8 | 0.3 | 0.6 | 0.6 | 0.8 | 0.8 | 0.6 | 0.6 | 0.3 | 0.6 | 0.8 | 0.8 | 0.6 | 0.6 | 0.8 |  | 0.7 | 0.8 | 0.6 | 0.8 | 0.8 | 0.6 | 0.4 | 0.6 | 0.8 | 0.8 | 0.7 | 20 | #REF!
32 | 75a | Constructing RCC man hole | Each | #REF! | 0.4 | 0.3 | 0.3 | 0.4 | 0.4 | 0.15 | 0.3 | 0.3 | 0.4 | 0.4 | 0.3 | 0.3 | 0.15 | 0.3 | 0.4 | 0.4 | 0.3 | 0.3 | 0.4 |  | 0.35 | 0.4 | 0.3 | 0.4 | 0.4 | 0.3 | 0.2 | 0.3 | 0.4 | 0.4 | 0.35 | 10 | #REF!
33 | 78 | Earthing Mat | MT | #REF! | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 2 | #REF!
[36 empty] | 0 | 0
MPH BOILER / ESP AREA [SHIV KUMAR RAJPUT E06405 WITH SHREEPAL E03922] | [35 empty] | 0 | 0
1 | 1(a) | In soil (All types) | Cum | #REF! | 32 | 24 | 24 | 32 | 32 | 12 | 24 | 24 | 32 | 32 | 24 | 24 | 12 | 24 | 32 | 32 | 24 | 24 | 32 |  | 32 | 32 | 24 | 32 | 32 | 24 | 16 | 24 | 32 | 28 | 28 | 800 | #REF!
2 | 6a | 63 mm to 45 mm graded hard stone agg. | Cum | 277 | 4 | 3 | 3 | 4 | 4 | 1.5 | 3 | 3 | 4 | 4 | 3 | 3 | 1.5 | 3 | 4 | 4 | 3 | 3 | 4 |  | 4 | 4 | 3 | 4 | 4 | 3 | 2 | 3.5 | 4 | 3.5 | 3 | 100 | 177
3 | 6b | Clean 40mm nominal size stone laid in layers not exceeding 200 mm in thickness & lightly tamped | Cum | #REF! | 1.6 | 1.2 | 1.2 | 1.6 | 1.6 | 0.6 | 1.2 | 1.2 | 1.6 | 1.6 | 1.2 | 1.2 | 0.6 | 1.2 | 1.6 | 1.6 | 1.2 | 1.2 | 1.6 |  | 1.4 | 1.6 | 1.2 | 1.6 | 1.6 | 1.2 | 0.8 | 1.2 | 1.6 | 1.6 | 1.4 | 40 | #REF!
4 | 7a | M 7.5 (with graded agg. of nominal size 40 mm) nominal mix | Cum | 145 | 2 | 2.8 | 2.4 | 2 | 2 | 0.8 | 2 | 1.6 | 2.4 | 2.4 | 2 | 2 | 0.8 | 1.6 | 1.6 | 2 | 2 | 2.4 | 0.8 |  | 2 | 2 | 1.6 | 2.4 | 2.4 | 2.8 | 0.8 | 2.8 | 2.4 | 2.4 | 2.8 | 60 | 85
5 | 7c | M 15 (with graded agg. of nominal size 40 mm) nominal mix | Cum | #REF! | 4 | 3 | 3 | 4 | 4 | 1.5 | 3 | 3 | 4 | 4 | 3 | 3 | 1.5 | 3 | 4 | 4 | 3 | 3 | 4 |  | 4 | 4 | 3 | 4 | 4 | 3 | 2 | 3.5 | 4 | 3.5 | 3 | 100 | #REF!
6 | 8(a) | For all works below ground level | Cum | 285 | 20 | 18 | 18 | 20 | 22 | 8 | 16 | 16 | 18 | 18 | 16 | 16 | 8 | 18 | 18 | 22 | 22 | 18 | 18 |  | 18 | 24 | 22 | 22 | 20 | 24 | 8 | 22 | 22 | 20 | 18 | 550 | -265
7 | 8(b) | For all works above ground lvl.(except top deck) | Cum | 485 | 2 | 1.5 | 1.5 | 2 | 2 | 0.75 | 1.5 | 1.5 | 2 | 2 | 1.5 | 1.5 | 0.75 | 1.5 | 2 | 2 | 1.5 | 1.5 | 2 |  | 1.25 | 2 | 1.5 | 2 | 2 | 1.5 | 1.5 | 1.5 | 2 | 2 | 1.75 | 50 | 435
8 | 8(d) | Extra over item no.(c), (i) & (c ) (ii) above for controlling of temperature | Cum | #REF! | 4 | 5 | 5 | 4 | 5 | 2 | 5 | 4 | 4 | 5 | 4 | 5 | 2 | 4 | 4 | 5 | 4 | 6 | 5 |  | 4 | 5 | 5 | 4 | 5 | 4 | 2 | 4 | 4.5 | 5.5 | 5 | 130 | #REF!
9 | 11(a) | For works below ground level | MT | 18.5 | 2 | 1.5 | 1.5 | 2 | 2 | 0.75 | 1.5 | 1.5 | 2 | 2 | 1.5 | 1.5 | 0.75 | 1.5 | 2 | 2 | 1.5 | 1.5 | 2 |  | 1.25 | 2 | 1.5 | 2 | 2 | 1.5 | 1.5 | 1.5 | 2 | 2 | 1.75 | 50 | -31.5
10 | 11(b)(ii) | High Strength deformed TMT bars | MT | 73 | 0.4 | 0.3 | 0.3 | 0.4 | 0.4 | 0.15 | 0.3 | 0.3 | 0.4 | 0.4 | 0.3 | 0.3 | 0.15 | 0.3 | 0.4 | 0.4 | 0.3 | 0.3 | 0.4 |  | 0.35 | 0.4 | 0.3 | 0.4 | 0.4 | 0.3 | 0.2 | 0.3 | 0.4 | 0.4 | 0.35 | 10 | 63
11 | 12(a) | For works below ground level | Sqm | 560 | 10 | 7 | 8 | 8 | 9 | 3 | 8 | 8 | 9 | 9 | 7 | 7 | 6 | 8 | 10 | 10 | 8 | 8 | 9 |  | 9 | 10 | 9 | 10 | 10 | 9 | 3 | 8 | 11 | 10 | 9 | 250 | 310
12 | 12(b) | For works above ground level | Sqm | 2680 | 20 | 14 | 16 | 16 | 18 | 6 | 16 | 16 | 18 | 18 | 14 | 14 | 6 | 16 | 20 | 20 | 16 | 16 | 18 |  | 18 | 20 | 18 | 20 | 20 | 18 | 6 | 22 | 22 | 20 | 18 | 500 | 2180
13 | G17 | Laying of rail | M.T. | #REF! | 0.25 | 0.5 | 0.25 | 0.3 | 0.4 |  | 0.25 | 0.25 | 0.4 | 0.4 | 0.2 | 0.25 |  | 0.2 | 0.25 | 0.25 | 0.2 | 0.2 | 0.25 |  | 0.25 | 0.3 | 0.4 | 0.5 | 0.3 | 0.3 |  | 0.25 | 0.2 | 0.4 | 0.3 | 8 | #REF!
14 | I.25a | S/F/INS Bolts, | MT | [32 empty] | 0 | 0
|  | Fabrication 65% | MT | #REF! | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 2 | #REF!
|  | Erection 10% | MT | #REF! | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 2 | #REF!
|  | Alignment10% | MT | #REF! | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 2 | #REF!
|  | Handed Over 10% | MT | #REF! | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 2 | #REF!
|  | Material reconcilation 5% | MT | #REF! | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 2 | #REF!
[36 empty] | 0 | 0
FABRICATION WORK [AJAI KUMAR E04944 WITH SUNIL LAMBA] | [35 empty] | 0 | 0
1 | I.26a-1 | Fabrication of str. Steel 65% | MT | #REF! | 28 | 28 | 30 | 26 | 26 | 8 | 34 | 34 | 28 | 28 | 24 | 24 | 8 | 30 | 30 | 26 | 26 | 22 | 22 |  | 26 | 26 | 24 | 24 | 30 | 26 | 8 | 28 | 28 | 24 | 24 | 750 | #REF!
| I.26b-5 | Material Reconcillation 10% | MT | #REF! | 56 | 56 | 60 | 52 | 52 | 16 | 68 | 68 | 56 | 56 | 48 | 48 | 16 | 60 | 60 | 52 | 52 | 44 | 44 |  | 52 | 52 | 48 | 48 | 60 | 52 | 16 | 56 | 56 | 48 | 48 | 1500 | #REF!
2 | I27b | SS HOOPER | MT | #REF! | [5 empty] | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.4 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0.4 | 0.2 |  | 0.3 | 0.3 | 0.3 | 0 | 0.3 | 0.2 | 0.3 | 0.2 | 0.2 | 0.16 |  | 5.26 | #REF!
3 | I.28a | BLAST CLEANING | MT | #REF! | [5 empty] | 56 | 21 | 42 | 56 | 56 | 42 | 49 | 42 | 35 | 56 | 56 | 42 | 42 | 49 |  | 28 | 56 | 49 | 56 | 56 | 42 | 42 | 42 | 56 | 49 |  | 1120 | #REF!
4 | I.28b | Applying intermediate coat | MT | #REF! | [5 empty] | 56 | 21 | 42 | 56 | 56 | 42 | 49 | 42 | 35 | 56 | 56 | 42 | 42 | 49 |  | 28 | 56 | 49 | 56 | 56 | 42 | 42 | 42 | 56 | 49 |  | 1120 | #REF!
[36 empty] | 0 | 0
ERECTION WORK [VISHAL KAUSHIK, VIPIN KUMAR WITH KUNJ BIHARI & JITENDRA PAL SINGH] | [35 empty] | 0 | 0
1 | I.26a-2 | Erection 7.5% | MT | 700 | [5 empty] | 34 | 31.5 | 63 | 74 | 69 | 68 | 63.5 | 75 | 22.5 | 64 | 72 | 63 | 75 | 75.5 |  | 27 | 64 | 63.5 | 79 | 64 | 78 | 78 | 33 | 56 | 58.5 |  | 1451 | -751
| I.26a-3 | Alignment 7.5% | MT | 1400 | 80 | 60 | 70 | 80 | 80 | 30 | 60 | 60 | 80 | 80 | 60 | 80 | 30 | 60 | 80 | 80 | 60 | 60 | 80 |  | 60 | 80 | 60 | 80 | 80 | 60 | 30 | 60 | 80 | 80 | 60 | 2000 | -600
| I.26a-4 | Handed Over 10% | MT | 1400 | 80 | 60 | 70 | 80 | 80 | 30 | 60 | 60 | 80 | 80 | 60 | 80 | 30 | 60 | 80 | 80 | 60 | 60 | 80 |  | 60 | 80 | 60 | 80 | 80 | 60 | 30 | 60 | 80 | 80 | 60 | 2000 | -600
2 | I.27b | S/F/erection of s s railing | Kg | #REF! | [5 empty] | 60 | 22.5 | 45 | 60 | 60 | 45 | 52.5 | 45 | 37.5 | 60 | 60 | 45 | 45 | 52.5 |  | 30 | 60 | 52.5 | 60 | 60 | 45 | 45 | 45 | 60 | 52.5 |  | 1200 | #REF!
2 | I.28c | POLYMIDE CURED EPOXY 75 MICRON | MT | 1500 | 32 | 24 | 24 | 32 | 32 | 12 | 24 | 24 | 32 | 32 | 24 | 24 | 12 | 24 | 32 | 32 | 24 | 24 | 32 |  | 32 | 32 | 24 | 32 | 32 | 24 | 16 | 24 | 32 | 28 | 28 | 800 | 700
3 | I29a | P/F electro forged grating | MT | #REF! | [5 empty] | 4 | 1.5 | 3 | 4 | 4 | 3 | 3.5 | 3 | 2.5 | 4 | 4 | 3 | 3 | 3.5 |  | 2 | 4 | 3.5 | 4 | 4 | 3 | 3 | 3 | 4 | 3.5 |  | 80 | #REF!
4 | 31 | Neoprene Bellow Straps | Rmt | 86 | 4 | 3 | 2 | 2 | 2 | 0.5 | 3 | 2.5 | 2.5 | 3 | 2 | 2.5 | 0.5 | 2.5 | 3.5 | 2.5 | 3 | 3 | 4 |  | 3 | 2.5 | 2.5 | 3 | 3 | 4 | 0.5 | 4 | 2.5 | 2.5 | 4.5 | 80 | 6
5 | 32 | dismantling st.steel | MT | #REF! | [5 empty] | 100 | 37.5 | 75 | 100 | 100 | 75 | 87.5 | 75 | 62.5 | 100 | 100 | 75 | 75 | 87.5 |  | 50 | 100 | 87.5 | 100 | 100 | 75 | 75 | 75 | 100 | 87.5 |  | 2000 | #REF!
4 | 34 | Re-Erection | MT | #REF! | [5 empty] | 112 | 42 | 84 | 112 | 112 | 84 | 98 | 84 | 70 | 112 | 112 | 84 | 84 | 98 |  | 56 | 112 | 98 | 112 | 112 | 84 | 84 | 84 | 112 | 98 |  | 2240 | #REF!
4 | 35b | PTFE slide bearing 40 MT to 150 MT | MT | #REF! | [5 empty] | 112 | 42 | 84 | 112 | 112 | 84 | 98 | 84 | 70 | 112 | 112 | 84 | 84 | 98 |  | 56 | 112 | 98 | 112 | 112 | 84 | 84 | 84 | 112 | 98 |  | 2240 | #REF!
5 | L.45 | colour coated metal decking 0.8 mm | Sqm | 2000 | 56 | 56 | 60 | 52 | 52 | 16 | 68 | 68 | 56 | 56 | 48 | 48 | 16 | 60 | 60 | 52 | 52 | 44 | 44 |  | 52 | 52 | 48 | 48 | 60 | 52 | 16 | 56 | 56 | 48 | 48 | 1500 | 500
5 | L.46a | colour coated metal decking 0.6 mm | Sqm | 5000 | 40 | 30 | 35 | 40 | 40 | 15 | 30 | 30 | 40 | 40 | 30 | 40 | 15 | 30 | 40 | 40 | 30 | 30 | 40 |  | 30 | 40 | 30 | 40 | 40 | 30 | 15 | 30 | 40 | 40 | 30 | 1000 | 4000
ROAD / OFFSITE BUILD. AREA [BADRI SINGH E00142 WITH BRIJ BIHARI SINGH & 4 DETs] | [35 empty] | 0 | 0
1 | 2a | In soil (all types) | Cum | #REF! | [5 empty] | 120 | 45 | 90 | 120 | 120 | 90 | 105 | 90 | 75 | 120 | 120 | 90 | 90 | 105 |  | 60 | 120 | 105 | 120 | 120 | 90 | 90 | 90 | 120 | 105 |  | 2400 | #REF!
2 | 7a | M 7.5 (with graded agg. of nominal size 40 mm) nominal mix | Cum | #REF! | 16 | 12 | 12 | 16 | 16 | 6 | 12 | 12 | 16 | 16 | 12 | 12 | 6 | 12 | 16 | 16 | 12 | 12 | 16 |  | 16 | 16 | 12 | 16 | 16 | 12 | 8 | 12 | 16 | 14 | 14 | 400 | #REF!
3 | 7d | M 20 (with graded agg. of nominal size 12.5 mm) nominal mix | Cum | 22 | 4 | 3 | 2 | 2 | 2 | 0.5 | 3 | 2.5 | 2.5 | 3 | 2 | 2.5 | 0.5 | 2.5 | 3.5 | 2.5 | 3 | 3 | 4 |  | 3 | 2.5 | 2.5 | 3 | 3 | 4 | 0.5 | 4 | 2.5 | 2.5 | 4.5 | 80 | -58
4 | 8(a) | For all works below ground level | Cum | 100 | 40 | 30 | 35 | 40 | 40 | 15 | 30 | 30 | 40 | 40 | 30 | 40 | 15 | 30 | 40 | 40 | 30 | 30 | 40 |  | 30 | 40 | 30 | 40 | 40 | 30 | 15 | 30 | 40 | 40 | 30 | 1000 | -900
5 | 8(b) | For all works above ground lvl.(except top deck) | Cum | #REF! | 16 | 12 | 12 | 16 | 16 | 6 | 12 | 12 | 16 | 16 | 12 | 12 | 6 | 12 | 16 | 16 | 12 | 12 | 16 |  | 16 | 16 | 12 | 16 | 16 | 12 | 8 | 12 | 16 | 14 | 14 | 400 | #REF!
6 | 10a | Providing & applying damp proofing & water proofing | Sqm | #REF! | 10 | 7 | 8 | 8 | 9 | 3 | 8 | 8 | 9 | 9 | 7 | 7 | 6 | 8 | 10 | 10 | 8 | 8 | 9 |  | 9 | 10 | 9 | 10 | 10 | 9 | 3 | 8 | 11 | 10 | 9 | 250 | #REF!
7 | 11(a) | For works below ground level | MT | #REF! | 4 | 5 | 5 | 4 | 5 | 2 | 5 | 4 | 4 | 5 | 4 | 5 | 2 | 4 | 4 | 5 | 4 | 6 | 5 |  | 4 | 5 | 5 | 4 | 5 | 4 | 2 | 4 | 4.5 | 5.5 | 5 | 130 | #REF!
8 | 11(b)(ii) | High Strength deformed TMT bars | MT | 3.5 | 1.6 | 1.2 | 1.2 | 1.6 | 1.6 | 0.6 | 1.2 | 1.2 | 1.6 | 1.6 | 1.2 | 1.2 | 0.6 | 1.2 | 1.6 | 1.6 | 1.2 | 1.2 | 1.6 |  | 1.4 | 1.6 | 1.2 | 1.6 | 1.6 | 1.2 | 0.8 | 1.2 | 1.6 | 1.6 | 1.4 | 40 | -36.5
9 | 12(a) | For works below ground level | Sqm | #REF! | [5 empty] | 40 | 15 | 30 | 40 | 40 | 30 | 35 | 30 | 25 | 40 | 40 | 30 | 30 | 35 |  | 20 | 40 | 35 | 40 | 40 | 30 | 30 | 30 | 40 | 35 |  | 800 | #REF!
10 | 12(b) | For works above ground level | Sqm | 350 | 56 | 56 | 60 | 52 | 52 | 16 | 68 | 68 | 56 | 56 | 48 | 48 | 16 | 60 | 60 | 52 | 52 | 44 | 44 |  | 52 | 52 | 48 | 48 | 60 | 52 | 16 | 56 | 56 | 48 | 48 | 1500 | -1150
11 | 15a | MS pipes of all diameters | Qtl | #REF! | 0.4 | 0.3 | 0.3 | 0.4 | 0.4 | 0.15 | 0.3 | 0.3 | 0.4 | 0.4 | 0.3 | 0.3 | 0.15 | 0.3 | 0.4 | 0.4 | 0.3 | 0.3 | 0.4 |  | 0.35 | 0.4 | 0.3 | 0.4 | 0.4 | 0.3 | 0.2 | 0.3 | 0.4 | 0.4 | 0.35 | 10 | #REF!
12 | 15b | PVC conduits of all sizes | Qtl | #REF! | 0.25 | 0.5 | 0.25 | 0.3 | 0.4 |  | 0.25 | 0.25 | 0.4 | 0.4 | 0.2 | 0.25 |  | 0.2 | 0.25 | 0.25 | 0.2 | 0.2 | 0.25 |  | 0.25 | 0.3 | 0.4 | 0.5 | 0.3 | 0.3 |  | 0.25 | 0.2 | 0.4 | 0.3 | 8 | #REF!
13 | J.36ai | Burnt Clay Brick work in 1:6 | cum | 225 | 8 | 6 | 6 | 8 | 8 | 3 | 6 | 6 | 8 | 8 | 6 | 6 | 3 | 6 | 8 | 8 | 6 | 6 | 8 |  | 8 | 8 | 6 | 8 | 8 | 6 | 4 | 6 | 8 | 7 | 7 | 200 | 25
14 | 38a | 18mm CM 1:4 (Cement : fine sand) | Sqm | 301 | 20 | 14 | 16 | 16 | 18 | 6 | 16 | 16 | 18 | 18 | 14 | 14 | 6 | 16 | 20 | 20 | 16 | 16 | 18 |  | 18 | 20 | 18 | 20 | 20 | 18 | 6 | 22 | 22 | 20 | 18 | 500 | -199
15 | 38b | 12mm thick Cement Plaster in fine sand | Sqm | 1850 | 16 | 12 | 12 | 16 | 16 | 6 | 12 | 12 | 16 | 16 | 12 | 12 | 6 | 12 | 16 | 16 | 12 | 12 | 16 |  | 16 | 16 | 12 | 16 | 16 | 12 | 8 | 12 | 16 | 14 | 14 | 400 | 1450
16 | 38d | 6mm thick plaster on ceiling | Sqm | 35 | 10 | 14 | 12 | 10 | 10 | 4 | 10 | 8 | 12 | 12 | 10 | 10 | 4 | 8 | 8 | 10 | 10 | 12 | 4 |  | 10 | 10 | 8 | 12 | 12 | 14 | 4 | 14 | 12 | 12 | 14 | 300 | -265
17 | 41a | OBD | Sqm | 450 | 16 | 12 | 12 | 16 | 16 | 6 | 12 | 12 | 16 | 16 | 12 | 12 | 6 | 12 | 16 | 16 | 12 | 12 | 16 |  | 16 | 16 | 12 | 16 | 16 | 12 | 8 | 12 | 16 | 14 | 14 | 400 | 50
18 | 41c | Acrylic emulsion paint | Sqm | #REF! | 4 | 5 | 5 | 4 | 5 | 2 | 5 | 4 | 4 | 5 | 4 | 5 | 2 | 4 | 4 | 5 | 4 | 6 | 5 |  | 4 | 5 | 5 | 4 | 5 | 4 | 2 | 4 | 4.5 | 5.5 | 5 | 130 | #REF!
19 | 41d | chemical resistant paint | Sqm | #REF! | 4 | 3 | 2 | 2 | 2 | 0.5 | 3 | 2.5 | 2.5 | 3 | 2 | 2.5 | 0.5 | 2.5 | 3.5 | 2.5 | 3 | 3 | 4 |  | 3 | 2.5 | 2.5 | 3 | 3 | 4 | 0.5 | 4 | 2.5 | 2.5 | 4.5 | 80 | #REF!
20 | 43b | granular textured coating 2.5 mm | Sqm | #REF! | [5 empty] | 8 | 4 | 8 | 10 | 8 | 10 | 7 | 10 | 4 | 9 | 10 | 12 | 11 | 12 |  | 5 | 12 | 10 | 7 | 12 | 7 | 10 | 4 | 8 | 8 |  | 206 | #REF!
21 | 51aii | Vitrified tiles in flooring/Skirting risers | Sqm | #REF! | [5 empty] | 8 | 4 | 8 | 10 | 8 | 10 | 7 | 10 | 4 | 9 | 10 | 12 | 11 | 12 |  | 5 | 12 | 10 | 7 | 12 | 7 | 10 | 4 | 8 | 8 |  | 206 | #REF!
22 | 51b | Matalic hardner topping | Sqm | 1050 | 20 | 14 | 16 | 16 | 18 | 6 | 16 | 16 | 18 | 18 | 14 | 14 | 6 | 16 | 20 | 20 | 16 | 16 | 18 |  | 18 | 20 | 18 | 20 | 20 | 18 | 6 | 22 | 22 | 20 | 18 | 500 | 550
23 | 58 | aluminium work for door, windows, ventilators etc. | Kg | 1200 | 16 | 12 | 12 | 16 | 16 | 6 | 12 | 12 | 16 | 16 | 12 | 12 | 6 | 12 | 16 | 16 | 12 | 12 | 16 |  | 16 | 16 | 12 | 16 | 16 | 12 | 8 | 12 | 16 | 14 | 14 | 400 | 800
24 | 60ai | Rolling shutter manual oprated | Sqm | #REF! | 0.8 | 0.6 | 0.6 | 0.8 | 0.8 | 0.3 | 0.6 | 0.6 | 0.8 | 0.8 | 0.6 | 0.6 | 0.3 | 0.6 | 0.8 | 0.8 | 0.6 | 0.6 | 0.8 |  | 0.7 | 0.8 | 0.6 | 0.8 | 0.8 | 0.6 | 0.4 | 0.6 | 0.8 | 0.8 | 0.7 | 20 | #REF!
25 | 66a | PVC Coated Chain link fencing | Sqm | #REF! | [5 empty] | 8 | 3 | 10 | 8 | 8 | 10 | 7 | 6 | 5 | 8 | 8 | 6 | 10 | 7 |  | 4 | 8 | 7 | 8 | 8 | 10 | 6 | 6 | 8 | 7 |  | 176 | #REF!
26 | 68aii | 100mm to 150mm nominal bore | Qtl | #REF! | 1.6 | 1.2 | 1.2 | 1.6 | 1.6 | 0.6 | 1.2 | 1.2 | 1.6 | 1.6 | 1.2 | 1.2 | 0.6 | 1.2 | 1.6 | 1.6 | 1.2 | 1.2 | 1.6 |  | 1.4 | 1.6 | 1.2 | 1.6 | 1.6 | 1.2 | 0.8 | 1.2 | 1.6 | 1.6 | 1.4 | 40 | #REF!
27 | 70a | WC pan with white solid plastic seat | Nos | 1 | [5 empty] | 1 | 0.5 | 1.5 | 2 | 2 | 1.5 | 1 | 2 | 0.5 | 2 | 1.25 | 1.5 | 1.5 | 1.5 |  | 1 | 1.5 | 1 | 2 | 1 | 1.5 | 1.5 | 0.5 | 1.5 | 1.75 |  | 33 | -32
28 | 70b | Providing the toilet block with all fixtures ang fittings | Nos | 1 | [5 empty] | 1 | 0.5 | 1.5 | 2 | 2 | 1.5 | 1 | 2 | 0.5 | 2 | 1.25 | 1.5 | 1.5 | 1.5 |  | 1 | 1.5 | 1 | 2 | 1 | 1.5 | 1.5 | 0.5 | 1.5 | 1.75 |  | 33 | -32
29 | 74a | 200 mm dia pipeNP3 | Rmt | #REF! | [5 empty] | 1 | 0.5 | 1.5 | 2 | 2 | 1.5 | 1 | 2 | 0.5 | 2 | 1.25 | 1.5 | 1.5 | 1.5 |  | 1 | 1.5 | 1 | 2 | 1 | 1.5 | 1.5 | 0.5 | 1.5 | 1.75 |  | 33 | #REF!
30 | 74b | 300 mm dia pipeNP3 | Rmt | #REF! | 8 | 6 | 6 | 8 | 8 | 3 | 6 | 6 | 8 | 8 | 6 | 6 | 3 | 6 | 8 | 8 | 6 | 6 | 8 |  | 8 | 8 | 6 | 8 | 8 | 6 | 4 | 6 | 8 | 7 | 7 | 200 | #REF!
31 | 74c | 450 mm dia pipeNP3 | Rmt | #REF! | 0.8 | 0.6 | 0.6 | 0.8 | 0.8 | 0.3 | 0.6 | 0.6 | 0.8 | 0.8 | 0.6 | 0.6 | 0.3 | 0.6 | 0.8 | 0.8 | 0.6 | 0.6 | 0.8 |  | 0.7 | 0.8 | 0.6 | 0.8 | 0.8 | 0.6 | 0.4 | 0.6 | 0.8 | 0.8 | 0.7 | 20 | #REF!
32 | 74d | 600 mm dia pipeNP3 | Rmt | #REF! | 2 | 1.5 | 1.5 | 2 | 2 | 0.75 | 1.5 | 1.5 | 2 | 2 | 1.5 | 1.5 | 0.75 | 1.5 | 2 | 2 | 1.5 | 1.5 | 2 |  | 1.25 | 2 | 1.5 | 2 | 2 | 1.5 | 1.5 | 1.5 | 2 | 2 | 1.75 | 50 | #REF!
33 | 74e | 900 mm dia pipeNP3 | Rmt | #REF! | 1 | 1.4 | 1.2 | 1 | 1 | 0.4 | 1 | 0.8 | 1.2 | 1.2 | 1 | 1 | 0.4 | 0.8 | 0.8 | 1 | 1 | 1.2 | 0.4 |  | 1 | 1 | 0.8 | 1.2 | 1.2 | 1.4 | 0.4 | 1.4 | 1.2 | 1.2 | 1.4 | 30 | #REF!
34 | 78 | S/F earthing mat | MT | #REF! | 0.25 | 0.5 | 0.25 | 0.3 | 0.4 |  | 0.25 | 0.25 | 0.4 | 0.4 | 0.2 | 0.25 |  | 0.2 | 0.25 | 0.25 | 0.2 | 0.2 | 0.25 |  | 0.25 | 0.3 | 0.4 | 0.5 | 0.3 | 0.3 |  | 0.25 | 0.2 | 0.4 | 0.3 | 8 | #REF!
ESP / MPH AREA [NARENDRA KUMAR E05460 WITH TALIM HUSSAIN] | [35 empty] | 0 | 0
1 | 1a | In soil (All types) | Cum | 8044 | 8 | 6 | 6 | 8 | 8 | 3 | 6 | 6 | 8 | 8 | 6 | 6 | 3 | 6 | 8 | 8 | 6 | 6 | 8 |  | 8 | 8 | 6 | 8 | 8 | 6 | 4 | 6 | 8 | 7 | 7 | 200 | 7844
2 | 1c | Extra over item no. 1(a) as applicable for compacting the backfilled soil for achieving 90% density at optimum moisture content | Cum | #REF! | 20 | 18 | 18 | 20 | 22 | 8 | 16 | 16 | 18 | 18 | 16 | 16 | 8 | 18 | 18 | 22 | 22 | 18 | 18 |  | 18 | 24 | 22 | 22 | 20 | 24 | 8 | 22 | 22 | 20 | 18 | 550 | #REF!
3 | 2a | In soil (all types) | Cum | #REF! | 32 | 24 | 24 | 32 | 32 | 12 | 24 | 24 | 32 | 32 | 24 | 24 | 12 | 24 | 32 | 32 | 24 | 24 | 32 |  | 32 | 32 | 24 | 32 | 32 | 24 | 16 | 24 | 32 | 28 | 28 | 800 | #REF!
4 | 6a | 63 mm to 45 mm graded hard stone agg. | Cum | #REF! | [5 empty] | 4 | 1.5 | 3 | 4 | 4 | 3 | 3.5 | 3 | 2.5 | 4 | 4 | 3 | 3 | 3.5 |  | 2 | 4 | 3.5 | 4 | 4 | 3 | 3 | 3 | 4 | 3.5 |  | 80 | #REF!
6 | 8(a) | For all works below ground level | Cum | 1729 | 16 | 12 | 12 | 16 | 16 | 6 | 12 | 12 | 16 | 16 | 12 | 12 | 6 | 12 | 16 | 16 | 12 | 12 | 16 |  | 16 | 16 | 12 | 16 | 16 | 12 | 8 | 12 | 16 | 14 | 14 | 400 | 1329
7 | 8(b) | For all works above ground lvl.(except top deck) | Cum | 570 | 10 | 14 | 12 | 10 | 10 | 4 | 10 | 8 | 12 | 12 | 10 | 10 | 4 | 8 | 8 | 10 | 10 | 12 | 4 |  | 10 | 10 | 8 | 12 | 12 | 14 | 4 | 14 | 12 | 12 | 14 | 300 | 270
7 | 11(a) | For works below ground level | MT | 155 | 1.6 | 1.2 | 1.2 | 1.6 | 1.6 | 0.6 | 1.2 | 1.2 | 1.6 | 1.6 | 1.2 | 1.2 | 0.6 | 1.2 | 1.6 | 1.6 | 1.2 | 1.2 | 1.6 |  | 1.4 | 1.6 | 1.2 | 1.6 | 1.6 | 1.2 | 0.8 | 1.2 | 1.6 | 1.6 | 1.4 | 40 | 115
9 | 12(a) | For works below ground level | Sqm | 150 | 8 | 6 | 6 | 8 | 8 | 3 | 6 | 6 | 8 | 8 | 6 | 6 | 3 | 6 | 8 | 8 | 6 | 6 | 8 |  | 8 | 8 | 6 | 8 | 8 | 6 | 4 | 6 | 8 | 7 | 7 | 200 | -50
10 | 12(b) | For works above ground level | Sqm | 3442 | 8 | 6 | 6 | 8 | 8 | 3 | 6 | 6 | 8 | 8 | 6 | 6 | 3 | 6 | 8 | 8 | 6 | 6 | 8 |  | 8 | 8 | 6 | 8 | 8 | 6 | 4 | 6 | 8 | 7 | 7 | 200 | 3242
BOILER TG AREA [VIJAYPAL SINGH E01065 WITH DINA NATH] | [35 empty] | 0 | 0
1 | 1(a) | In soil (All types) | Cum | #REF! | 20 | 14 | 16 | 16 | 18 | 6 | 16 | 16 | 18 | 18 | 14 | 14 | 6 | 16 | 20 | 20 | 16 | 16 | 18 |  | 18 | 20 | 18 | 20 | 20 | 18 | 6 | 22 | 22 | 20 | 18 | 500 | #REF!
2 | 1c | Extra over item no. 1(a) as applicable for compacting the backfilled soil for achieving 90% density at optimum moisture content | Cum | #REF! | 32 | 24 | 24 | 32 | 32 | 12 | 24 | 24 | 32 | 32 | 24 | 24 | 12 | 24 | 32 | 32 | 24 | 24 | 32 |  | 32 | 32 | 24 | 32 | 32 | 24 | 16 | 24 | 32 | 28 | 28 | 800 | #REF!
3 | 2a | In soil (All types) | Cum | 1400 | 40 | 30 | 35 | 40 | 40 | 15 | 30 | 30 | 40 | 40 | 30 | 40 | 15 | 30 | 40 | 40 | 30 | 30 | 40 |  | 30 | 40 | 30 | 40 | 40 | 30 | 15 | 30 | 40 | 40 | 30 | 1000 | 400
4 | 6a | 63 mm to 45 mm graded hard stone agg. | Cum | 1280 | 16 | 12 | 12 | 16 | 16 | 6 | 12 | 12 | 16 | 16 | 12 | 12 | 6 | 12 | 16 | 16 | 12 | 12 | 16 |  | 16 | 16 | 12 | 16 | 16 | 12 | 8 | 12 | 16 | 14 | 14 | 400 | 880
5 | 7(a) | M 7.5 (with graded agg. of nominal size 40 mm) nominal mix | Cum | 218 | 4 | 5 | 5 | 4 | 5 | 2 | 5 | 4 | 4 | 5 | 4 | 5 | 2 | 4 | 4 | 5 | 4 | 6 | 5 |  | 4 | 5 | 5 | 4 | 5 | 4 | 2 | 4 | 4.5 | 5.5 | 5 | 130 | 88
6 | 8(a) | For all works below ground level | Cum | 280 | 32 | 24 | 24 | 32 | 32 | 12 | 24 | 24 | 32 | 32 | 24 | 24 | 12 | 24 | 32 | 32 | 24 | 24 | 32 |  | 32 | 32 | 24 | 32 | 32 | 24 | 16 | 24 | 32 | 28 | 28 | 800 | -520
7 | 8(b) | For all works above ground lvl.(except top deck) | Cum | 1500 | 8 | 6 | 6 | 8 | 8 | 3 | 6 | 6 | 8 | 8 | 6 | 6 | 3 | 6 | 8 | 8 | 6 | 6 | 8 |  | 8 | 8 | 6 | 8 | 8 | 6 | 4 | 6 | 8 | 7 | 7 | 200 | 1300
8 | 8ci | M 35 for deck of MDBFP & TDBFP,ID,PA AND FD Fans Supported on vibration isolation system | Cum | #REF! | 16 | 12 | 12 | 16 | 16 | 6 | 12 | 12 | 16 | 16 | 12 | 12 | 6 | 12 | 16 | 16 | 12 | 12 | 16 |  | 16 | 16 | 12 | 16 | 16 | 12 | 8 | 12 | 16 | 14 | 14 | 400 | #REF!
9 | 8ciii | M 30 for block type machine fdn like coal mill | Cum | #REF! | [5 empty] | 0.75 |  | 0.5 | 1 | 0.75 | 1 | 0.5 | 2 |  | 0.5 | 1 | 0.75 | 0.5 | 0.5 |  | 0.25 | 1 | 0.5 | 1.5 | 1 | 1.5 | 1 | 0.5 | 1.5 | 1.5 |  | 20 | #REF!
10 | 11(a) | For works below ground level | MT | 15 | [5 empty] | 0.75 |  | 0.5 | 1 | 0.75 | 1 | 0.5 | 2 |  | 0.5 | 1 | 0.75 | 0.5 | 0.5 |  | 0.25 | 1 | 0.5 | 1.5 | 1 | 1.5 | 1 | 0.5 | 1.5 | 1.5 |  | 20 | -5
11 | 11(b)(ii) | High Strength deformed TMT bars | MT | 101 | 0.4 | 0.3 | 0.3 | 0.4 | 0.4 | 0.15 | 0.3 | 0.3 | 0.4 | 0.4 | 0.3 | 0.3 | 0.15 | 0.3 | 0.4 | 0.4 | 0.3 | 0.3 | 0.4 |  | 0.35 | 0.4 | 0.3 | 0.4 | 0.4 | 0.3 | 0.2 | 0.3 | 0.4 | 0.4 | 0.35 | 10 | 91
12 | 12(a) | For works below ground level | Sqm | 1200 | 10 | 14 | 12 | 10 | 10 | 4 | 10 | 8 | 12 | 12 | 10 | 10 | 4 | 8 | 8 | 10 | 10 | 12 | 4 |  | 10 | 10 | 8 | 12 | 12 | 14 | 4 | 14 | 12 | 12 | 14 | 300 | 900
13 | 12(b) | For works above ground level | Sqm | 3600 | 40 | 30 | 35 | 40 | 40 | 15 | 30 | 30 | 40 | 40 | 30 | 40 | 15 | 30 | 40 | 40 | 30 | 30 | 40 |  | 30 | 40 | 30 | 40 | 40 | 30 | 15 | 30 | 40 | 40 | 30 | 1000 | 2600
14 | 13b | For TDBFP & MDBFP deck | Sqm | #REF! | 4 | 5 | 5 | 4 | 5 | 2 | 5 | 4 | 4 | 5 | 4 | 5 | 2 | 4 | 4 | 5 | 4 | 6 | 5 |  | 4 | 5 | 5 | 4 | 5 | 4 | 2 | 4 | 4.5 | 5.5 | 5 | 130 | #REF!
15 | 20a | PVC water stop 225 x6mm | Rmt | 20 | 2 | 2.8 | 2.4 | 2 | 2 | 0.8 | 2 | 1.6 | 2.4 | 2.4 | 2 | 2 | 0.8 | 1.6 | 1.6 | 2 | 2 | 2.4 | 0.8 |  | 2 | 2 | 1.6 | 2.4 | 2.4 | 2.8 | 0.8 | 2.8 | 2.4 | 2.4 | 2.8 | 60 | -40
16 | I.25a | MS Foundation bolt | #REF! | [32 empty] | 0 | 0
|  | Fabrication 65% | MT | #REF! | [8 empty] | 0.1 |  |  | 0.1 |  |  |  | 0.1 |  | 0.25 |  |  |  |  | 0.1 |  | 0.1 | 0.25 |  |  | 0.2 | 0.1 |  | 1.3 | #REF!
|  | Erection 10% | MT | #REF! | [8 empty] | 0.1 |  |  | 0.1 |  |  |  | 0.1 |  | 0.25 |  |  |  |  | 0.1 |  | 0.1 | 0.25 |  |  | 0.2 | 0.1 |  | 1.3 | #REF!
|  | Alignment10% | MT | #REF! | [8 empty] | 0.1 |  |  | 0.1 |  |  |  | 0.1 |  | 0.25 |  |  |  |  | 0.1 |  | 0.1 | 0.25 |  |  | 0.2 | 0.1 |  | 1.3 | #REF!
|  | Handed Over 10% | MT | #REF! | [8 empty] | 0.1 |  |  | 0.1 |  |  |  | 0.1 |  | 0.25 |  |  |  |  | 0.1 |  | 0.1 | 0.25 |  |  | 0.2 | 0.1 |  | 1.3 | #REF!
|  | Material reconcilation 5% | MT | #REF! | [8 empty] | 0.1 |  |  | 0.1 |  |  |  | 0.1 |  | 0.25 |  |  |  |  | 0.1 |  | 0.1 | 0.25 |  |  | 0.2 | 0.1 |  | 1.3 | #REF!
17 | J.36ai | Burnt Clay Brick work in 1:6 | Cum | 280 | 4 | 3 | 3 | 4 | 4 | 1.5 | 3 | 3 | 4 | 4 | 3 | 3 | 1.5 | 3 | 4 | 4 | 3 | 3 | 4 |  | 4 | 4 | 3 | 4 | 4 | 3 | 2 | 3.5 | 4 | 3.5 | 3 | 100 | 180
18 | 49ai | mineral wool insulation 50 mm th with framed strips | Cum | #REF! | 10 | 14 | 12 | 10 | 10 | 4 | 10 | 8 | 12 | 12 | 10 | 10 | 4 | 8 | 8 | 10 | 10 | 12 | 4 |  | 10 | 10 | 8 | 12 | 12 | 14 | 4 | 14 | 12 | 12 | 14 | 300 | #REF!
19 | 51b | Matalic hardner topping | Sqm | 3000 | 20 | 14 | 16 | 16 | 18 | 6 | 16 | 16 | 18 | 18 | 14 | 14 | 6 | 16 | 20 | 20 | 16 | 16 | 18 |  | 18 | 20 | 18 | 20 | 20 | 18 | 6 | 22 | 22 | 20 | 18 | 500 | 2500
20 | 58 | aluminium work for door, windows, ventilators etc. | Kg | #REF! | 20 | 14 | 16 | 16 | 18 | 6 | 16 | 16 | 18 | 18 | 14 | 14 | 6 | 16 | 20 | 20 | 16 | 16 | 18 |  | 18 | 20 | 18 | 20 | 20 | 18 | 6 | 22 | 22 | 20 | 18 | 500 | #REF!
21 | 60aii | Rolling shutter gear oprated | Sqm | #REF! | 0.8 | 0.6 | 0.6 | 0.8 | 0.8 | 0.3 | 0.6 | 0.6 | 0.8 | 0.8 | 0.6 | 0.6 | 0.3 | 0.6 | 0.8 | 0.8 | 0.6 | 0.6 | 0.8 |  | 0.7 | 0.8 | 0.6 | 0.8 | 0.8 | 0.6 | 0.4 | 0.6 | 0.8 | 0.8 | 0.7 | 20 | #REF!
22 | 66a | PVC Coated Chain link fencing | Sqm | 360 | 4 | 5 | 6 | 4 | 6 | 1 | 6 | 3 | 4 | 4 | 3 | 3 | 1 | 3 | 4 | 4 | 3 | 3 | 5 |  | 2 | 4 | 3 | 4 | 4 | 2 | 1 | 4 | 5 | 4 | 5 | 110 | 250
MPH AREA [ASHOK KUMAR E08476 WITH SANJEET KUMAR E03937] | [35 empty] | 0 | 0
1 | 1a | In soil (All types) | Cum | #REF! | 20 | 14 | 16 | 16 | 18 | 6 | 16 | 16 | 18 | 18 | 14 | 14 | 6 | 16 | 20 | 20 | 16 | 16 | 18 |  | 18 | 20 | 18 | 20 | 20 | 18 | 6 | 22 | 22 | 20 | 18 | 500 | #REF!
2 | 2a | Excavation incl. Stacking of excavated material (rock/soil) up to a total lead of 5.0 kms | Cum | 400 | 60 | 64 | 54 | 58 | 62 | 28 | 64 | 58 | 58 | 60 | 62 | 62 | 28 | 60 | 60 | 62 | 58 | 58 | 64 |  | 62 | 56 | 58 | 56 | 62 | 64 | 28 | 58 | 60 | 60 | 56 | 1700 | -1300
3 | 6a | 63 mm to 45 mm graded hard stone agg. | Cum | 500 | 20 | 18 | 18 | 20 | 22 | 8 | 16 | 16 | 18 | 18 | 16 | 16 | 8 | 18 | 18 | 22 | 22 | 18 | 18 |  | 18 | 24 | 22 | 22 | 20 | 24 | 8 | 22 | 22 | 20 | 18 | 550 | -50
4 | 7a | M 7.5 (with graded agg. of nominal size 40 mm) nominal mix | Cum | 150 | 4 | 3 | 3 | 4 | 4 | 1.5 | 3 | 3 | 4 | 4 | 3 | 3 | 1.5 | 3 | 4 | 4 | 3 | 3 | 4 |  | 4 | 4 | 3 | 4 | 4 | 3 | 2 | 3.5 | 4 | 3.5 | 3 | 100 | 50
5 | 8(a) | For all works below ground level | Cum | 90 | 10 | 14 | 12 | 10 | 10 | 4 | 10 | 8 | 12 | 12 | 10 | 10 | 4 | 8 | 8 | 10 | 10 | 12 | 4 |  | 10 | 10 | 8 | 12 | 12 | 14 | 4 | 14 | 12 | 12 | 14 | 300 | -210
6 | 8(a) | For all works above ground lvl.(except top deck) | Cum | 500 | 10 | 7 | 8 | 8 | 9 | 3 | 8 | 8 | 9 | 9 | 7 | 7 | 6 | 8 | 10 | 10 | 8 | 8 | 9 |  | 9 | 10 | 9 | 10 | 10 | 9 | 3 | 8 | 11 | 10 | 9 | 250 | 250
7 | 8ci | M 35 for deck of MDBFP & TDBFP,ID,PA AND FD Fans Supported on vibration isolation system | Cum | #REF! | 4 | 5 | 5 | 4 | 5 | 2 | 5 | 4 | 4 | 5 | 4 | 5 | 2 | 4 | 4 | 5 | 4 | 6 | 5 |  | 4 | 5 | 5 | 4 | 5 | 4 | 2 | 4 | 4.5 | 5.5 | 5 | 130 | #REF!
8 | B9 | Providing & mixing as cement concrete admixtures - super plasticizers | Per bag (50 kg) of cement | #REF! | [7 empty] | 1 |  | 0.5 |  | 0.5 |  |  |  | 0.5 |  | 1 |  |  |  | 0.5 |  | 0.5 |  | 1 | 0.5 |  | 0.5 | 0.5 |  | 7 | #REF!
9 | 11(a) | For works below ground level | MT | 6 | 2 | 2.8 | 2.4 | 2 | 2 | 0.8 | 2 | 1.6 | 2.4 | 2.4 | 2 | 2 | 0.8 | 1.6 | 1.6 | 2 | 2 | 2.4 | 0.8 |  | 2 | 2 | 1.6 | 2.4 | 2.4 | 2.8 | 0.8 | 2.8 | 2.4 | 2.4 | 2.8 | 60 | -54
10 | 11(b)(ii) | High Strength deformed TMT bars | MT | 70 | 1.6 | 1.2 | 1.2 | 1.6 | 1.6 | 0.6 | 1.2 | 1.2 | 1.6 | 1.6 | 1.2 | 1.2 | 0.6 | 1.2 | 1.6 | 1.6 | 1.2 | 1.2 | 1.6 |  | 1.4 | 1.6 | 1.2 | 1.6 | 1.6 | 1.2 | 0.8 | 1.2 | 1.6 | 1.6 | 1.4 | 40 | 30
11 | 12(a) | For works below ground level | Sqm | 150 | 8 | 6 | 6 | 8 | 8 | 3 | 6 | 6 | 8 | 8 | 6 | 6 | 3 | 6 | 8 | 8 | 6 | 6 | 8 |  | 8 | 8 | 6 | 8 | 8 | 6 | 4 | 6 | 8 | 7 | 7 | 200 | -50
12 | 12(b) | For works above ground level | Sqm | 250 | 54 | 54 | 52 | 56 | 56 | 16 | 58 | 58 | 54 | 54 | 48 | 48 | 16 | 50 | 50 | 52 | 52 | 48 | 48 |  | 46 | 46 | 48 | 48 | 46 | 46 | 16 | 48 | 48 | 42 | 42 | 1400 | -1150
13 | 15(a) | MS pipes of all diameters | Qtl | #REF! | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 2 | #REF!
14 | 18a | Cement sand grout | cu.dm | #REF! | 40 | 30 | 35 | 40 | 40 | 15 | 30 | 30 | 40 | 40 | 30 | 40 | 15 | 30 | 40 | 40 | 30 | 30 | 40 |  | 30 | 40 | 30 | 40 | 40 | 30 | 15 | 30 | 40 | 40 | 30 | 1000 | #REF!
15 | 24 | P/L Pre cast CCM-25 at all floor level | cum | #REF! | 10 | 7 | 8 | 8 | 9 | 3 | 8 | 8 | 9 | 9 | 7 | 7 | 6 | 8 | 10 | 10 | 8 | 8 | 9 |  | 9 | 10 | 9 | 10 | 10 | 9 | 3 | 8 | 11 | 10 | 9 | 250 | #REF!
16 | I.25a | MS Foundation bolt | #REF! | [32 empty] | 0 | 0
|  | Fabrication 65% | MT | #REF! | [8 empty] | 0.1 |  |  | 0.1 |  |  |  | 0.1 |  | 0.25 |  |  |  |  | 0.1 |  | 0.1 | 0.25 |  |  | 0.2 | 0.1 |  | 1.3 | #REF!
|  | Erection 10% | MT | #REF! | [8 empty] | 0.1 |  |  | 0.1 |  |  |  | 0.1 |  | 0.25 |  |  |  |  | 0.1 |  | 0.1 | 0.25 |  |  | 0.2 | 0.1 |  | 1.3 | #REF!
|  | Alignment10% | MT | #REF! | [8 empty] | 0.1 |  |  | 0.1 |  |  |  | 0.1 |  | 0.25 |  |  |  |  | 0.1 |  | 0.1 | 0.25 |  |  | 0.2 | 0.1 |  | 1.3 | #REF!
|  | Handed Over 10% | MT | #REF! | [8 empty] | 0.1 |  |  | 0.1 |  |  |  | 0.1 |  | 0.25 |  |  |  |  | 0.1 |  | 0.1 | 0.25 |  |  | 0.2 | 0.1 |  | 1.3 | #REF!
|  | Material reconcilation 5% | MT | #REF! | [8 empty] | 0.1 |  |  | 0.1 |  |  |  | 0.1 |  | 0.25 |  |  |  |  | 0.1 |  | 0.1 | 0.25 |  |  | 0.2 | 0.1 |  | 1.3 | #REF!
17 | J.36ai | Burnt Clay Brick work in 1:6 | cum | 250 | 4 | 3 | 3 | 4 | 4 | 1.5 | 3 | 3 | 4 | 4 | 3 | 3 | 1.5 | 3 | 4 | 4 | 3 | 3 | 4 |  | 4 | 4 | 3 | 4 | 4 | 3 | 2 | 3.5 | 4 | 3.5 | 3 | 100 | 150
18 | 38a | 18mm CM 1:4 (Cement : fine sand) | Sqm | 400 | 20 | 14 | 16 | 16 | 18 | 6 | 16 | 16 | 18 | 18 | 14 | 14 | 6 | 16 | 20 | 20 | 16 | 16 | 18 |  | 18 | 20 | 18 | 20 | 20 | 18 | 6 | 22 | 22 | 20 | 18 | 500 | -100
19 | 38b | 12mm thick Cement Plaster in fine sand | Sqm | 600 | 16 | 12 | 12 | 16 | 16 | 6 | 12 | 12 | 16 | 16 | 12 | 12 | 6 | 12 | 16 | 16 | 12 | 12 | 16 |  | 16 | 16 | 12 | 16 | 16 | 12 | 8 | 12 | 16 | 14 | 14 | 400 | 200
20 | 38d | 6mm thick plaster on ceiling | Sqm | #REF! | 16 | 12 | 12 | 16 | 16 | 6 | 12 | 12 | 16 | 16 | 12 | 12 | 6 | 12 | 16 | 16 | 12 | 12 | 16 |  | 16 | 16 | 12 | 16 | 16 | 12 | 8 | 12 | 16 | 14 | 14 | 400 | #REF!
21 | 51b | Matalic hardner topping | Sqm | 450 | 40 | 30 | 35 | 40 | 40 | 15 | 30 | 30 | 40 | 40 | 30 | 40 | 15 | 30 | 40 | 40 | 30 | 30 | 40 |  | 30 | 40 | 30 | 40 | 40 | 30 | 15 | 30 | 40 | 40 | 30 | 1000 | -550
22 | 51d | Precast concrete pavers | Sqm | #REF! | 8 | 6 | 6 | 8 | 8 | 3 | 6 | 6 | 8 | 8 | 6 | 6 | 3 | 6 | 8 | 8 | 6 | 6 | 8 |  | 8 | 8 | 6 | 8 | 8 | 6 | 4 | 6 | 8 | 7 | 7 | 200 | #REF!
23 | 56 | Hollow metal double sheet shutter | Sqm | 6 | 0.4 | 0.3 | 0.3 | 0.4 | 0.4 | 0.15 | 0.3 | 0.3 | 0.4 | 0.4 | 0.3 | 0.3 | 0.15 | 0.3 | 0.4 | 0.4 | 0.3 | 0.3 | 0.4 |  | 0.35 | 0.4 | 0.3 | 0.4 | 0.4 | 0.3 | 0.2 | 0.3 | 0.4 | 0.4 | 0.35 | 10 | -4
24 | 58 | aluminium work for door, windows, ventilators etc. | Kg | 250 | 8 | 6 | 6 | 8 | 8 | 3 | 6 | 6 | 8 | 8 | 6 | 6 | 3 | 6 | 8 | 8 | 6 | 6 | 8 |  | 8 | 8 | 6 | 8 | 8 | 6 | 4 | 6 | 8 | 7 | 7 | 200 | 50
25 | 62a | 4mm thick glass | Sqm | #REF! | 0.8 | 0.6 | 0.6 | 0.8 | 0.8 | 0.3 | 0.6 | 0.6 | 0.8 | 0.8 | 0.6 | 0.6 | 0.3 | 0.6 | 0.8 | 0.8 | 0.6 | 0.6 | 0.8 |  | 0.7 | 0.8 | 0.6 | 0.8 | 0.8 | 0.6 | 0.4 | 0.6 | 0.8 | 0.8 | 0.7 | 20 | #REF!
26 | 62e | 6.00mm thick float glass | Sqm | #REF! | 1.6 | 1.2 | 1.2 | 1.6 | 1.6 | 0.6 | 1.2 | 1.2 | 1.6 | 1.6 | 1.2 | 1.2 | 0.6 | 1.2 | 1.6 | 1.6 | 1.2 | 1.2 | 1.6 |  | 1.4 | 1.6 | 1.2 | 1.6 | 1.6 | 1.2 | 0.8 | 1.2 | 1.6 | 1.6 | 1.4 | 40 | #REF!
27 | 70c | water cooler of 30 litre capacity | Nos | #REF! | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 0.1 | 0.1 | 0.1 |  | 2 | #REF!
28 | 74b | 300 mm dia pipeNP3 | MT | #REF! | [7 empty] | 0.1 |  |  | 0.1 |  | 0.1 |  | 0.15 |  | 0.15 | [6 empty] | 0.1 |  | 0.1 | [5 empty] | 0.8 | #REF!
29 | 74d | 600 mm dia pipeNP3 | MT | #REF! | 1.6 | 1.2 | 1.2 | 1.6 | 1.6 | 0.6 | 1.2 | 1.2 | 1.6 | 1.6 | 1.2 | 1.2 | 0.6 | 1.2 | 1.6 | 1.6 | 1.2 | 1.2 | 1.6 |  | 1.4 | 1.6 | 1.2 | 1.6 | 1.6 | 1.2 | 0.8 | 1.2 | 1.6 | 1.6 | 1.4 | 40 | #REF!

## DLR
ERA INFRA ENGINEERING LIMITED
(CONSTRUCTION & CONTRACTS DIVISION)
Daily Loss Report of Labour for the Month of - DEC-2014
PROJECT : DDA Kalkaji (2005)
[6 empty] | SUBMITTED BY PROJECT | [5 empty] | VERIFIED & CERTIFIED AT HEAD OFFICE
Sl. No. | Description | Unit | Rate | Budgeted as per Monthly Budget |  | As per Monthly Budget for Today |  | Actual for Today |  | Balance budget |  | Actual for Today |  | Cumulative As per Actual (Upto Previous Day) |  | Cumulative As per Actual (Upto Date) |  | Justification % as on today | Justification % Cummulative | Material Coeff.
|  |  |  | Qty | Amount (in Rs.) | Qty | Amount (in Rs.) | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount
A | Fixed Muster Roll (w/o O.T) | [18 empty] | Cement | Agg | Coarse sand | Fine sand | Modular brick | Fps Brick | Steel 6mm | Steel 8mm | Steel 10mm | Steel 12mm | 40x40x5
| Total A (Annexure-I) |  |  | 0 | 0
B | Muster Roll (with O.T) (Non-Productive)
| Total B (Annexure-II) |  |  |  | 0
C | Productive Labour
a. | Muster Roll (P.C not working on Item Rate)
#REF! | #REF! | #REF! | #REF!
1 | Zerat Ali (MALDA) | #REF! | #REF! |  | #REF!
#REF! | LABOUR | Nos. | 280.5 |  | 0
#REF! | MASON | Nos. | 445.5 |  | 0
#REF! | #REF! | #REF! | #REF!
2 | MALDA ENTERPRISES (MALDA) | #REF! | #REF!
#REF! | F COOLIE | Nos. | 200 |  | 0
#REF! | MASON | Nos. | 300
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
6 | Dilip Kuamr Mehato | #REF! | #REF! |  | #REF!
#REF! | C HELPER | Nos. | 170
#REF! | CARPENTER | Nos. | 270
#REF! | LABOUR | Nos. | 255 |  | 0
#REF! | MASON | Nos. | 405
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
12 | Sky Enterprises | #REF! | #REF!
#REF! | B HELPER | Nos. | 190
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
b. | Muster Roll (P.C working on Item Rate)
13 | Saroj Kumar | #REF! | #REF!
#REF! | B HELPER | Nos. | 170 |  | 0
#REF! | BARBINDER | Nos. | 270 |  | 0
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
14 | M. P. Gupta | #REF! | #REF!
#REF! | LABOUR | Nos. | 170
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
0
| Total C (a+b) (Annexure-III) |  |  | 14820 | 3742860
D | Debitable Labour to P/C
1 | Muster Roll
| Un Skilled | Nos. | 130 |  | 0
| Skilled | Nos. | 160 |  | 0
2 | P/C |  |  |  | 0
| Un Skilled | Nos. | 130 |  | 0
| Skilled | Nos. | 160 |  | 0
| Total of D |  |  |  | 0
E | Net Supply for Productive Work | C-D |  | 14820 | 3742860
F | Productive Work
1 | RCC in foundation | Cum | 200
2 | Earth Filling | Cum | 25
3 | Excavation | Cum | 42
4 | Brick Work | Cum | 300
5 | Chipping Work | Cum | 150
6 | Shifting of Material | MT | 100
7 | PCC | Cum | 175
8 | Metal Soiling | Cum | 75
9 | Plaster | Sqm. | 30
10 | Shuttering. | Sqm. | 65
11 | Sand Filling | Cum | 50
| Total F |  |  | 0 | 0
| %age Achievement of Labour on supply basis | [7 empty] | #DIV/0! |  |  |  | #DIV/0! |  | #DIV/0!
| %age Achievement of Machinery on supply basis | [7 empty] | #REF! |  |  |  | #REF! |  | #REF!
Note:- | Separate Measurement Sheet to be attached for justification.
Project In-Charge

## Muster Roll A
ANNEXURE-I
MUSTER ROLL-A | [24 empty] | 0 | 0
Budget- OCT- 2014 | [6 empty] | SUBMITTED | [9 empty] | VERIFIED & CERTIFIED AT HEAD OFFICE
Sl. No. | Description | Designation | Unit | Rate (per day) | Budgeted as per Monthly Budget |  | Budgeted as per Monthly Budget for Today |  | Revised Target for Today |  | Achievement for Today |  | Revised target for Next day |  | Balance budget |  | Achievement for Today |  | Revised target for Next day |  | Cumulative Achievement Previous Day |  | Cumulative Achievement Upto Date |  | Justification % as on today | Justification % Cummulative
[5 empty] | Qty (day) | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.)
A1 | Temporary Staff - B
ET6937 | RAJESH KUMAR | TRANSIT OPERATOR | Nos | 370.9677 | 31 | 11500
ET7242 | BIPIN KUMAR | SAFETY SUPERVISOR | Nos | 290.3226 | 31 | 9000
| MANOJ | COOK | Nos | 300 | 31 | 9300
| HARI | COOK HELPER | Nos | 262.0968 | 31 | 8125
ET7104 | AJAY | SWEEPER | Nos | 209.6774 | 31 | 6500
| OFFICE BOY | OFF. BOY | Nos | 258.0645 | 31 | 8000
| OFFICE BOY | OFF. BOY | Nos | 258.0645 | 31 | 8000
| COOK | COOK | Nos | 300 | 31 | 9300
| HELPER | HELPER | Nos | 262.0968 | 31 | 8125
| Total of A1 |  |  |  |  | 77850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A2 | Muster Roll (w/o O.T)
1 | [5 empty] | 0
2 | [5 empty] | 0
| Total of A2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Muster Roll B
ANNEXURE-II
MUSTUR ROLL-B
Budget- OCT- 2014 | [24 empty] | 0 | 0
[9 empty] | SUBMITTED | [7 empty] | VERIFIED & CERTIFIED AT HEAD OFFICE
Sl. No. | Description | Designation | Unit | Rate | Budgeted as per Monthly Budget |  | Budgeted as per Monthly Budget for Today |  | Revised Target for Today |  | Achievement for Today |  | Revised target for Next day |  | Balance budget |  | Achievement for Today |  | Revised target for Next day |  | Cumulative Achievement Previous Day |  | Cumulative Achievement Upto Date |  | Justification % as on today | Justification % Cummulative
[5 empty] | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.)
B | Muster Roll (with O.T) (Non-Productive)
1 | Mason | MASON | Nos |  |  | 0
2 | Curing labour | Helper | Nos |  |  | 0
3 | Helper | MASON HELPER | Nos |  |  | 0
4 | ADD FOR OVER TIME @ 25% | MASSON | Nos | 0 |  | 0
| Total B |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S. No. | Labour engaged |  | Unit | Rate | Qty | Amount
| Total |  |  |  | 0 | 0

## Muster Roll C
ANNEXURE-III
MUSTER ROLL-C
[18 empty] | 0 | 0
|  |  |  | SUBMITTED BY PROJECT | [7 empty] | VERIFIED & CERTIFIED AT HEAD OFFICE
Sl. No. | Description | Unit | Rate | Budgeted as per Monthly Budget |  | As per Monthly Budget for Today |  | Actual for Today |  | Balance budget |  | Actual for Today |  | Cumulative As per Actual (Upto Previous Day) |  | Cumulative As per Actual (Upto Date) |  | Justification % as on today | Justification % Cummulative
|  |  |  | Qty | Amt. (in Rs.) | Qty | Amt. (in Rs.) | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount
C | Productive Labour
a. | Muster Roll (P.C not working on Item Rate) | [19 empty] | Mason | Labour
MALDA LABOUR
1 | Lalu Ram (R/f Steel) | [19 empty] | 0 | 0
| Helper | Nos. | 200 | 450 | 90000 | 15 | [14 empty] | 0 | 0
| BARBINDER | Nos. | 280 | 150 | 42000 | 5 | [14 empty] | 0 | 0
[21 empty] | 0 | 0 |  |  | 900
2 | Neelam Devi (Malda) | [19 empty] | 0 | 0
| UNSKILLED | Nos. | 200 | 390 | 78000 | 13 | [14 empty] | 0 | 0
| MASON | Nos. | 280 | 120 | 33600 | 4 | [14 empty] | 0 | 0
[21 empty] | 0 | 0
3 | Others (New)
| UNSKILLED | Nos. | 200 | 600 | 120000 | 20
| MASON | Nos. | 280 | 150 | 42000 | 5
3 | malda
| UNSKILLED | Nos. | 200 | 450 | 90000 | 15
| MASON | Nos. | 280 | 150 | 42000 | 5
3 | bajrangi
| UNSKILLED | Nos. | 200 | 180 | 36000 | 6
| MASON | Nos. | 280 | 60 | 16800 | 2
3 | ramesh singh
| UNSKILLED | Nos. | 200 | 180 | 36000 | 6
| MASON | Nos. | 280 | 60 | 16800 | 2
GOVIND SINGH
| UNSKILLED | Nos. | 200 | 120 | 24000 | 4
| MASON | Nos. | 280 | 30 | 8400 | 1
b. | Muster Roll (P.C working on Item Rate)
| Total of C (a+b) |  |  | 3090 | 675600 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
[5 empty] | 0.7732% | [14 empty] | Donkey | #REF! | 0 |  | 6.756
|  |  |  | loss @10% | 0.6756 | [15 empty] | #REF! | 0 |  | 36.97%
| MASON | 19
| PAINTER | 0
| CARPENTER | 0
| BARBINDER | 5
| M COOLIE | 0
| FCOOLIE | 0
| FITTER | 0
| WELDER | 0
| CUTTER | 0
| C HELPER | 0
| F HELPER | 0
| B HELPER | 0
| P HELPER | 0
| PL HELPER | 0
| PLUMBER | 0
| HELPER | 15
| UNSKILLED | 64
| MECH. SKILLED | 0
| MECH. HELPER | 0
| SKILLED | 0
103

## AOR (hidden)
ANALYSIS OF RATE
[8 empty] | BOQ QTY |  |  |  | BUDGET QTY
SI. No. | Description | Unit | BOQ Rate | BOQ Qty. | lab Rate | New Mat Rate | party Rate. | BOQ AMOUNT | LABOUR AMOUNT | MATERIAL AMOUNT | PARTY AMOUNT | 0 | CEMENT | TOR STEEL | SAND | AGG 10 | AGG 20 | CICO PLAST | BRICKS | AGG 40-63 | BOULDER | PLY 12 MM | BATTEN | NAILS | SHUTTERING OIL | MASON | M. HELPER | CARPENTER | C. HELPER | BAR BINDER | B.HELPER | FITTER | F.HELPER | CUTTER | C.HELPER | WELDER | W.HELPER | SHEET Fixer | S.Helper | UNSKILLED | EXCAVATOR | HYWA | HYDRA | STR.STEEL | BITUMEN | FIBRE BOARD | MURRUM | CI PIPE 75 MM | CI PIPE 100 MM | CI PIPE 150 MM | RCC PIPE-NP3 150 | RCC PIPE-NP3 200 | RCC PIPE-NP3 250 | RCC PIPE-NP3 300 | RCC PIPE-NP3 500 | RCC PIPE-NP3 600 | RCC PIPE-NP3 900
SUB-HEAD - I: EARTH WORK
2.7 | Earth work in excavation by mechanical means (Hydraulic excavator) / manual means in over areas (exceeding 30cm in depth 1.5m in width or 10 sqm on plan) including disposal of excavated earth, lead upto 50 m and lift upto 1.50m, disposed earth to be levelled and neatly dressed.
2.7.1 | Ordinary rock | Cum | 197.75 | 47580.56 | 160 |  |  | 9409055.74 | 31640 | 0 | 0 | 4749.3 | [27 empty] | 0.1
[8 empty] | 0 | 0 | 0 | 0 | 0
2.25 | Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundation etc. in layers not exceeding 20 cm in depth: consolidating each deposited layer by ramming and watering, lead upto 50 m and lift upto 1.5 m | Cum | 83.8 | 21872.68 |  |  |  | 1832930.584 | 0 | 0 | 0 | 3180
[5 empty] | 15 |  |  | 0 | 0 | 0 | 0 | 0
2.26 | Extra for every additional lift of 1.5 m or part thereof in excavation /banking excavated or stacked materials. All kinds of soil. |  |  |  | 15 |  |  | 0 | 0 | 0 | 0 | 0
2.26.2 | Ordinary or hard rock. | cum | 48.3 | 31467.32 | 30 |  |  | 1519871.556 | 1449 | 0 | 0 | 2849.58
[8 empty] | 0 | 0 | 0 | 0 | 0
2.27 | Supplying and filling in plinth with Jamuna sand under floors including, watering, ramming consolidating and dressing complete. | Cum | 749.3 | 867.8 |  |  |  | 650242.54 | 0 | 0 | 0 | 0
[5 empty] | 10 |  |  | 0 | 0 | 0 | 0 | 0
NS (DSR Based 23.2) | Supplying & stacking of good earth by mechanical transport including loading, unloading and stacking all leads including filling, inlayers not exceeding 20 cm in depth consolidating each deposited layer by ramming and watering any lead. | Cum | 509.65 | 5089.51 |  |  |  | 2593868.7715 | 0 | 0 | 0 | 0
[5 empty] | 35 |  |  | 0 | 0 | 0 | 0 | 0
| SUB-HEAD - II: PCC WORK |  |  |  | 55 |  |  | 0 | 0 | 0 | 0 | 0
| Providing & laying in position cement concrete of specified grade excluding the cost of centering and shuttering - All work upto plinth level. | [6 empty] | 0 | 0 | 0 | 0 | 0
4.1.8 | 1:4:8 (1 Cement : 4 coarse sand : 8 graded stone aggregate 40 mm nominal size) | Cum | 3593.3 | 1776.05 | 35 |  |  | 6381880.465 | 125765.5 | 0 | 0 | 0
[5 empty] | 55 |  |  | 0 | 0 | 0 | 0 | 0
4.1.10 | 1:5:10 (1cement: 5 coarse sand: 10 stone aggregate 40mm nominal size) | Cum | 3357.4 | 4475.52 |  |  |  | 15026110.848 | 0 | 0 | 0 | 151.1472
[8 empty] | 0 | 0 | 0 | 0 | 0
N.S. (Based on DSR 4.17) | Making plinth protection 50mm thick of M-20 concrete over 75mm thick bed of dry brick ballast 40 mm nominal size, well rammed and consolidated and grouted with fine sand including finishing the top smooth. | Sqm | 359.85 | 885.49 | 35 | 105 |  | 318643.5765 | 12594.75 | 37784.25 | 0 | 0
| SUB-HEAD - III: RCC WORK |  |  |  | 55 | 105 |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 35 | 1409 |  | 0 | 0 | 0 | 0 | 0 |  |  | 1.05
5.9 | Centring and shuttering including strutting, propping etc. and removal of form for : |  |  |  | 110 | 1074 |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1.05
5.9.1 | Foundations, footings, bases of columns, etc. for mass concrete. | Sqm | 166.9 | 1490.8 | 75 | 1074 |  | 248814.52 | 12517.5 | 179250.6 | 0 | 256.42 | [7 empty] | 1.05
5.9.2 | Walls (any thickness) i/c attached pilasters, butteresses, plinth and string courses etc. | Sqm | 285.15 | 632.34 | 20 |  |  | 180311.751 | 5703 | 0 | 0 | 533.26
5.9.3 | Suspended floors, roofs, landings, balconies and access platform. | Sqm | 311.2 | 115479.97 | 150 | 500 |  | 35937366.664 | 46680 | 155600 | 0 | 18070.4789 | [8 empty] | 1.05
5.9.4 | Shelves (Cast-in -situ) | Sqm | 311.2 | 4324.32 |  |  |  | 1345728.384 | 0 | 0 | 0 | 0
5.9.5 | Lintels, beams, plinth beams, girders, bressumers and cantilevers. | Sqm | 262.25 | 118590.25 |  |  | 25 | 31100293.0625 | 0 | 0 | 6556.25 | 515.2
5.9.6 | Columns, Pillars, Piers, Abutments, Posts and Struts | Sqm | 365.6 | 76872.86 |  |  |  | 28104717.616 | 0 | 0 | 0 | 6375.2316
5.9.7 | Stairs, (excluding landings) except spiral stair-cases | Sqm | 326.3 | 2894.09 |  |  |  | 944341.567 | 0 | 0 | 0 | 0
5.9.16 | Edges of slabs and breaks in floors and walls. |  |  |  | 345 | 2163 |  | 0 | 0 | 0 | 0 | 0
5.9.16.1 | Under 20 cm wide | Mtr | 99.45 | 28131.33 |  |  |  | 2797660.7685 | 0 | 0 | 0 | 0
[5 empty] | 400 | 2540 |  | 0 | 0 | 0 | 0 | 0
| Providing precast cement concrete Jali 1:2:4 (1 cement : 2 coarse sand: 4 graded stone aggregate 6 mm nominal size), reinforced with 1.6 mm dia mild steel wire, including centering and shuttering, roughening cleaning, fixing and finishing in cement mortar 1:3 (1 cement: 3 fine sand) etc. complete, excluding plastering of the jambs, sills and soffits. | [6 empty] | 0 | 0 | 0 | 0 | 0
5.18.2 | 40 mm thick | Sqm | 523.8 | 2039.38 | 400 | 3234.036 |  | 1068227.244 | 209520 | 1693988.0725 | 0 | 0 | 6.4 |  | 0.44 | 0.33 | 0.53 | 1.6 | [7 empty] | 0.05 | 0.05 | [12 empty] | 0.5
[8 empty] | 0 | 0 | 0 | 0 | 0
5.22 | Steel reinforcement for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete up to plinth level. |  |  |  | 400 | 2841.3684 |  | 0 | 0 | 0 | 0 | 0 | 4.8 |  | 0.56 | 0.35 | 0.45 | 1.2 | [7 empty] | 0.05 | 0.05 | [12 empty] | 0.5
5.22.6 | Thermo-Mechanically Treated bars | Kg | 62.25 | 1135575.81 |  |  |  | 70689594.1725 | 0 | 0 | 0 | 96649
[5 empty] | 400 | 3386.7273 |  | 0 | 0 | 0 | 0 | 0 | 7 |  | 0.48 | 0.29 | 0.49 | 1.75 | [7 empty] | 0.05 | 0.05 | [12 empty] | 0.5
5.22A | Steel reinforcement for for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete above plinth level. | [6 empty] | 0 | 0 | 0 | 0 | 0
5.22A.6 | Thermo-Mechanically Treated bars | Kg | 62.25 | 4732165.5 | 580 | 3386.7273 |  | 294577302.375 | 36105 | 210823.7757 | 0 | 540786.05 | 7 |  | 0.48 | 0.29 | 0.49 | 1.75 | [7 empty] | 0.05 | 0.05 | [12 empty] | 0.5
[8 empty] | 0 | 0 | 0 | 0 | 0
NS | Providing and fixing sheet covering over expansion joints with iron screws as per design. |  |  |  | 340 | 3504.1127 |  | 0 | 0 | 0 | 0 | 0 | 7.4 |  | 0.51 | 0.32 | 0.43 | 1.85 | [7 empty] | 0.05 | 0.05 | [12 empty] | 0.5
(Based on DSR 5.29.1) | Non-absestos fibre cement board 6 mm thick as per IS : 148862 - 350 mm wide | mtr | 163.25 | 1467.6 |  |  |  | 239585.7 | 0 | 0 | 0 | 0
[5 empty] | 340 | 3596.3022 |  | 0 | 0 | 0 | 0 | 0 | 7.5 |  | 0.48 | 0.3 | 0.45 | 4.13 | [7 empty] | 0.05 | 0.05 | [12 empty] | 0.5
(Based on DSR 5.29.2) | Aluminium fluted stips 3.15 mm thick 350 mm wide | mtr | 702.7 | 108.6 |  |  |  | 76313.22 | 0 | 0 | 0 | 0
[7 empty] | 145 | 0 | 0 | 0 | 0 | 0
5.34 | Extra for providing richer mixes at all floor levels. Note:- Excess/less cement over the specified cement content used is payable /recoverable separately. |  |  |  | 10 | 150 |  | 0 | 0 | 0 | 0 | 0
5.34.1 | Providing M-30 grade concrete instead of M-25 grade BMC/RMC. (Note:- Cement content considered in M-30 is @ 340 kg/cum). | cum | 63.2 | 8615.63 |  |  |  | 544507.816 | 0 | 0 | 0 | 739.6782
[5 empty] | 580 | 3231.2715 |  | 0 | 0 | 0 | 0 | 0 | 6.4 |  | 0.7 | 0.6 | 0 | [8 empty] | 0.05 | 0.05 | [12 empty] | 0.5
5.37 | Providing & laying in position ready mixed M-25 grade concrete for reinforced cement concrete work, using cement content as per approved mix design manufactured in fully automatic batching plant and transported to site of work in transit mixer for all leads having continuous agitated mixer, manufactured as per mix design of specified grade for reinforced cement concrete work including pumping of RMC from transit mixer to site of laying, excluding the cost of centering, shuttering finishing and reinforcement including cost of admixtures in recommended proportions as per IS:9103 to accelerate/ retard setting of concrete, improve workability without impairing strength and durability as per direction of the Engineer-in-charge. Cement content is considered in this item is @ 330 kg/cum. Excess/less cement used as per design mix is payable/recoverable separately). | [6 empty] | 0 | 0 | 0 | 0 | 0
5.37.1 | All works up to plinth level | Cum | 5590.6 | 9264.44 | 225 | 3386.7273 |  | 51793778.264 | 1257885 | 18933837.7552 | 0 | 1075.105 | 7 |  | 0.48 | 0.29 | 0.49 | 1.75 | [7 empty] | 0.05 | 0.05
| All works above plinth upto floor V level | Cum | 6130 | 30792.21 |  |  |  | 188756247.3 | 0 | 0 | 0 | 2635.4741
[5 empty] | 350 |  |  | 0 | 0 | 0 | 0 | 0
5.38 | Extra for R.C.C./ B.M.C/ R.M.C. work above floor V level for each four floors or part thereof. | Cum | 151 | 44435.9 | 650 |  |  | 6709820.9 | 98150 | 0 | 0 | 0
[5 empty] | 10 | 15 |  | 0 | 0 | 0 | 0 | 0
NS (Based on DSR 5.43) | Providing and fixing in position Stainless steel Grade 304 plate-1.0 mm thick as per design for expansion joints. | mtr | 943.15 | 1619.5 | 35 |  |  | 1527431.425 | 33010.25 | 0 | 0 | 350.776
[5 empty] | 80 |  |  | 0 | 0 | 0 | 0 | #REF!
| SUB - HEAD - IV: BRICK WORK | [6 empty] | 0 | 0 | 0 | 0 | #REF!
6.1.2 | Brick work with F.P.S. bricks of class designation 75 in foundation and plinth in cement mortar 1:6 (1 cement : 6 coarse sand) | Cum | 3316.55 | 396.52 | 100 | 44 |  | 1315078.406 | 331655 | 145928.2 | 0 | #REF!
[5 empty] | 120 | 124 |  | 0 | 0 | 0 | 0 | #REF! | [9 empty] | 0.152 | 0.228 | 0.1 | 0.0328
N.S. (DSR Based) | Providing & laying Autoclaved Areatd Cement blocks masonary with 200mm thick AAC Blocks in super structure above plinth level upto floor V level in Cement mortar 1:4 (1 cement : 4 coarse sand) | Cum | 3759.21 | 31601.9 | 145 | 44 |  | 118798178.499 | 545085.45 | 165405.24 | 0 | #REF! | [12 empty] | 0.0328
[5 empty] | 145 | 124 |  | 0 | 0 | 0 | 0 | #REF! | [9 empty] | 0.152 | 0.228 | 0.12 | 0.0328
6.5 | Extra for brick work/AAC block masonary/Tile masonary in superstructure above floor V level for each four floors or part thereof by mechanical means. | Cum | 250.45 | 58141.87 | 320 | 124 |  | 14561631.3415 | 80144 | 31055.8 | 0 | #REF! | [9 empty] | 0.152 | 0.228 | 0.12 | 0.0328
[5 empty] | 7000 | 2500 |  | 0 | 0 | 0 | 0 | #REF!
6.38 | Providing & laying autoclaved aerated cement blocks masonry with 100mm thick AAC blocks in super structure above plinth level up to floor V level in cement mortar 1:4 (1 cement : 4 coarse sand) The rate includes providing and placing in position 2 Nos. 6 mm dia M.S. bars at every third course of masonry work. | Cum | 4508.3 | 7543.094 | 250 | 124 |  | 34006530.6802 | 1127075 | 559029.2 | 0 | #REF! | [9 empty] | 0.152 | 0.228 | 0.125 | 0.0328
[8 empty] | 0 | 0 | 0 | 0 | #REF!
| SUB - HEAD - V: WOOD WORK |  |  |  | 60 | 45 |  | 0 | 0 | 0 | 0 | #REF! | [9 empty] | 0.05472 | 0.08208 | 0.15 | 0.011808
(9.21 based on DSR) | Providing & fixing ISI marked flush door shutters conforming to IS:2202 (Part-I) non-decorative type, core of block board construction with frame of 1st class hard wood and well matched commercial 3 ply veneering with vertical grains or cross bands and face veneers on both faces of shutters : |  |  |  | 60 | 90 |  | 0 | 0 | 0 | 0 | #REF! | [9 empty] | 0.10944 | 0.16416 | 0.165 | 0.023616
| 40 mm thick including ISI marked Mild steel butt hinges with necessary screws. | Sqm | 1694.65 | 24343.2 | 90 | 149 |  | 41253203.88 | 152518.5 | 252502.85 | 0 | #REF! | [9 empty] | 0.1824 | 0.2736 | 0.17 | 0.03936
[8 empty] | 0 | 0 | 0 | 0 | #REF!
9.48 | Providing & fixing MS grills of required pattern in frames of windows etc. with MS flats, square or round bars etc. all complete. |  |  |  | 3300 |  |  | 0 | 0 | 0 | 0 | #REF! |  | 1.02
9.48.1 | Fixed to steel windows by welding | Kg | 90.75 | 167840.64 |  |  | 8438 | 15231538.08 | 0 | 0 | 765748.5 | #REF! |  | 0
[8 empty] | 0 | 0 | 0 | 0 | #REF!
9.63 | Providing and fixing ISI marked oxidised M.S. tower bolt black finish, (Barrel type) with necessary screws etc. complete : |  |  |  |  | 231 | 1050 | 0 | 0 | 0 | 0 | #REF!
9.63.4 | 100x10 mm | Each | 29.4 | 15120 |  |  | 550 | 444528 | 0 | 0 | 16170 | #REF!
[5 empty] | 125 | 304 |  | 0 | 0 | 0 | 0 | #REF!
9.66 | Providing and fixing ISI marked oxidised M.S. handles conforming to IS:4992 with necessary screws etc. complete : |  |  |  | 20 | 90 |  | 0 | 0 | 0 | 0 | #REF! | [32 empty] | 0.95
9.66.2 | 100 mm | Each | 21.25 | 15120 |  |  |  | 321300 | 0 | 0 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
9.68 | Providing & fixing oxidised M.S. casement stays (straight peg type) with necessary screws etc. complete. | [6 empty] | 0 | 0 | 0 | 0 | #REF!
9.68.1 | 300 mm weighing not less than 200 gms. | Each | 29.8 | 30240 | 225 | 365 |  | 901152 | 6705 | 10877 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
9.96 | Providing & fixing Aluminium sliding door bolts ISI marked anodised (anodic coating not less than grade AC 10 as per IS:1868) transparent or dyed to required colour or shade with nuts and screws etc. complete | [6 empty] | 0 | 0 | 0 | 0 | #REF!
9.96.2 | 250 x16 mm | Each | 168.95 | 6048 | 25 | 45 |  | 1021809.6 | 4223.75 | 7602.75 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
9.97 | Providing & fixing Aluminium tower bolt ISI marked anodised (anodic coating not less than grade AC 10 as per IS:1868) transparent or dyed to required colour or shade with nuts and screws etc. complete. |  |  |  | 15000 | 48300 |  | 0 | 0 | 0 | 0 | #REF! | [31 empty] | 1.025
9.97.2 | 250 x 10 mm | Each | 86.45 | 30240 | 8500 |  |  | 2614248 | 734825 | 0 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
9.98 | Providing & fixing Aluminium pull bolt lock ISI marked anodised (anodic coating not less than grade AC 10 as per IS:1868) transparent or dyed to required colour or shade with nuts and screws etc. complete | Each | 62.45 | 9072 | 15 | 48.3 |  | 566546.4 | 936.75 | 3016.335 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
9.1 | Providing & fixing Aluminium handles ISI marked anodised (anodic coating not less than grade AC 10 as per IS:1868) transparent or dyed to required colour or shade with nuts and screws etc. complete. |  |  |  | 30 | 120 |  | 0 | 0 | 0 | 0 | #REF!
9.100.2 | 100 mm | Each | 49.55 | 30240 | 40 | 200 |  | 1498392 | 1982 | 9910 | 0 | #REF!
[5 empty] | 50 | 300 |  | 0 | 0 | 0 | 0 | #REF!
9.101 | Providing & fixing Aluminium hanging floor door stopper ISI marked anodised (anodic coating not less than grade AC 10 as per IS:1868) transparent or dyed to required colour or shade with nuts and screws etc. complete |  |  |  | 15000 | 50000 |  | 0 | 0 | 0 | 0 | #REF!
9.101.1 | Single rubber stopper | Each | 28.6 | 15120 | 425 |  |  | 432432 | 12155 | 0 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
9.136 | Providing & fixing fire resistant door frame of section 143 x 57 mm having built in rebate made out of 16 SWG G.I.sheet (zinc coating not less than 120 gm/sqm) duly filled with vermuculite based concrete mix, suitable for mounting 60 minutes fire rated door shutters. The frame is fitted with intumuscent fire seal strip of size 10x4 mm (minimum) alround the frame and fixing with dash fastener of approved size and make, including applying a coat of approved brand fire resistant primer etc. complete as per direction of Engineer-in-charge (Dash fastener to be paid for separately). | Mtr | 1161.45 | 2394 | 250 | 1250 |  | 2780511.3 | 290362.5 | 1451812.5 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
N.S. (DSR Based) | Providing & fixing 50 mm thick fire resistant Flush Door shutters of 60 minutes fire rating conforming to IS:3614 (Part-II) tested and certified as per laboratory approved by Engineer-in-charge with suitable mounting on door frame using 0.80 mm thick steel pressed formed to provide a 50 mm thick fully flush double skin door shell with lock seam joints at stile edges. The internal construction of the door to be phenolic resin impregrated specially designed honey comb craft paper with suitable internal reinforcement for receiving the hardware. Pressed steel used to be galvanised with zinc coating not less than 120 gm/sqm and fixing with stainless steel ball bearing hinges of approved make including a coat of approved fire resistant primer complete as per direction of Engineer-in-charge. | Sqm | 5727.2 | 1222.2 |  |  |  | 6999783.84 | 0 | 0 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
N.S. | Providing & fixing in position 2mm thick Aluminium Sheet on inside of doors in W.C. and bath complete with screws. | Sqm | 1576.27 | 1814.4 |  |  |  | 2859984.288 | 0 | 0 | 0 | #REF!
[5 empty] | 500 | 1985 |  | 0 | 0 | 0 | 0 | #REF!
9.139 | Providing & fixing panic bar / latch (Double point) fitted with a single body, Trim Latch & Lock on back side of the Panic Latch of reputed brand and manufacture to be approved by the Engineer- in- charge, all complete. | Each | 5873.25 | 420 |  |  | 850 | 2466765 | 0 | 0 | 4992262.5 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
| SUB - HEAD - VI: STEEL WORK |  |  |  |  | 950 |  | 0 | 0 | 0 | 0 | #REF!
10.5 | Providing & fixing 1mm thick M.S. sheet door with frame of 40x40x6 mm angle iron and 3 mm M.S. gusset plates at the junctions and corners, all necessary fittings complete, including applying a priming coat of approved steel primer. |  |  |  | 220 |  |  | 0 | 0 | 0 | 0 | #REF!
10.5.2 | Using flats 30x6mm for diagonal braces and central cross piece | sqm | 2427.15 | 64.26 |  |  |  | 155968.659 | 0 | 0 | 0 | #REF!
[6 empty] | 3420 |  | 0 | 0 | 0 | 0 | #REF!
10.11 | Providing & fixing factory made ISI marked steel glazed doors, windows and ventilators side /top /centre hung with beading and all members such as F7D, F4B, K11 B and K12 B etc. complete of standard rolled steel sections, joints mitred and flash butt welded and sash bars tenoned and riveted, including providing and fixing of hinges, pivots, including priming coat of approved steel primer , but excluding the cost of other fittings, complete all as per approved design (sectional weight of only steel members shall be measured for payment). |  |  |  | 220 |  |  | 0 | 0 | 0 | 0 | #REF!
10.11.1 | Fixing with 15x3 mm lugs 10 cm long embedded in cement concrete block 15x10x10 cm of CC 1:3:6 (1 Cement : 3 coarse sand : 6 graded stone aggregate 20 mm nominal size). | kg | 96.3 | 172036.64 |  |  |  | 16567128.432 | 0 | 0 | 0 | #REF!
[5 empty] | 0 | 7500 |  | 0 | 0 | 0 | 0 | #REF!
| Providing & fixing T-iron frames for doors, windows and ventilators of mild steel Tee-sections, joints mitred and welded, including fixing of necessary butt hinges and screws and applying a priming coat of approved steel primer. |  |  |  | 250 |  |  | 0 | 0 | 0 | 0 | #REF!
10.13.1 | Fixing with 15x3mm lugs 10cm long embedded in cement concrete block 15x10x10cm of CC 1:3:6 (1 Cement : 3 coarse sand : 6 graded stone aggregate 20 mm nominal size) | Kg | 73.3 | 157208.1 |  |  | 2750 | 11523353.73 | 0 | 0 | 201575 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
10.14 | Providing & fixing pressed steel door frames conforming to IS: 4351 manufactured from commercial mild steel sheet of 1.60 mm thickness including hinges, jamb, lock jamb, bead and if required angle threshold of mild steel angle of section 50x25mm, or base ties of 1.60 mm pressed mild steel welded or rigidly fixed together by mechanical means, including M.S. pressed butt hinges, 2.5mm thick with mortar guards, lock strike-plate and shock absorbers as specified and applying a coat of approved steel primer after pre-treatment of the surface as directed by Engineer-in-charge: | [5 empty] | 850 | 0 | 0 | 0 | 0 | #REF!
10.14.2 | Profile C (62 x 125mm) | [5 empty] | 2450 | 0 | 0 | 0 | 0 | #REF!
10.14.2.1 | Fixing with adjustable lugs with split end tail to each jamb. | Meter | 370 | 30844.8 | 15 | 65 |  | 11412576 | 5550 | 24050 | 0 | #REF!
[5 empty] | 220 | 1650 |  | 0 | 0 | 0 | 0 | #REF!
10.25 | Steel work welded in built up sections/framed work including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer using structural steel etc. as required. | [6 empty] | 0 | 0 | 0 | 0 | #REF!
10.25.2 | In gratings, frames, guard bar, ladder, railings, brackets, gates and similar works. | Kg | 77.9 | 22588.17 |  | 2050 |  | 1759618.443 | 0 | 159695 | 0 | #REF!
[5 empty] | 230 |  |  | 0 | 0 | 0 | 0 | #REF!
| Providing & fixing hand rail of approved size welding etc. to steel ladder railing, balcony railing and stair case railing including applying a priming coat of approved steel primer | [6 empty] | 0 | 0 | 0 | 0 | #REF!
10.26.1 | MS Tube - 50mm dia | Kg | 86.45 | 60923.8 |  | 4000 |  | 5266862.51 | 0 | 345800 | 0 | #REF!
[5 empty] | 250 |  |  | 0 | 0 | 0 | 0 | #REF!
| Providing & fixing glass panes with putty and glazing clips in steel doors, windows, clerestory windows all complete. | [6 empty] | 0 | 0 | 0 | 0 | #REF!
10.30.1 | With 4.0 mm thick glass panes. | Sqm | 657.75 | 13986.72 |  |  | 1200 | 9199765.08 | 0 | 0 | 789300 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
[7 empty] | 400 | 0 | 0 | 0 | 0 | #REF!
| SUB - HEAD - VII: FLOORING WORK | [5 empty] | 450 | 0 | 0 | 0 | 0 | #REF!
[7 empty] | 450 | 0 | 0 | 0 | 0 | #REF!
11.5 | 62 mm thick cement concrete flooring with concrete hardener topping, under layer 50 mm thick cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) and top layer 12mm thick cement hardener consisting of mix 1:2 (1 cement hardener mix : 2 graded stone aggregate, 6mm nominal size) by volume, hardening compound mixed @ 2 litre per 50kg of cement or as per manufactures specifications. This includes cost of cement slurry, but excluding the cost of nosing of steps etc. complete. | Sqm | 464.8 | 8649.85 |  |  | 550 | 4020450.28 | 0 | 0 | 255640 | #REF!
[7 empty] | 800 | 0 | 0 | 0 | 0 | #REF!
8.1 | Marble work gang saw cut (polished and machine cut) of thickness 18mm for wall lining (veneer work), backing filled with a grout of average 12 mm thick in cement mortar 1:3 (1 cement : 3 coarse sand) including pointing with white cement mortar 1:2 (1 white cement : 2 marble dust) with an admixture of pigment to match the marble shade: (To be secured to the backing by means of cramps, which shall be paid for separately). | [5 empty] | 700 | 0 | 0 | 0 | 0 | #REF!
8.1.1 | Udaipur green marble | [5 empty] | 2000 | 0 | 0 | 0 | 0 | #REF!
8.1.1.2 | Area of slab over 0.50 sqm | Sqm | 2314.1 | 23193.66 |  |  | 750 | 53672448.606 | 0 | 0 | 1735575 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
8.2 | Providing and fixing 18mm thick gang saw cut mirror polished premoulded and prepolished) machine cut for kitchen platforms, vanity counters, window sills, facias and similar locations of required size of approved shade, colour and texture laid over 20mm thick base cement mortar 1:4 (1 cement : 4 coarse sand) with joints treated with white cement, mixed with matching pigment, epoxy touch ups, including rubbing, curing, moulding and polishing to edges to give high gloss finish etc. complete at all levels. |  |  |  |  | 1800 |  | 0 | 0 | 0 | 0 | #REF!
8.2.1 | Udaipur green marble |  |  |  | 250 |  |  | 0 | 0 | 0 | 0 | #REF!
8.2.1.2 | Area of slab over 0.50 sqm | Sqm | 1980.8 | 4838.4 |  |  |  | 9583902.72 | 0 | 0 | 0 | #REF!
[5 empty] | 950 | 3654 |  | 0 | 0 | 0 | 0 | #REF! | 1.25 |  | 0.177 |  |  |  | 487
8.4 | Extra for fixing marble /granite stone over and above corresponding basic item, in facia and drops of width upto 150 mm with epoxy resin based adhesive including cleaning etc. complete. | mtr | 185.8 | 6924.96 | 850 | 2850 |  | 1286657.568 | 157930 | 529530 | 0 | #REF!
[5 empty] | 600 | 3654 |  | 0 | 0 | 0 | 0 | #REF! | 1.55 |  | 0.177 |  |  |  | 487
8.5 | Extra for providing opening of required size & shape for wash basins/ kitchen sink in kitchen platform, vanity counters and similar location in marble/Granite/stone work including necessary holes for pillar taps etc. including moulding, rubbing and polishing of cut edges etc. complete. | each | 281.1 | 3024 | 75 | 420.21 |  | 850046.4 | 21082.5 | 118121.031 | 0 | #REF! | 0.21 |  | 0.0198 |  |  |  | 56.5
[5 empty] | 75 | 327.75 |  | 0 | 0 | 0 | 0 | #REF!
8.7 | Providing & fixing cramps of required size & shape in RCC/ CC / Brick masonry backing with cement mortar 1:2 ( 1 cement :2 coarse sand) including drilling necessary hole in stones and embedding the cramp in the hole (fastener to be paid separately). |  |  |  | 200 |  |  | 0 | 0 | 0 | 0 | #REF!
8.7.2 | Stainless steel cramps. | Kg | 524.1 | 6958.09 | 46 |  |  | 3646734.969 | 24108.6 | 0 | 0 | #REF!
[5 empty] | 550 | 3654 |  | 0 | 0 | 0 | 0 | #REF!
11.6 | Cement plaster skirting (up to 30 cm height) with cement mortar 1:3 (1 cement : 3 coarse sand) finished with a floating coat of neat cement. |  |  |  | 500 |  |  | 0 | 0 | 0 | 0 | #REF!
11.6.1 | 18 mm thick | Sqm | 258.2 | 681.74 | 10 | 225 |  | 176025.268 | 2582 | 58095 | 0 | #REF!
[5 empty] | 100 | 350 |  | 0 | 0 | 0 | 0 | #REF!
11.26 | Kota stone slab flooring over 20 mm (average) thick base laid over and jointed with grey cement slurry mixed with pigment to match the shade of the slab, including rubbing and polishing complete with base of cement mortar 1 : 4 (1 cement : 4 coarse sand) : | [6 empty] | 0 | 0 | 0 | 0 | #REF!
11.26.1 | 25mm thick | Sqm | 945.7 | 16420.51 | 45 | 270 |  | 15528876.307 | 42556.5 | 255339 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
11.27 | Kota stone slabs 20 mm thick in risers of steps, skirting, dado and pillars laid on 12 mm (average) thick cement mortar 1:3 (1 cement: 3 coarse sand) and jointed with grey cement slurry mixed with pigment to match the shade of the slabs, including rubbing and polishing complete. | Sqm | 954.1 | 3187.11 | 55 | 39 |  | 3040821.651 | 52475.5 | 37209.9 | 0 | #REF! | 0.071 |  | 0.01003
[5 empty] | 65 | 59 |  | 0 | 0 | 0 | 0 | #REF! | 0.107 |  | 0.01512
11.31 | Extra for pre finished nosing in Kota stone/Sand stone labs | meter | 52.45 | 8064 | 72 | 66 |  | 422956.8 | 3776.4 | 3461.7 | 0 | #REF! | 0.112 |  | 0.01582
[5 empty] | 79 | 20 |  | 0 | 0 | 0 | 0 | #REF!
11.32 | Extra for Kota stone/Sand stone in treads of steps and risers using single length up to 1.55m | Sqm | 12.1 | 16420.51 | 125 | 70 |  | 198688.171 | 1512.5 | 847 | 0 | #REF!
[7 empty] | 60 | 0 | 0 | 0 | 0 | #REF!
11.36 | Providing & fixing 1st quality white ceramic glazed wall tiles conforming to IS:15622 (thickness to be specified by the manufacture) to approved make in as approved by Engineer -in- charge in skirting, risers of steps, and dados over 12 mm thick bed of Cement Mortar 1:3 (1 cement: 3 coarse sand) and jointing with grey cement slurry @ 3.3 kg per sqm including pointing in white cement mixed with pigment of matching shade complete. | Sqm | 724.25 | 27911.52 | 65 | 66 |  | 20214918.36 | 47076.25 | 47800.5 | 0 | #REF! | 0.112 |  | 0.01582
[7 empty] | 150 | 0 | 0 | 0 | 0 | #REF!
11.37 | Providing & laying Ceramic glazed floor tiles 300x300 mm (thickness to be specified by the manufacturer) of 1st quality conforming to IS:15622 of approved make in colours such as White, Ivory, Grey, Fume Red Brown, laid on 20 mm thick Cement Mortar 1:4 (1 Cement : 4 Coarse sand) including pointing the joints with white cement and matching pigment etc., complete. | Sqm | 764.55 | 6985.44 |  |  | 12 | 5340718.152 | 0 | 0 | 9174.6 | #REF!
[5 empty] | 45 | 66 |  | 0 | 0 | 0 | 0 | #REF!
11.41 | Providing & laying vitrified floor tiles in different sizes (thickness to be specified by the manufacturer) with water absorption less than 0.08% and conforming to IS:15622, of approved make, in all colours and shades, laid on 20mm thick cement mortar 1:4 (1 cement : 4 coarse sand), including grouting the joints with white cement and matching pigments etc., complete. | [6 empty] | 0 | 0 | 0 | 0 | #REF!
11.41.2 | Size of Tile 600x600 mm | Sqm | 1337.4 | 76235.04 |  |  | 10 | 101956742.496 | 0 | 0 | 13374 | #REF!
[7 empty] | 55 | 0 | 0 | 0 | 0 | #REF!
11.46 | Providing & laying Vitrified tiles in different sizes (thickness to be specified by manufacturer) with water absorption less than 0.08 % and conforming to IS:15622, of approved make in all colours & shade in skirting, riser of steps, over 12 mm thick bed of cement mortar 1:3 (1 cement: 3 coarse sand), including grouting the joint with white cement & matching pigments etc. complete. | [5 empty] | 55 | 0 | 0 | 0 | 0 | #REF!
11.46.2 | Size of Tile 600x600 mm | Sqm | 1339.2 | 10190.88 |  |  | 350 | 13647626.496 | 0 | 0 | 468720 | #REF!
[7 empty] | 375 | 0 | 0 | 0 | 0 | #REF!
| SUB - HEAD - VIII: ROOFING WORK | [5 empty] | 375 | 0 | 0 | 0 | 0 | #REF!
[7 empty] | 95 | 0 | 0 | 0 | 0 | #REF!
22.5 | Providing & laying water proofing treatment in sunken portion of WCs, bathroom etc., by applying cement slurry mixed with water proofing cement compound consisting of applying : a) First layer of slurry of cement @ 0.488 kg/sqm mixed with water proofing cement compound @ 0.253 kg/sqm. This layer will be allowed to air cure for 4 hours. b) Second layer of slurry of cement @ 0.242 kg/sqm mixed with water proofing cement compound @ 0.126 kg/sqm. This layer will be allowed to air cure for 4 hours followed with water curing for 48 hours. The rate includes preparation of surface, treatment and sealing of all joints, corners, junctions of pipes and masonry with polymer mixed slurry. | Sqm | 215.15 | 34624.8 | 150 | 190.957 |  | 7449525.72 | 32272.5 | 41084.3985 | 0 | #REF!
[7 empty] | 225 | 0 | 0 | 0 | 0 | #REF!
22.7 | Providing and laying integral cement based waterproofing treatment including preparation of surface as required for treatment of roofs, balconies, terraces etc. consisting of following operations. | [5 empty] | 30 | 0 | 0 | 0 | 0 | #REF!
| Applying a slurry coat of neat cement using 2.75 kg. / sqm of cement admixed with waterproofing compound conforming to IS:2645 and approved by Engineer-in-charge over the R.C.C. slab including adjoining walls up to 300mm height including cleaning the surface before treatment. | [6 empty] | 0 | 0 | 0 | 0 | #REF!
| Laying brick bats with mortar using broken bricks/brick bats 25mm to 115 mm size with 50% of cement mortar 1:5 (1 cement : 5 coarse sand) admixed with waterproofing compound conforming to IS:2645 and approved by Engineer-in-charge over 20mm thick layer of cement mortar of mix 1:5 (1 cement :5 coarse sand) admixed with waterproofing compound conforming to IS:2645 and approved by Engineer-in-Charge over 20mm thick layer of cement mortar of mix 1:5 (1 cement : 5 coarse sand) admixed with water proofing compound conforming to IS : 2645 and approved by Engineer-in-charge to required slope and treating similarly the adjoining walls upto 300 mm height including rounding of junctions of walls and slabs. | [6 empty] | 0 | 0 | 0 | 0 | #REF!
| After two days of proper curing applying a second coat of cement slurry using 2.75 Kg/Sqm of cement admixed with waterproofing compound conforming to IS:2645 and approved by Engineer-in-charge. |  |  |  |  | 258.068 |  | 0 | 0 | 0 | 0 | #REF!
| Finishing the surface with 20mm thick jointless cement mortar of mix 1:4 (1 cement : 4 coarse sand) admixed with waterproofing compound conforming to IS:2645 and approved by Engineer-in-charge laying glass fibre cloth of approved quality in top layer of plaster and finally finishing the surface with trowel with neat cement slurry and making of 300x300 mm square 3mm deep. |  |  |  | 65 |  |  | 0 | 0 | 0 | 0 | #REF!
| The whole terrace so finished shall be flooded with water for a minimum period of two weeks for curing and for final test. All above operations to be done in order and as directed & specified by the Engineer-in-charge. |  |  |  | 65 | 183.143 |  | 0 | 0 | 0 | 0 | #REF!
22.7.1 | With average thickness of 120 mm and minimum thickness at Khurra as 65 mm | Sqm | 786.7 | 8928.98 | 150 | 488.4 |  | 7024428.566 | 118005 | 384224.28 | 0 | #REF!
[5 empty] | 150 | 474.064 |  | 0 | 0 | 0 | 0 | #REF!
12.22 | Making khurras 45x45cm with average minimum thickness of 5cm cement concrete 1:2:4 (1cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) over PVC sheet 1mx1mx400micron, finished with 12mm cement plaster 1:3 (1cement : 3 coarse sand) and a coat of neat cement rounding the edge sand making and finishing the outlet complete. | Each | 148.75 | 250 | 100 | 437.45 |  | 37187.5 | 14875 | 65070.6875 | 0 | #REF!
[7 empty] | 3500 | 0 | 0 | 0 | 0 | #REF!
12.42 | Providing & fixing on wall face unplasticised-Rigid PVC rain water pipes conformining to IS:13592 Type A including jointing with seal ring conforming to IS:5382 leaving 10 mm gap for thermal expansion. | [6 empty] | 0 | 0 | 0 | 0 | #REF!
12.42.1.1 | Single Socketed Pipes - 110 mm | meter | 206.9 | 9466.8 |  |  |  | 1958680.92 | 0 | 0 | 0 | #REF!
[6 empty] | 1701 |  | 0 | 0 | 0 | 0 | #REF!
12.42 | Providing & fixing on wall face unplasticised - PVC moulded fittings / accessories for unplasticised Rigid PVC rain water pipes conforming to IS:13592 Type A including jointing with seal ring conforming to IS:5382 leaving 10 mm gap for thermal expansion. |  |  |  | 541.2 |  |  | 0 | 0 | 0 | 0 | #REF!
12.42.5 | Bend 87.5° | [6 empty] | 0 | 0 | 0 | 0 | #REF!
12.42.5.2 | 110 mm bend | Each | 156.95 | 250 |  | 1755.6 |  | 39237.5 | 0 | 275541.42 | 0 | #REF!
[5 empty] | 752.4 |  |  | 0 | 0 | 0 | 0 | #REF!
12.42.6 | Shoe (Plain) | [6 empty] | 0 | 0 | 0 | 0 | #REF!
12.42.6.2 | 110 mm Shoe | Each | 287.05 | 250 |  | 2371.6 |  | 71762.5 | 0 | 680767.78 | 0 | #REF!
[5 empty] | 1016.4 |  |  | 0 | 0 | 0 | 0 | #REF!
12.43 | Providing & fixing unplasticised - PVC pipe clips of approved design to unplasticised - PVC rain water pipes by means of 50x50x50mm hard wood plugs, screwed with M.S. screws of required length including cutting brick work and fixing in cement mortar 1:4 (1 cement : 4 coarse sand) and making good the wall etc. complete. |  |  |  | 257.5 | 750 |  | 0 | 0 | 0 | 0 | #REF!
12.43.2 | 110 mm | Each | 144.6 | 6582 | 515 | 750 |  | 951757.2 | 74469 | 108450 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
12.46 | Providing & fixing to the inlet mouth of rain water pipe PTMT (an Engineering thermoplastic) grating square (Slit) 150 mm square with a height of 8 mm and weighing not less than 100 gms. | Each | 96.65 | 250 |  | 1550 |  | 24162.5 | 0 | 149807.5 | 0 | #REF!
[5 empty] | 504.7 |  |  | 0 | 0 | 0 | 0 | #REF!
| SUB - HEAD - IX: FINISHING WORK |  |  |  | 504.7 | 1550 |  | 0 | 0 | 0 | 0 | #REF!
13.1 | 12 mm cement plaster of mix: |  |  |  | 154.5 | 588.41 |  | 0 | 0 | 0 | 0 | #REF!
13.1.2 | 1:6 (1 cement: 6 fine sand) | Sqm | 112.5 | 415905.54 |  |  |  | 46789373.25 | 0 | 0 | 0 | #REF!
[6 empty] | 678.41 |  | 0 | 0 | 0 | 0 | #REF!
13.16 | 6 mm cement plaster of mix: |  |  |  | 154.5 |  |  | 0 | 0 | 0 | 0 | #REF!
13.16.1 | 1:3 (1 cement: 6 fine sand) | Sqm | 101 | 110500.24 | 154.5 | 250.91 |  | 11160524.24 | 15604.5 | 25341.91 | 0 | #REF!
[5 empty] | 504.7 | 1550 |  | 0 | 0 | 0 | 0 | #REF!
13.41 | Distempering with oil bound washable distemper of approved brand and manufacture to give an even shade | [6 empty] | 0 | 0 | 0 | 0 | #REF!
13.41.1 | New work (two or more coats) over and including water thinnable priming coat with cement primer. | Sqm | 66.7 | 437800.4 |  | 318.41 |  | 29201286.68 | 0 | 21237.947 | 0 | #REF!
[5 empty] | 154.5 |  |  | 0 | 0 | 0 | 0 | #REF!
13.44 | Finishing walls with water proofing cement paint of required shade : |  |  |  | 65 | 195 |  | 0 | 0 | 0 | 0 | #REF!
13.44.1 | New work (Two or more coat applied @ 3.84 ltr/10 sqm). | Sqm | 44.95 | 100141.44 | 125 | 387.5 |  | 4501357.728 | 5618.75 | 17418.125 | 0 | #REF!
[5 empty] | 150 | 363.41 |  | 0 | 0 | 0 | 0 | #REF!
13.5 | Applying priming coat : |  |  |  | 150 | 206.3 |  | 0 | 0 | 0 | 0 | #REF!
13.50.1 | With ready mixed pink or Grey primer of approved brand and manufacture on wood work (hard and soft wood). | Sqm | 25.85 | 55989.36 |  |  |  | 1447324.956 | 0 | 0 | 0 | #REF!
[5 empty] | 2 | 9 |  | 0 | 0 | 0 | 0 | #REF!
13.58 | Providing & applying two coats of fire retardant paint on cleaned wood/ply surface @ 3.5 sqm per litre per coat including preparation of base surface as per recommendations of manufacturer to make the surface fire retardant. | Sqm | 267.15 | 3045 | 2 | 63 |  | 813471.75 | 534.3 | 16830.45 | 0 | #REF!
[5 empty] | 2 | 45 |  | 0 | 0 | 0 | 0 | #REF!
13.61 | Painting with synthetic enamel paint of approved brand and manufacture to give an even shade : | [6 empty] | 0 | 0 | 0 | 0 | #REF!
13.61.1 | Two or more coats on new work | Sqm | 53.85 | 90838.94 |  |  |  | 4891676.919 | 0 | 0 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
13.72 | Washed stone grit plaster on exterior walls of height upto 10 M. above ground level in two layers, under layer 12mm cement plaster 1:4 (1 cement: 4 coarse sand) furrowing the under layer with scratching tool, applying cement slurry on the under layer @ 2 Kg of cement per square metre, top layer 15mm cement plaster 1:1/2:2 (1 cement: 1/2 coarse sand : 2 stone chipping 10mm nominal size) in panels with groove all around as per approved pattern including scrubbing and washing, the top layer with brushes and water to expose the stone chippings, complete as per specification & direction of Engineer-in-charge (Payment for providing grooves shall be made separately). | Sqm | 417.35 | 87700.95 |  |  |  | 36601991.4825 | 0 | 0 | 0 | #REF!
[6 empty] | 625 |  | 0 | 0 | 0 | 0 | #REF!
13.73 | Forming groove of uniform size in the top layer of washed stone grit plaster as per approved pattern using wooden battens, nailed to the under layer including removal of wooden battens, repair to the edges of panels and finishing the groove complete as per specifications and direction of the Engineer-in-charge : | mtr | 23.65 | 256400.93 | 100 |  |  | 6063881.9945 | 2365 | 0 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
13.74 | Extra for washed grit plaster on exterior walls of height more than 10m from ground level for every additional height of 3 m or part thereof. | Sqm | 65.85 | 391989.74 |  |  |  | 25812524.379 | 0 | 0 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
[6 empty] | 655 |  | 0 | 0 | 0 | 0 | #REF!
[5 empty] | 100 |  |  | 0 | 0 | 0 | 0 | #REF!
| Sub Total | [6 empty] | 0 | 0 | 0 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
Horticulture & Landscaping | [5 empty] | 1150 |  | 0 | 0 | 0 | 0 | #REF!
[5 empty] | 255 |  |  | 0 | 0 | 0 | 0 | #REF!
18.12 | Providing & fixing GI pipes complete with GI fittings including trenching and refilling etc. | [6 empty] | 0 | 0 | 0 | 0 | #REF!
| External work |  |  |  |  | 580 |  | 0 | 0 | 0 | 0 | #REF!
18.12.3 | 25 mm dia. nominal bore | metre | 209.4 | 145 | 110 |  |  | 30363 | 23034 | 0 | 0 | #REF!
[7 empty] | 475 | 0 | 0 | 0 | 0 | #REF!
18.38 | Painting G.I. pipes and fittings with synthetic enamel white paint with two coats over a ready mixed priming coat, both of approved quality for new work : | [5 empty] | 800 | 0 | 0 | 0 | 0 | #REF!
18.38.3 | 25 mm diameter pipe | metre | 11.4 | 145 |  |  |  | 1653 | 0 | 0 | 0 | #REF!
[7 empty] | 650 | 0 | 0 | 0 | 0 | #REF!
18.41 | Providing and filling sand of grading zone V or coarser grade all-round the G.I. pipes in external work. | [6 empty] | 0 | 0 | 0 | 0 | #REF!
18.41.3 | 25 mm diameter pipe | metre | 56.95 | 145 |  |  | 385 | 8257.75 | 0 | 0 | 21925.75 | #REF!
[7 empty] | 165 | 0 | 0 | 0 | 0 | #REF!
18.46 | Providing and fixing G.I. Union in G.I. pipe including cutting and threading the pipe and making long screws etc. complete (New work) | [6 empty] | 0 | 0 | 0 | 0 | #REF!
18.46.3 | 25 mm nominal bore | each | 307.7 | 5 |  |  | 840 | 1538.5 | 0 | 0 | 258468 | #REF!
[7 empty] | 360 | 0 | 0 | 0 | 0 | #REF!
23.1 | Trenching in ordinary soil up to a depth of 60cm including removal and stacking of serviceable materials and then disposing of surplus soil, by spreading and neatly leveling within a lead of 50m and making up the trenched area to proper levels by filling with earth or earth mixed with sludge or/and manure before and after flooding trench with water (excluding cost of imported earth, sludge or manure). | cum | 30.9 | 157.53 |  |  |  | 4867.677 | 0 | 0 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
23.2 | Supplying and stacking of good earth at site including royalty and carriage up to 1 km (earth measured in stacks will be reduced by 20% for payment). | cum | 260.7 | 78.77 |  |  |  | 20535.339 | 0 | 0 | 0 | #REF!
[6 empty] | 434 |  | 0 | 0 | 0 | 0 | #REF!
23.4 | Supplying and stacking at site dump manure from approved source, including carriage up to 1 km (manure measured in stacks will be reduced by 8% for payment) : |  |  |  | 201 |  |  | 0 | 0 | 0 | 0 | #REF!
23.4.3 | Screened through sieve of I.S. designation 4.75mm | cum | 164.1 | 19.69 |  |  |  | 3231.129 | 0 | 0 | 0 | #REF!
[6 empty] | 701 |  | 0 | 0 | 0 | 0 | #REF!
23.5 | Rough dressing the trenched ground including breaking clods. | 100 sqm | 0.5985 | 1050.22 | 260 |  |  | 628.5567 | 155.61 | 0 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
23.7 | Fine dressing of the ground | 100 sqm | 1.459 | 1050.22 |  | 1120 |  | 1532.271 | 0 | 1634.08 | 0 | #REF!
[5 empty] | 300 |  |  | 0 | 0 | 0 | 0 | #REF!
23.9 | Mixing earth and sludge or manure in the required proportion specified or directed by the Officer-in-charge. | cum | 14.35 | 98.46 |  |  |  | 1412.901 | 0 | 0 | 0 | #REF!
[5 empty] | 77 | 185 |  | 0 | 0 | 0 | 0 | #REF!
23.10 | Grassing with selection No.1 grass including watering and maintenance of the lawn for 30 days or more till the grass forms a thick lawn, free from weeds and fit for mowing including supplying good earth, if needed (the good earth shall be paid for separately). | 100 sqm |  |  | 111 | 245 |  | 0 | 0 | 0 | 0 | #REF!
23.10.1 | In rows 5 cm apart in both directions. |  | 7.0025 | 1050.22 | 151 | 345 |  | 7354.1656 | 1057.3775 | 2415.8625 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
(AR) | Providing and fixing ball valve with lever : |  |  |  | 25 | 225 |  | 0 | 0 | 0 | 0 | #REF!
| 25 mm nominal bore | each | 250 | 13 |  | 13830 |  | 3250 | 0 | 3457500 | 0 | #REF!
[5 empty] | 275 | 399.75 |  | 0 | 0 | 0 | 0 | #REF!
(AR) | Providing and installing sprinklers for irrigation including 15 metre PVC pipe to the entire satisfaction of Engineer-in-charge. | each | 2500 | 4 | 25 | 125 |  | 10000 | 62500 | 312500 | 0 | #REF!
[5 empty] | 25 | 205 |  | 0 | 0 | 0 | 0 | #REF!
(AR) | Providing & laying 60mm thick factory made cement concrete grass crete block of M -30 grade made by block making machine with strong vibratory compaction, of approved size, design & shape, laid in required colour and pattern over and including 50mm thick compacted bed of fine sand, filling the joints with fine sand etc. all complete as per the direction of Engineer-in-charge. | sqm | 536.65 | 294.95 | 15000 |  |  | 158284.9175 | 8049750 | 0 | 0 | #REF!
[5 empty] | 7500 |  |  | 0 | 0 | 0 | 0 | #REF!
23.14 | Digging holes in ordinary soil and refilling the same with the excavated earth mixed with manure or sludge in the ratio of 2:1 by volume (2 parts of stacked volume of earth after reduction by 20% : 1 part of stacked volume of manure after reduction by 8%) flooding with water, dressing including removal of rubbish and surplus earth, if any, with all leads and lifts (cost of manure, sludge or extra good earth if needed to be paid for separately) : |  |  |  | 25 | 67.5 |  | 0 | 0 | 0 | 0 | #REF!
23.14.2 | Holes 90 cm dia, and 90 cm deep. | each | 80.2 | 50 |  |  | 100700 | 4010 | 0 | 0 | 8076140 | #REF!
[7 empty] | 105000 | 0 | 0 | 0 | 0 | #REF!
23.16 | Providing & fixing M.S. flat iron tree guard 60 cm dia. and 2 m high, above ground consisting 4 nos. 25 x 6 mm, 2.25 m long and 8 nos. 25 x 3 mm 2 m long verticals M.S. flats, riveted to 3 nos. 25 x 6 mm M.S. flat iron rings in two halves, fixing together at site with required six numbers of 8 mm dia. and 30 mm long bolts, including painting two coats with synthetic enamel paint of approved brand and manufacture over a coat of primer. One name plate of 1 mm thick M.S. sheet of size 250x100 mm shall be welded to the tree guard near the middle height and lettered CPWD / PWD/ any other approved name. The tree guard shall be suitably fixed to the ground by embedding four legs of tree guard in pits of suitable dia and to a depth of 25 cm, refilling the pits with soil and ramming, complete in all respect as per satisfaction and direction of Officer-in-charge. | each | 2580.6 | 50 | 2000 |  | 5000 | 129030 | 5161200 | 0 | 12903000 | #REF!
[5 empty] | 25 | 45 |  | 0 | 0 | 0 | 0 | #REF!
23.28 | Preparation of mounds of various size and shape by available excavated / supplied earth in layers not exceeding 20 cm in depth, breaking clods, watering of each layer, dressing etc., lead upto 50 meter and lift upto 1.5 m complete as per direction of Officer-in-charge. | cum | 178.7 | 36 |  |  |  | 6433.2 | 0 | 0 | 0 | #REF!
[5 empty] | 70 | 137 |  | 0 | 0 | 0 | 0 | #REF!
(MR) | Supply & Planting of Trees |  |  |  | 105 | 205 |  | 0 | 0 | 0 | 0 | #REF!
| Ashoka Tree | each | 255.5 | 50 | 142 | 285 |  | 12775 | 36281 | 72817.5 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
| Sub Total |  |  |  | 114 | 237.6 |  | 0 | 0 | 0 | 0 | #REF!
[5 empty] | 32.25 | 68.25 |  | 0 | 0 | 0 | 0 | #REF!
CLUBED ABSTRACT FOR INFRASTRUCTURE WORK |  |  |  |  | 22000 | 68000 |  | 0 | 0 | 0 | 0 | #REF!
2.3 | Banking excavated earth in layers not exceeding 20 cm. in depth, breaking clods, watering, rolling each layer with ½ tonne roller, or wooden or steel rammers, and rolling every 3rd and top-most layer with power roller of minimum 8 tonnes and dressing up, in embankments for roads, flood banks, marginal banks, and guide banks etc., lead upto 50 m and lift upto 1.5 m. | [6 empty] | 0 | 0 | 0 | 0 | #REF!
2.3.1 | All kinds of soil | cum | 181.25 | 15723.8 | 50 | 340 |  | 2849938.75 | 9062.5 | 61625 | 0 | #REF!
[5 empty] | 50 | 340 |  | 0 | 0 | 0 | 0 | #REF!
2.6 | Earth work in excavation by mechanical means (Hydraulic excavator) / manual means over areas (exceeding 30cm in depth. 1.5m in width as well as 10 sqm on plan) including disposal of excavated earth, lead upto 50m and lift upto 1.5m, disposed earth to be levelled and neatly dressed. |  |  |  | 50 | 620 |  | 0 | 0 | 0 | 0 | #REF!
2.6.1 | All kinds of soil | cum | 129.35 | 3280.26 | 50 | 1960 |  | 424301.631 | 6467.5 | 253526 | 0 | #REF!
[5 empty] | 40 | 55.45 |  | 0 | 0 | 0 | 0 | #REF!
2.7 | Earth work in excavation by mechanical means (Hydraulic excavator) / manual means over areas (exceeding 30 cm in depth, 1.5 m in width as well as 10 sqm on plan) including disposal of excavated earth, lead upto 50 m and lift upto 1.5 m, disposed earth to be levelled and neatly dressed. |  |  |  | 45 | 69.85 |  | 0 | 0 | 0 | 0 | #REF!
2.7.1 | Ordinary rock | cum | 197.75 | 471.51 | 50 | 98.65 |  | 93241.1025 | 9887.5 | 19508.0375 | 0 | #REF!
[5 empty] | 40 | 55.45 |  | 0 | 0 | 0 | 0 | #REF!
2.8 | Earth work in excavation by mechanical means (Hydraulic excavator) / manual means in foundation trenches or drains (not exceeding 1.5 m in width or 10 sqm on plan) including dressing of sides and ramming of bottoms, lift upto 1.5 m, including getting out the excavated soil and disposal of surplus excavated soil as directed, within a lead of 50 m. |  |  |  | 45 | 70 |  | 0 | 0 | 0 | 0 | #REF!
2.8.1 | All kinds of soil. | cum | 130.8 | 939.05 | 50 | 100 |  | 122827.74 | 6540 | 13080 | 0 | #REF!
[5 empty] | 65 | 205 |  | 0 | 0 | 0 | 0 | #REF!
2.25 | Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundations etc. in layers not exceeding 20cm in depth, consolidating each deposited layer by ramming and watering, lead up to 50 m and lift upto 1.5 m. | cum | 83.8 | 190.34 | 50 | 360 |  | 15950.492 | 4190 | 30168 | 0 | #REF!
[5 empty] | 50 | 520 |  | 0 | 0 | 0 | 0 | #REF!
2.26 | Extra for every additional lift of 1.5 m or part thereof in excavation / banking excavated or stacked materials. |  |  |  | 40 | 520 |  | 0 | 0 | 0 | 0 | #REF!
2.26.2 | Ordinary or hard rock | cum | 62 | 207.36 | 30 | 600 |  | 12856.32 | 1860 | 37200 | 0 | #REF!
[5 empty] | 30 | 160 |  | 0 | 0 | 0 | 0 | #REF!
4.1 | Providing and laying in position cement concrete of specified grade excluding the cost of centering and shuttering - All work up to plinth level : |  |  |  | 60 | 140 |  | 0 | 0 | 0 | 0 | #REF!
4.1.8 | 1:4:8 (1 Cement : 4 coarse sand : 8 graded stone aggregate 40 mm nominal size). | cum | 3593.3 | 1729.14 |  |  |  | 6213318.762 | 0 | 0 | 0 | #REF!
[5 empty] | 500 | 4000 |  | 0 | 0 | 0 | 0 | #REF!
4.2 | Providing & laying cement concrete in retaining walls, return walls, walls (any thickness) including attached pilasters, columns, piers, abutments, pillars, posts, struts, buttresses, string or lacing courses, parapets, coping, bed blocks, anchor blocks, plain window sills, fillets, sunken floor,etc., up to floor five level, excluding the cost of centering, shuttering and finishing : |  |  |  | 750 | 8000 |  | 0 | 0 | 0 | 0 | #REF!
4.2.2 | 1:1½:3 (1 cement:1½ coarse sand:3 graded stone aggregate 20 mm nominal size). | cum | 5663.3 | 43.58 | 1000 | 20000 |  | 246806.614 | 5663300 | 113266000 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
5.9 | Centering and shuttering including strutting, propping etc. and removal of form for : |  |  |  | 250 | 2084 |  | 0 | 0 | 0 | 0 | #REF!
5.9.3 | Suspended floors, roofs, landings, balconies and access platform. | sqm | 311.2 | 73.35 | 250 | 3200 |  | 22826.52 | 77800 | 995840 | 0 | #REF!
5.9.16 | Edges of slabs and breaks in floors and walls. |  |  |  | 250 | 2496 |  | 0 | 0 | 0 | 0 | #REF!
5.9.16.1 | Under 20 cm wide | mtr | 99.45 | 185.76 | 250 | 2509 |  | 18473.832 | 24862.5 | 249520.05 | 0 | #REF!
[5 empty] | 250 | 2224 |  | 0 | 0 | 0 | 0 | #REF!
5.22 | Steel reinforcement for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete upto plinth level. |  |  |  | 300 | 3021.5 |  | 0 | 0 | 0 | 0 | #REF!
5.22.6 | Thermo-Mechanically Treated bars. | kg | 62.25 | 1809 | 50 | 445 |  | 112610.25 | 3112.5 | 27701.25 | 0 | #REF! | [35 empty] | 1
[5 empty] | 75 | 528 |  | 0 | 0 | 0 | 0 | #REF! | [36 empty] | 1
5.33 | Providing & laying in position machine batched and machine mixed design mix M-25 grade cement concrete for reinforced cement concrete work, using cement content as per approved design mix, including pumping of concrete to site of laying but excluding the cost of centering, shuttering, finishing and reinforcement, including admixtures in recommended proportions as per IS: 9103 to accelerate, retard setting of concrete, improve workability without impairing strength and durability as per direction of Engineer-in-charge. (Note :- Cement content considered in this item is @ 330 kg/cum. Excess/less cement used as per design mix is payable/recoverable separately). |  |  |  | 100 | 978 |  | 0 | 0 | 0 | 0 | #REF! | [37 empty] | 1
5.33.1 | All works upto plinth level. | cum | 5242.15 | 18.09 | 115 | 214 |  | 94830.4935 | 602847.25 | 1121820.1 | 0 | #REF! | [38 empty] | 1
[5 empty] | 135 | 318 |  | 0 | 0 | 0 | 0 | #REF! | [39 empty] | 1
6.1 | Brick work with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in foundation and plinth in: |  |  |  | 160 | 398 |  | 0 | 0 | 0 | 0 | #REF! | [40 empty] | 1
6.1.2 | Cement mortar 1:6 (1 cement : 6 coarse sand) | cum | 3316.55 | 394.28 | 185 | 478 |  | 1307649.334 | 613561.75 | 1585310.9 | 0 | #REF! | [41 empty] | 1
[5 empty] | 208 | 1096 |  | 0 | 0 | 0 | 0 | #REF! | [42 empty] | 1
7.1 | Random rubble masonry with hard stone in foundation and plinth including levelling up with cement concrete 1:6:12 (1 cement : 6 coarse sand : 12 graded stone aggregate 20mm nominal size) upto plinth level with : |  |  |  | 258 | 1457 |  | 0 | 0 | 0 | 0 | #REF! | [43 empty] | 1
7.1.1 | Cement mortar 1:6 (1 cement : 6 coarse sand). | cum | 3059.2 | 715.42 | 308 | 2185 |  | 2188612.864 | 942233.6 | 6684352 | 0 | #REF! | [44 empty] | 1
[8 empty] | 0 | 0 | 0 | 0 | #REF!
10.25 | Steel work welded in built up sections / framed work including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer using structural steel etc. as required. |  |  |  | 115 | 203.36 |  | 0 | 0 | 0 | 0 | #REF!
10.25.2 | In gratings, frames, guard bar, ladder, railings, brackets, gates and similar works. | kg | 77.9 | 630 | 135 | 365.25 |  | 49077 | 10516.5 | 28452.975 | 0 | #REF!
[5 empty] | 158 | 447.73 |  | 0 | 0 | 0 | 0 | #REF!
11.2 | Chequerred precast cement concrete tiles 22 mm thick in footpath & courtyard, jointed with neat cement slurry mixed with pigment to match the shade of tiles including rubbing and cleaning etc. complete, on 20 mm thick bed of cement mortar 1:4 (1 cement: 4 coarse sand). |  |  |  | 208 | 615.95 |  | 0 | 0 | 0 | 0 | #REF!
11.20.4 | Ordinary cement without any pigment. | sqm | 564.35 | 1948.61 | 258 | 718.325 |  | 1099698.0535 | 145602.3 | 405386.7138 | 0 | #REF!
[5 empty] | 308 | 802.431 |  | 0 | 0 | 0 | 0 | #REF!
13.1 | 12 mm cement plaster of mix : |  |  |  | 358 | 1188.04 |  | 0 | 0 | 0 | 0 | #REF!
13.1.2 | 1:6 (1 cement: 6 fine sand) | sqm | 112.5 | 1064 | 100 | 1440 |  | 119700 | 11250 | 162000 | 0 | #REF!
[5 empty] | 100 | 6800 |  | 0 | 0 | 0 | 0 | #REF!
13.33 | Pointing on stone work with cement mortar 1:3 (1 cement: 3 fine sand) : |  |  |  | 70 | 1068.43 |  | 0 | 0 | 0 | 0 | #REF!
13.33.2 | Raised and cut pointing | sqm | 201.85 | 1355.04 | 70 | 1088.43 |  | 273514.824 | 14129.5 | 219699.5955 | 0 | #REF!
[5 empty] | 70 | 1104.43 |  | 0 | 0 | 0 | 0 | #REF!
13.43 | Applying one coat of water thinnable cement primer of approved brand and manufacture on wall surface : |  |  |  | 75 | 386 |  | 0 | 0 | 0 | 0 | #REF!
13.43.1 | Water thinnable cement primer. | sqm | 27.55 | 1064 | 500 | 14400 |  | 29313.2 | 13775 | 396720 | 0 | #REF!
[5 empty] | 500 | 22400 |  | 0 | 0 | 0 | 0 | #REF!
13.61 | Painting with synthetic enamel paint of approved brand and manufacture to give an even shade : |  |  |  | 150 | 750 |  | 0 | 0 | 0 | 0 | #REF!
13.61.1 | Two or more coats on new work. | sqm | 53.85 | 25.2 | 150 | 3500 |  | 1357.02 | 8077.5 | 188475 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
16.1 | Preparation & consolidation of sub grade with power road roller of 8 to 12 tonne capacity after excavating earth to an average of 22.5 cm. depth, dressing to camber and consolidating with road roller including making good the undulations etc. and re-rolling the sub grade and disposal of surplus earth with lead upto 50 metres. | sqm | 61.25 | 14499.86 | 15200 | 1500 |  | 888116.425 | 931000 | 91875 | 0 | #REF!
[8 empty] | 0 | 0 | 0 | 0 | #REF!
16.42 (Modified) | Cement concrete M-20 in pavements, laid to required slope and camber in panels as required including consolidation finishing and tamping complete. | cum | 4502.55 | 115.13 | 110 |  |  | 518378.5815 | 495280.5 | 0 | 0 | #REF!
[5 empty] | 45 | 893.343 |  | 0 | 0 | 0 | 0 | #REF! | [34 empty] | 1.05
16.43 | Providing & laying design mix cement concrete of M-30 grade, in roads / taxi tracks / runways, using cement content as per design mix, using coarse sand and graded stone aggregate of 40 mm nominal size in appropriate proportions as per approved & specified design criteria, providing dowel bars with sleeve / tie bars wherever required, laying at site, spreading and compacting, mechanically by using needle and surface vibrators, levelling to required slope / camber, finishing with required texture, including steel form work with sturdy M.S. channel sections, curing, making provision for contraction / expansion, construction & longitudinal joints (10 mm wide x 50 mm deep) by groove cutting machine, providing and filling joints with approved joint filler and sealants, complete all as per direction of Engineer-in-charge (Item of joint fillers, sealants, dowel bars with sleeve / tie bars to be paid separately) Note:- Cement content considered in M-30 is @ 340 kg/cum. Excess / less cement used as per design mix is payable / recoverable separately. |  |  |  | 216.5 | 1084.9 |  | 0 | 0 | 0 | 0 | #REF!
16.43.2 | Cement concrete manufactured in automatic batching plant (RMC plant) i/c transportation to site in transit mixer. | cum | 5967.95 | 1228.07 | 216.5 | 1084.9 |  | 7329060.3565 | 1292061.175 | 6474628.955 | 0 | #REF!
[5 empty] | 15 | 35 |  | 0 | 0 | 0 | 0 | #REF!
16.46 | Providing & laying in position bitumen hot sealing compound for expansion joints etc. | Per cm depth per cm width |  |  | 50 | 204.63 |  | 0 | 0 | 0 | 0 | #REF!
16.46.1 | Using grade ‘A’ sealing compound. | per m length | 1.65 | 1364.52 | 38 | 91.045 |  | 2251.458 | 62.7 | 150.2242 | 0 | #REF!
[5 empty] | 15 | 33.75 |  | 0 | 0 | 0 | 0 | #REF!
16.68 | Providing & laying 60mm thick factory made cement concrete interlocking paver block of M -30 grade made by block making machine with strong vibratory compaction, of approved size, design & shape, laid in required colour and pattern over and including 50mm thick compacted bed of fine sand, filling the joints with fine sand etc. all complete as per the direction of Engineer-in-charge. | sqm | 536.65 | 4364.12 | 52.5 | 169.785 |  | 2342004.998 | 28174.125 | 91115.1202 | 0 | #REF!
[5 empty] | 1000 | 3234 |  | 0 | 0 | 0 | 0 | #REF!
18.12 | Providing & fixing GI pipes complete with GI fittings including trenching and refilling etc. |  |  |  | 25 | 45.34 |  | 0 | 0 | 0 | 0 | #REF!
| External work |  |  |  | 400 |  |  | 0 | 0 | 0 | 0 | #REF!
18.12.3 | 25 mm dia. nominal bore | metre | 209.4 | 145 | 95 | 95.205 |  | 30363 | 19893 | 19935.927 | 0 | #REF!
[5 empty] | 470 | 3504 |  | 0 | 0 | 0 | 0 | #REF!
18.38 | Painting G.I. pipes and fittings with synthetic enamel white paint with two coats over a ready mixed priming coat, both of approved quality for new work : |  |  |  | 110 | 982.5 |  | 0 | 0 | 0 | 0 | #REF! | 7.4 |  | 0.514 | 0.291 | 0.426 | 1.85
18.38.3 | 25 mm diameter pipe | metre | 11.4 | 145 |  |  |  | 1653 | 0 | 0 | 0 | #REF! |  |  | 0.1575 |  |  |  |  | 0.8925
[8 empty] | 0 | 0 | 0 | 0
18.41 | Providing & filling sand of grading zone V or coarser grade all-round the G.I. pipes in external work. | [6 empty] | 0 | 0 | 0 | 0
18.41.3 | 25 mm diameter pipe | metre | 56.95 | 145 |  |  |  | 8257.75 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
18.46 | Providing & fixing G.I. Union in G.I. pipe including cutting and threading the pipe and making long screws etc. complete (New work) | [6 empty] | 0 | 0 | 0 | 0
18.46.3 | 25 mm nominal bore | each | 307.7 | 5 |  |  |  | 1538.5 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
19.19 | Providing and fixing in position pre-cast R.C.C. manhole cover and frame of required shape and approved quality. | [6 empty] | 0 | 0 | 0 | 0 |  | UNIT
19.19.4 | EHD - 35 | [6 empty] | 0 | 0 | 0 | 0 |  | BAGS
19.19.4.1 | Circular shape 560 mm internal dia. | each | 1529.65 | 27 |  |  |  | 41300.55 | 0 | 0 | 0 |  | MT
[8 empty] | 0 | 0 | 0 | 0 | 2648 | CUM | 2648.25
23.1 | Trenching in ordinary soil up to a depth of 60cm including removal and stacking of serviceable materials and then disposing of surplus soil, by spreading and neatly leveling within a lead of 50m and making up the trenched area to proper levels by filling with earth or earth mixed with sludge or/and manure before and after flooding trench with water (excluding cost of imported earth, sludge or manure). | cum | 30.9 | 157.53 |  |  |  | 4867.677 | 0 | 0 | 0 | #REF! | CUM
[8 empty] | 0 | 0 | 0 | 0 | #REF! | CUM
23.2 | Supplying & stacking of good earth at site including royalty and carriage up to 1 km (earth measured in stacks will be reduced by 20% for payment). | cum | 260.7 | 78.77 |  |  |  | 20535.339 | 0 | 0 | 0 | #REF! | LTR
[8 empty] | 0 | 0 | 0 | 0 | #REF! | NOS
23.4 | Supplying & stacking at site dump manure from approved source, including carriage up to 1 km (manure measured in stacks will be reduced by 8% for payment) : | [6 empty] | 0 | 0 | 0 | 0 | #REF! | CUM
23.4.3 | Screened through sieve of I.S. designation 4.75mm | cum | 164.1 | 19.69 |  |  |  | 3231.129 | 0 | 0 | 0 | #REF! | CUM
[8 empty] | 0 | 0 | 0 | 0 | #REF! | NOS
23.5 | Rough dressing the trenched ground including breaking clods. | 100 sqm | 0.5985 | 1050.22 |  |  |  | 628.5567 | 0 | 0 | 0 | #REF! | CFT
[8 empty] | 0 | 0 | 0 | 0 | #REF! | KG
23.7 | Fine dressing of the ground | 100 sqm | 1.459 | 1050.22 |  |  |  | 1532.271 | 0 | 0 | 0 | #REF! | LTR
[8 empty] | 0 | 0 | 0 | 0 | #REF! | MT
23.9 | Mixing earth & sludge or manure in the required proportion specified or directed by the Officer-in-charge. | cum | 14.35 | 98.46 |  |  |  | 1412.901 | 0 | 0 | 0 | #REF! | KG
[8 empty] | 0 | 0 | 0 | 0 | #REF! | SQM
23.10 | Grassing with selection No.1 grass including watering and maintenance of the lawn for 30 days or more till the grass forms a thick lawn, free from weeds and fit for mowing including supplying good earth, if needed (the good earth shall be paid for separately). | [6 empty] | 0 | 0 | 0 | 0 | #REF! | CUM
23.10.1 | In rows 5 cm apart in both directions. | 100 sqm | 7.0025 | 1050.22 |  |  |  | 7354.1656 | 0 | 0 | 0 | #REF! | RM
[8 empty] | 0 | 0 | 0 | 0 | #REF! | RM
24.1 | Boring/drilling bore well of required dia for casing/ strainer pipe, by suitable method prescribed in IS: 2800 (part I), including collecting samples from different strata, preparing and submitting strata chart/bore log, including hire & running charges of all equipments, tools, plants & machineries required for the job, all complete as per direction of Engineer–in-charge, upto 90 metre depth below ground level. | [6 empty] | 0 | 0 | 0 | 0 | #REF! | RM
24.1.2 | Rocky strata including Boulders. | [6 empty] | 0 | 0 | 0 | 0 | #REF! | RM
24.1.2.1 | 300 mm dia. | mtr | 797.9 | 220.5 |  |  |  | 175936.95 | 0 | 0 | 0 | #REF! | RM
[8 empty] | 0 | 0 | 0 | 0 | #REF! | RM
24.3 | Supplying, assembling, lowering and fixing in vertical position in bore well, unplasticized PVC medium well casing (CM) pipe of required dia, conforming to IS: 12818, including required hire and labour charges, fittings & accessories etc. all complete, for all depths, as per direction of Engineer –in-charge. | [6 empty] | 0 | 0 | 0 | 0 | #REF! | RM
24.3.1 | 100 mm nominal size dia. | mtr | 452 | 13.5 |  |  |  | 6102 | 0 | 0 | 0 | #REF! | RM
24.3.2 | 150 mm nominal size dia. | mtr | 539.15 | 159.3 |  |  |  | 85886.595 | 0 | 0 | 0 | #REF! | RM
[8 empty] | 0 | 0 | 0 | 0 | #REF! | RM
24.4 | Supplying, assembling, lowering and fixing in vertical position in bore well unplasticized PVC medium well screen (RMS) pipes with ribs, conforming to IS: 12818, including hire & labour charges, fittings & accessories etc. all complete, for all depths, as per direction of Engineer-in-charge. | [6 empty] | 0 | 0 | 0 | 0
24.4.2 | 150 mm nominal size dia. | mtr | 544.15 | 72 |  |  |  | 39178.8 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
24.5 | Supplying, filling, spreading & leveling stone boulders of size range 5 cm to 20 cm, in recharge pit, in the required thickness, for all leads & lifts, all complete as per direction of Engineer-in-charge. | cum | 459.05 | 23.31 |  |  |  | 10700.4555 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
24.6 | Supplying, filling, spreading & leveling gravels of size range 5 mm to 10 mm, in the recharge pit, over the existing layer of boulders, in required thickness, for all leads & lifts, all complete as per direction of Engineer-in-charge. | cum | 828.45 | 23.31 |  |  |  | 19311.1695 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
24.7 | Supplying, filling, spreading & leveling coarse sand of size range 1.5 mm to 2 mm in recharge pit, in required thickness over gravel layer, for all leads & lifts, all complete as per direction of Engineer –in-charge. | cum | 799.4 | 23.31 |  |  |  | 18634.014 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
24.8 | Gravel packing in tubewell construction in accordance with IS: 4097, including providing gravel fine / medium / coarse, in required grading & sizes as per actual requirement, all complete as per direction of Engineer-in-charge. | cum | 842.8 | 10.35 |  |  |  | 8722.98 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
24.13 | Providing &fixing suitable size threaded mild steel cap or spot welded plate to the top of bore well housing/ casing pipe, removable as per requirement, all complete for borewell of: | [6 empty] | 0 | 0 | 0 | 0
24.13.2 | 150 mm dia | each | 182.95 | 9 |  |  |  | 1646.55 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
23.14 | Digging holes in ordinary soil and refilling the same with the excavated earth mixed with manure or sludge in the ratio of 2:1 by volume (2 parts of stacked volume of earth after reduction by 20% : 1 part of stacked volume of manure after reduction by 8%) flooding with water, dressing including removal of rubbish and surplus earth, if any, with all leads and lifts (cost of manure, sludge or extra good earth if needed to be paid for separately) : | [6 empty] | 0 | 0 | 0 | 0
23.14.2 | Holes 90 cm dia, and 90 cm deep. | each | 80.2 | 50 |  |  |  | 4010 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
24.15 | Providing & fixing Bail plug / Bottom plug of required dia to the bottom of pipe assembly of tubewell as per IS:2800 (part I). | [6 empty] | 0 | 0 | 0 | 0
24.15.2 | 150 mm dia | each | 206.1 | 9 |  |  |  | 1854.9 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
23.16 | Providing & fixing M.S. flat iron tree guard 60 cm dia. and 2 m high, above ground consisting 4 nos. 25 x 6 mm, 2.25 m long and 8 nos. 25 x 3 mm 2 m long verticals M.S. flats, riveted to 3 nos. 25 x 6 mm M.S. flat iron rings in two halves, fixing together at site with required six numbers of 8 mm dia. and 30 mm long bolts, including painting two coats with synthetic enamel paint of approved brand and manufacture over a coat of primer. One name plate of 1 mm thick M.S. sheet of size 250x100 mm shall be welded to the tree guard near the middle height and lettered CPWD / PWD/ any other approved name. The tree guard shall be suitably fixed to the ground by embedding four legs of tree guard in pits of suitable dia and to a depth of 25 cm, refilling the pits with soil and ramming, complete in all respect as per satisfaction and direction of Officer-in-charge. | each | 2580.6 | 50 |  |  |  | 129030 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
23.28 | Preparation of mounds of various size and shape by available excavated / supplied earth in layers not exceeding 20 cm in depth, breaking clods, watering of each layer, dressing etc., lead upto 50 meter and lift upto 1.5 m complete as per direction of Officer-in-charge. | cum | 178.7 | 36 |  |  |  | 6433.2 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
(MR) | Supply & Planting of Trees | [6 empty] | 0 | 0 | 0 | 0
| Ashoka Tree | each | 255.5 | 50 |  |  |  | 12775 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
(MR) | Providing & fixing in position 50 mm thic prefabricated SFRC panels in position for boundry wall properly embedded and in plumb as per direciton of Engineer-in-charge. | sqm | 745.65 | 761.31 |  |  |  | 567670.8015 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
(AR) | Providing & fixing ball valve with lever : | [6 empty] | 0 | 0 | 0 | 0
| 25 mm nominal bore | each | 250 | 13 |  |  |  | 3250 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
(AR) | Providing & installing sprinklers for irrigation including 15 metre PVC pipe to the entire satisfaction of Engineer-in-charge. | each | 2500 | 4 |  |  |  | 10000 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
(AR) | Providing & laying 60mm thick factory made cement concrete grass crete block of M -30 grade made by block making machine with strong vibratory compaction, of approved size, design & shape, laid in required colour and pattern over and including 50mm thick compacted bed of fine sand, filling the joints with fine sand etc. all complete as per the direction of Engineer-in-charge. | sqm | 536.65 | 294.95 |  |  |  | 158284.9175 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
NS (Based on DSR 16.61) | Providing Retro-reflective regulatory sign board of required size made out of 2mm thick aluminium sheet, face to be fully covered with high intensity encapsulated lens type retro-reflective sheeting as approved by Engineer-in-charge. Letter, symbols, borders etc. will be as per direction of Engineer-in-charge with required colour scheme on the boards and with the high intensity grade A. The aluminium sheet to be riveted to M.S. frame of angle iron of size 40x40x4mm. The boards will be fixed to 1 No. 50x50mm square post made of MS angle 50x50x4mm, 3m long welded to the frame with adequate anti-theft arrangement. Steel work to be painted with two or more coats of synthetic enamel paint over an under coat (primer) and back side of aluminium sheet to be painted with two or more coats of epoxy paint including appropriate priming coat complete in all respects as per direction of Engineer-in-charge. | sqm | 7691.55 | 15.24 |  |  |  | 117219.222 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
NS (DSR Based) | Providing and fixing in position white ceramic glazed tiles of size 100 mm x 100 mm with printed house numbers in desired combinations. | each | 14.5 | 21208 |  |  |  | 307516 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
| Under Ground Tank (1224 KL capacity) | each | 12350160 | 1 |  |  |  | 12350160 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
| Total | [6 empty] | 0 | 0 | 0 | 0
| Boundary Wall & Steel Gate | [6 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
2.8 | Earth work in excavation by mechanical means (Hydraulic excavator) / manual means in foundation trenches or drains (not exceeding 1.5 m in width or 10 sqm on plan) including dressing of sides and ramming of bottoms, lift upto 1.5 m, including getting out the excavated soil and disposal of surplus excavated soil as directed, within a lead of 50 m. | [6 empty] | 0 | 0 | 0 | 0
2.8.1 | All kinds of soil. | cum | 130.8 | 719.02 |  |  |  | 94047.816 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
2.25 | Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundations etc. in layers not exceeding 20cm in depth, consolidating each deposited layer by ramming and watering, lead up to 50 m and lift upto 1.5 m. | cum | 83.8 | 190.34 |  |  |  | 15950.492 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
4.1 | Providing and laying in position cement concrete of specified grade excluding the cost of centering and shuttering - All work up to plinth level : | [6 empty] | 0 | 0 | 0 | 0
4.1.8 | 1:4:8 (1 Cement : 4 coarse sand : 8 graded stone aggregate 40 mm nominal size). | cum | 3593.3 | 84.59 |  |  |  | 303957.247 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
4.2 | Providing and laying cement concrete in retaining walls, return walls, walls (any thickness) including attached pilasters, columns, piers, abutments, pillars, posts, struts, buttresses, string or lacing courses, parapets, coping, bed blocks, anchor blocks, plain window sills, fillets, sunken floor,etc., up to floor five level, excluding the cost of centering, shuttering and finishing : | [6 empty] | 0 | 0 | 0 | 0
4.2.2 | 1:1½:3 (1 cement:1½ coarse sand:3 graded stone aggregate 20 mm nominal size). | cum | 5663.3 | 33.9 |  |  |  | 191985.87 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
7.1 | Random rubble masonry with hard stone in foundation and plinth including levelling up with cement concrete 1:6:12 (1 cement : 6 coarse sand : 12 graded stone aggregate 20mm nominal size) upto plinth level with : | [6 empty] | 0 | 0 | 0 | 0
7.1.1 | Cement mortar 1:6 (1 cement : 6 coarse sand). | cum | 3059.2 | 715.42 |  |  |  | 2188612.864 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
10.25 | Steel work welded in built up sections/ framed work including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer using structural steel etc. as required. | [6 empty] | 0 | 0 | 0 | 0
10.25.2 | In gratings, frames, guard bar, ladder, railings, brackets, gates and similar works. | kg | 77.9 | 630 |  |  |  | 49077 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
13.33 | Pointing on stone work with cement mortar 1:3 (1 cement: 3 fine sand) : | [6 empty] | 0 | 0 | 0 | 0
13.33.2 | Raised and cut pointing | sqm | 201.85 | 1355.04 |  |  |  | 273514.824 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
13.61 | Painting with synthetic enamel paint of approved brand and manufacture to give an even shade : | [6 empty] | 0 | 0 | 0 | 0
13.61.1 | Two or more coats on new work. | sqm | 53.85 | 25.2 |  |  |  | 1357.02 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
(MR) | Providing and fixing in position 65 mm thic prefabricated SFRC panels in position for boundry wall properly embedded and in plumb as per direciton of Engineer-in-charge. | sqm | 745.65 | 761.31 |  |  |  | 567670.8015 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
| TOTAL | [6 empty] | 0 | 0 | 0 | 0
Road, Path, Paver, Chequred, Tiles etc. | [7 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
2.3 | Banking excavated earth in layers not exceeding 20 cm. in depth, breaking clods, watering, rolling each layer with ½ tonne roller, or wooden or steel rammers, and rolling every 3rd and top-most layer with power roller of minimum 8 tonnes and dressing up, in embankments for roads, flood banks, marginal banks, and guide banks etc., lead upto 50 m and lift upto 1.5 m. | [6 empty] | 0 | 0 | 0 | 0
2.3.1 | All kinds of soil | cum | 181.25 | 15723.8 |  |  |  | 2849938.75 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
2.6 | Earth work in excavation by mechanical means (Hydraulic excavator) / manual means over areas (exceeding 30cm in depth. 1.5m in width as well as 10 sqm on plan) including disposal of excavated earth, lead upto 50m and lift upto 1.5m, disposed earth to be levelled and neatly dressed. | [6 empty] | 0 | 0 | 0 | 0
2.6.1 | All kinds of soil | cum | 129.35 | 3280.26 |  |  |  | 424301.631 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
4.1 | Providing & laying in position cement concrete of specified grade excluding the cost of centering and shuttering - All work up to plinth level : | [6 empty] | 0 | 0 | 0 | 0
4.1.8 | 1:4:8 (1 Cement : 4 coarse sand : 8 graded stone aggregate 40 mm nominal size). | cum | 3593.3 | 1565.11 |  |  |  | 5623909.763 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
11.2 | Chequerred precast cement concrete tiles 22 mm thick in footpath & courtyard, jointed with neat cement slurry mixed with pigment to match the shade of tiles including rubbing and cleaning etc. complete, on 20 mm thick bed of cement mortar 1:4 (1 cement: 4 coarse sand). | [6 empty] | 0 | 0 | 0 | 0
11.20.4 | Ordinary cement without any pigment. | sqm | 564.35 | 1948.61 |  |  |  | 1099698.0535 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
16.1 | Preparation & consolidation of sub grade with power road roller of 8 to 12 tonne capacity after excavating earth to an average of 22.5 cm. depth, dressing to camber and consolidating with road roller including making good the undulations etc. and re-rolling the sub grade and disposal of surplus earth with lead upto 50 metres. | sqm | 61.25 | 14499.86 |  |  |  | 888116.425 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
16.42 (Modified) | Cement concrete M-20 in pavements, laid to required slope and camber in panels as required including consolidation finishing and tamping complete. | cum | 4502.55 | 115.13 |  |  |  | 518378.5815 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
16.43 | Providing & laying design mix cement concrete of M-30 grade, in roads / taxi tracks / runways, using cement content as per design mix, using coarse sand and graded stone aggregate of 40 mm nominal size in appropriate proportions as per approved & specified design criteria, providing dowel bars with sleeve / tie bars wherever required, laying at site, spreading and compacting, mechanically by using needle and surface vibrators, levelling to required slope / camber, finishing with required texture, including steel form work with sturdy M.S. channel sections, curing, making provision for contraction / expansion, construction & longitudinal joints (10 mm wide x 50 mm deep) by groove cutting machine, providing and filling joints with approved joint filler and sealants, complete all as per direction of Engineer-in-charge (Item of joint fillers, sealants, dowel bars with sleeve / tie bars to be paid separately) Note:- Cement content considered in M-30 is @ 340 kg/cum. Excess / less cement used as per design mix is payable / recoverable separately. | [6 empty] | 0 | 0 | 0 | 0
16.43.2 | Cement concrete manufactured in automatic batching plant (RMC plant) i/c transportation to site in transit mixer. | cum | 5967.95 | 1228.07 |  |  |  | 7329060.3565 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
16.46 | Providing & laying in position bitumen hot sealing compound for expansion joints etc. | Per cm depth per cm width per m length | [5 empty] | 0 | 0 | 0 | 0
16.46.1 | Using grade ‘A’ sealing compound. |  | 1.65 | 1364.52 |  |  |  | 2251.458 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
16.68 | Providing & laying 60mm thick factory made cement concrete interlocking paver block of M -30 grade made by block making machine with strong vibratory compaction, of approved size, design & shape, laid in required colour and pattern over and including 50mm thick compacted bed of fine sand, filling the joints with fine sand etc. all complete as per the direction of Engineer-in-charge. | sqm | 536.65 | 4364.12 |  |  |  | 2342004.998 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
| TOTAL | [6 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Toe Wall & Retaining Wall | [7 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
2.8 | Earth work in excavation by mechanical means (Hydraulic excavator) / manual means in foundation trenches or drains (not exceeding 1.5 m in width or 10 sqm on plan) including dressing of sides and ramming of bottoms, lift upto 1.5 m, including getting out the excavated soil and disposal of surplus excavated soil as directed, within a lead of 50 m. | [6 empty] | 0 | 0 | 0 | 0
2.8.1 | All kinds of soil. | cum | 130.8 | 220.03 |  |  |  | 28779.924 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
4.1 | Providing and laying in position cement concrete of specified grade excluding the cost of centering and shuttering - All work up to plinth level : | [6 empty] | 0 | 0 | 0 | 0
4.1.8 | 1:4:8 (1 Cement : 4 coarse sand : 8 graded stone aggregate 40 mm nominal size). | cum | 3593.3 | 49.47 |  |  |  | 177760.551 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
4.2 | Providing & laying cement concrete in retaining walls, return walls, walls (any thickness) including attached pilasters, columns, piers, abutments, pillars, posts, struts, buttresses, string or lacing courses, parapets, coping, bed blocks, anchor blocks, plain window sills, fillets, sunken floor,etc., up to floor five level, excluding the cost of centering, shuttering and finishing : | [6 empty] | 0 | 0 | 0 | 0
4.2.2 | 1:1½:3 (1 cement:1½ coarse sand:3 graded stone aggregate 20 mm nominal size). | cum | 5663.3 | 9.68 |  |  |  | 54820.744 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
6.1 | Brick work with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in foundation and plinth in: | [6 empty] | 0 | 0 | 0 | 0
6.1.2 | Cement mortar 1:6 (1 cement : 6 coarse sand) | cum | 3316.55 | 301.22 |  |  |  | 999011.191 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
13.1 | 12 mm cement plaster of mix : | [6 empty] | 0 | 0 | 0 | 0
13.1.2 | 1:6 (1 cement: 6 fine sand) | sqm | 112.5 | 1064 |  |  |  | 119700 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
13.43 | Applying one coat of water thinnable cement primer of approved brand and manufacture on wall surface : | [6 empty] | 0 | 0 | 0 | 0
13.43.1 | Water thinnable cement primer. | sqm | 27.55 | 1064 |  |  |  | 29313.2 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
| TOTAL | [6 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Directional Boards & House Numbering | [7 empty] | 0 | 0 | 0 | 0
NS (Based on DSR 16.61) | Providing Retro-reflective regulatory sign board of required size made out of 2mm thick aluminium sheet, face to be fully covered with high intensity encapsulated lens type retro -reflective sheeting as approved by Engineer-in-charge . Letter, symbols, borders etc. will be as per direction of Engineer-in-charge with required colour scheme on the boards and with the high intensity grade A. The aluminium sheet to be riveted to M.S. frame of angle iron of size 40x40x4mm. The boards will be fixed to 1 No. 50x50mm square post made of M.S. angle 50x50x4mm, 3m long welded to the frame with adequate anti-theft arrangement. Steel work to be painted with two or more coats of synthetic enamel paint over an under coat (primer) and back side of aluminium sheet to be painted with two or more coats of epoxy paint including appropriate priming coat complete in all respects as per direction of Engineer-in-charge. | sqm | 7691.55 | 15.24 |  |  |  | 117219.222 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
NS (DSR Based) | Providing and fixing in position white ceramic glazed tiles of size 100 mm x 100 mm with printed house numbers in desired combinations. | each | 14.5 | 21208 |  |  |  | 307516 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
| TOTAL | [6 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Rain Water Harwesting | [7 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
2.7 | Earth work in excavation by mechanical means (Hydraulic excavator) / manual means over areas (exceeding 30 cm in depth, 1.5 m in width as well as 10 sqm on plan) including disposal of excavated earth, lead upto 50 m and lift upto 1.5 m, disposed earth to be levelled and neatly dressed. | [6 empty] | 0 | 0 | 0 | 0
2.7.1 | Ordinary rock | cum | 197.75 | 471.51 |  |  |  | 93241.1025 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
2.26 | Extra for every additional lift of 1.5 m or part thereof in excavation / banking excavated or stacked materials. | [6 empty] | 0 | 0 | 0 | 0
2.26.2 | Ordinary or hard rock | cum | 62 | 207.36 |  |  |  | 12856.32 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
4.1 | Providing and laying in position cement concrete of specified grade excluding the cost of centering and shuttering - All work up to plinth level : | [6 empty] | 0 | 0 | 0 | 0
4.1.8 | 1:4:8 (1 Cement : 4 coarse sand : 8 graded stone aggregate 40 mm nominal size) | cum | 3593.3 | 29.97 |  |  |  | 107691.201 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
5.9 | Centering and shuttering including strutting, propping etc. and removal of form for : | [6 empty] | 0 | 0 | 0 | 0
5.9.3 | Suspended floors, roofs, landings, balconies and access platform. | sqm | 311.2 | 73.35 |  |  |  | 22826.52 | 0 | 0 | 0
5.9.16 | Edges of slabs and breaks in floors and walls. | [6 empty] | 0 | 0 | 0 | 0
5.9.16.1 | Under 20 cm wide | mtr | 99.45 | 185.76 |  |  |  | 18473.832 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
5.22 | Steel reinforcement for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete upto plinth level. | [6 empty] | 0 | 0 | 0 | 0
5.22.6 | Thermo-Mechanically Treated bars. | kg | 62.25 | 1809 |  |  |  | 112610.25 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
5.33 | Providing & laying in position machine batched and machine mixed design mix M-25 grade cement concrete for reinforced cement concrete work, using cement content as per approved design mix, including pumping of concrete to site of laying but excluding the cost of centering, shuttering, finishing and reinforcement, including admixtures in recommended proportions as per IS: 9103 to accelerate, retard setting of concrete, improve workability without impairing strength and durability as per direction of Engineer-in-charge. (Note :- Cement content considered in this item is @ 330 kg/cum. Excess/less cement used as per design mix is payable/recoverable separately). | [6 empty] | 0 | 0 | 0 | 0
5.33.1 | All works upto plinth level. | cum | 5242.15 | 18.09 |  |  |  | 94830.4935 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
6.1 | Brick work with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in foundation and plinth in: | [6 empty] | 0 | 0 | 0 | 0
6.1.2 | Cement mortar 1:6 (1 cement : 6 coarse sand) | cum | 3316.55 | 93.06 |  |  |  | 308638.143 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
19.19 | Providing and fixing in position pre-cast R.C.C. manhole cover and frame of required shape and approved quality. | [6 empty] | 0 | 0 | 0 | 0
19.19.4 | EHD - 35 | [6 empty] | 0 | 0 | 0 | 0
19.19.4.1 | Circular shape 560 mm internal dia. | each | 1529.65 | 27 |  |  |  | 41300.55 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
24.1 | Boring/drilling bore well of required dia for casing/ strainer pipe, by suitable method prescribed in IS: 2800 (part I), including collecting samples from different strata, preparing and submitting strata chart/bore log, including hire & running charges of all equipments, tools, plants & machineries required for the job, all complete as per direction of Engineer–in-charge, upto 90 metre depth below ground level. | [6 empty] | 0 | 0 | 0 | 0
24.1.2 | Rocky strata including Boulders. | [6 empty] | 0 | 0 | 0 | 0
24.1.2.1 | 300 mm dia. | mtr | 797.9 | 220.5 |  |  |  | 175936.95 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
24.3 | Supplying, assembling, lowering and fixing in vertical position in bore well, unplasticized PVC medium well casing (CM) pipe of required dia, conforming to IS: 12818, including required hire and labour charges, fittings & accessories etc. all complete, for all depths, as per direction of Engineer –in-charge. | [6 empty] | 0 | 0 | 0 | 0
24.3.1 | 100 mm nominal size dia. | mtr | 452 | 13.5 |  |  |  | 6102 | 0 | 0 | 0
24.3.2 | 150 mm nominal size dia. | mtr | 539.15 | 159.3 |  |  |  | 85886.595 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
24.4 | Supplying, assembling, lowering and fixing in vertical position in bore well unplasticized PVC medium well screen (RMS) pipes with ribs, conforming to IS: 12818, including hire & labour charges, fittings & accessories etc. all complete, for all depths, as per direction of Engineer-in-charge. | [6 empty] | 0 | 0 | 0 | 0
24.4.2 | 150 mm nominal size dia. | mtr | 544.15 | 72 |  |  |  | 39178.8 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
24.5 | Supplying, filling, spreading & leveling stone boulders of size range 5 cm to 20 cm, in recharge pit, in the required thickness, for all leads & lifts, all complete as per direction of Engineer-in-charge. | cum | 459.05 | 23.31 |  |  |  | 10700.4555 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
24.6 | Supplying, filling, spreading & leveling gravels of size range 5 mm to 10 mm, in the recharge pit, over the existing layer of boulders, in required thickness, for all leads & lifts, all complete as per direction of Engineer-in-charge. | cum | 828.45 | 23.31 |  |  |  | 19311.1695 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
24.7 | Supplying, filling, spreading & leveling coarse sand of size range 1.5 mm to 2 mm in recharge pit, in required thickness over gravel layer, for all leads & lifts, all complete as per direction of Engineer –in-charge. | cum | 799.4 | 23.31 |  |  |  | 18634.014 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
24.8 | Gravel packing in tubewell construction in accordance with IS: 4097, including providing gravel fine / medium / coarse, in required grading & sizes as per actual requirement, all complete as per direction of Engineer-in-charge. | cum | 842.8 | 10.35 |  |  |  | 8722.98 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
24.13 | Providing &fixing suitable size threaded mild steel cap or spot welded plate to the top of bore well housing/ casing pipe, removable as per requirement, all complete for borewell of: | [6 empty] | 0 | 0 | 0 | 0
24.13.2 | 150 mm dia | each | 182.95 | 9 |  |  |  | 1646.55 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
24.15 | Providing & fixing Bail plug / Bottom plug of required dia to the bottom of pipe assembly of tubewell as per IS:2800 (part I). | [6 empty] | 0 | 0 | 0 | 0
24.15.2 | 150 mm dia | each | 206.1 | 9 |  |  |  | 1854.9 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
| TOTAL | [6 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
Sample Under Ground Water Tank including Pump Room | [7 empty] | 0 | 0 | 0 | 0
| (Capacity 5,30,000 litres) | [6 empty] | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
2.6 | Earth work in excavation by mechanical means (Hydraulic excavator) / manual means over areas (exceeding 30cm in depth. 1.5m in width as well as 10sqm on plan) including disposal of excavated earth, lead upto 50m and lift upto 1.5m, disposed earth to be levelled and neatly dressed. | [6 empty] | 0 | 0 | 0 | 0
2.6.1 | All kinds of soil. | cum | 129.35 | 1175.7 |  |  |  | 152076.795 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
2.25 | Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundations etc. in layers not exceeding 20 cm in depth : consolidating each deposited layer by ramming and watering, lead up to 50 m and lift upto 1.5 m. | cum | 83.8 | 472.843 |  |  |  | 39624.2434 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
2.26 | Extra for every additional lift of 1.5 m or part thereof in : | [6 empty] | 0 | 0 | 0 | 0
2.26.1 | All kinds of soil. | cum | 34.6 | 753.9695 |  |  |  | 26087.3447 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
2.7 | Earth work in excavation by mechanical means (Hydraulic excavator) / manual means over areas (exceeding 30cm in depth, 1.5m in width as well as 10sqm on plan) including disposal of excavated earth, lead upto 50m & lift upto 1.5m, disposed earth to be levelled and neatly dressed. | [6 empty] | 0 | 0 | 0 | 0
2.7.1 | Ordinary rock | cum | 197.75 | 130.63 |  |  |  | 25832.0825 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
| CEMENT CONCRETE (CAST-IN-SITU) | [6 empty] | 0 | 0 | 0 | 0
4.1 | Providing and laying in position cement concrete of specified grade excluding the cost of centring and shuttering - All work upto plinth level. | [6 empty] | 0 | 0 | 0 | 0
4.1.9 | 1:4:8 (1 cement : 4 corase sand : 8 graded stone aggregate 40 mm nominal size) | cum | 3331.25 | 32.391 |  |  |  | 107902.5187 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
| FORM WORK | [6 empty] | 0 | 0 | 0 | 0
5.9 | Centring and shuttering including strutting, propping etc. and removal form for : | [6 empty] | 0 | 0 | 0 | 0
5.9.1 | Foundations, footings, bases of columns etc. for mass concrete. | sqm | 166.9 | 29.64 |  |  |  | 4946.916 | 0 | 0 | 0
5.9.2 | Walls any thickness including attached pillasters buttresses plinth & string courses etc. | sqm | 285.15 | 608.4 |  |  |  | 173485.26 | 0 | 0 | 0
5.9.3 | Suspended floors roofs landings & balconies & access plateform. | sqm | 311.2 | 319.52 |  |  |  | 99434.624 | 0 | 0 | 0
5.9.5 | Lintel beams plinth beams girders bressumers & cantilevers. | sqm | 262.25 | 9 |  |  |  | 2360.25 | 0 | 0 | 0
5.9.6 | Columns, Pillars, Piers, Abutments, Posts and Struts. | sqm | 365.6 | 4.26 |  |  |  | 1557.456 | 0 | 0 | 0
5.9.7 | Stairs (excluding landings) except spiral stair case | sqm | 326.3 | 9.6195 |  |  |  | 3138.8429 | 0 | 0 | 0
5.9.15 | Small lintels not exceeding 1.5m clear span, moulding as in cornices, window sills, string courses, bands, copings, bed plates, anchor blocks and the like. | sqm | 166.9 | 0.49 |  |  |  | 81.781 | 0 | 0 | 0
5.9.16 | Edges of slabs and breaks in floors and walls. | [6 empty] | 0 | 0 | 0 | 0
5.9.16.2 | Above 20 cm wide | sqm | 441.1 | 15.8 |  |  |  | 6969.38 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
| STEEL REINFORCEMENT | [6 empty] | 0 | 0 | 0 | 0
5.22 | Reinforcement for RCC work including straightening, cutting bending, placing in position and binding all complete upto plinth level. | [6 empty] | 0 | 0 | 0 | 0
5.22.6 | Thermo-Mechanically Treated bars. | kg | 62.25 | 32704 |  |  |  | 2035824 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
5.22A | Steel reinforcement for RCC work including straightening, cutting, bending, placing in position and binding all complete above plinth level. | [6 empty] | 0 | 0 | 0 | 0
5.22A.6 | Thermo-Mechanically Treated bars. | kg | 62.25 | 911.1 |  |  |  | 56715.975 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
| DESIGN MIX CONCRETE | [6 empty] | 0 | 0 | 0 | 0
5.33 | Providing & laying in position machine batched and machine mixed design mix M-25 grade cement concrete for reinforced cement concrete work, using cement content as per approved design mix, including pumping of concrete to site of laying but excluding the cost of centering, shuttering, finishing and reinforcement, including admixtures in recommended proportions as per IS:9103 to accelerate, retard setting of concrete, improve workability without impairing strength and durability as per direction of Engineer-in-charge. (Note: Cement content considered in this item is @ 330 kg/cum. Excess/less cement used as per design mix is payable/recoverable separately). | [6 empty] | 0 | 0 | 0 | 0
5.33.1 | All works upto plinth level. | cum | 5242.15 | 263.55 |  |  |  | 1381568.6325 | 0 | 0 | 0
5.33.2 | All works above plinth level upto floor V level. | cum | 5781.5 | 7.6 |  |  |  | 43939.4 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
6.34 | Brick work with non modular fly ash lime bricks (FALG Bricks) conforming to IS:12894-2002, class designation 10 average compressive strength in super structure above plinth level up to floor V level in : | [6 empty] | 0 | 0 | 0 | 0
6.34.2 | Cement mortar 1:6 (1 cement : 6 Coarse sand) | cum | 3978.5 | 22.25 |  |  |  | 88521.625 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
10.11 | Providing & fixing factory made ISI marked steel glazed doors, windows and ventilators side /top /centre hung with beading and all members such as F7D, F4B, K11 B and K12 B etc. complete of standard rolled steel sections, joints mitred and flash butt welded and sash bars tenoned and riveted, including providing and fixing of hinges, pivots, including priming coat of approved steel primer , but excluding the cost of other fittings, complete all as per approved design (sectional weight of only steel members shall be measured for payment). | [6 empty] | 0 | 0 | 0 | 0
10.11.1 | Fixing with 15x3 mm lugs 10 cm. long embedded in cement concrete block 15x10x10 cm of CC 1:3:6 (1 cement : 3 coarse sand : 6 graded stone aggregate 20 mm nominal size). | kg | 96.3 | 51.12 |  |  |  | 4922.856 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
10.13 | Providing & fixing T-iron frames for doors, windows and ventilators of mild steel Tee-sections, joints mitred and welded, including fixing of necessary butt hinges and screws and applying a priming coat of approved steel primer. | [6 empty] | 0 | 0 | 0 | 0
10.13.1 | Fixing with 15x3 mm lugs 10 cm. long embedded in cement concrete block 15x10x10 cm of C.C. 1:3:6 (1 Cement : 3 coarse sand : 6 graded stone aggregate 20 mm nominal size). | kg | 73.3 | 23.4 |  |  |  | 1715.22 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
10.25 | Steel work welded in built up sections / framed work including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer using structural steel etc. as required. | [6 empty] | 0 | 0 | 0 | 0
10.25.1 | In stringers, treads, landings etc. of stair cases including use of chequered plate wherever required, all complete. | kg | 67.2 | 102.62 |  |  |  | 6896.064 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
10.3 | Providing & fixing glass panes with putty and glazing clips in steel doors, windows, clerestory windows all complete. | [6 empty] | 0 | 0 | 0 | 0
10.30.1 | With 4.0 mm thick glass panes | sqm | 657.75 | 2.16 |  |  |  | 1420.74 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
11.26 | Kota stone slab flooring over 20 mm (average) thick base laid over and jointed with grey cement slurry mixed with pigment to match the shade of the slab including rubbing and polishing complete with base of cement mortar 1:4 (1 cement : 4 coarse sand) : | [6 empty] | 0 | 0 | 0 | 0
11.26.1 | 25 mm thick. | sqm | 945.7 | 337.25 |  |  |  | 318937.325 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
11.37 | Providing and laying Ceramic glazed floor tiles 300x300 mm (thickness to be specified by the manufacturer) of 1st quality conforming to IS : 15622 of approved make in colours such as White, Ivory, Grey, Fume Red Brown, laid on 20 mm thick Cement Mortar 1:4 (1 Cement : 4 Coarse sand) including pointing the joints with white cement and matching pigment etc., complete. | sqm | 764.55 | 195 |  |  |  | 149087.25 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
11.27 | Kota stone slabs 20mm thick in risers of steps, skirting, dado and pillars laid on 12 mm (average) thick cement mortar 1:3 (1 cement 3 coarse sand) and jointed with grey cement slurry mixed with pigment to match the shade of the slabs, including rubbing and polishing complete. | sqm | 954.1 | 12.966 |  |  |  | 12370.8606 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
11.36 | Providing & fixing Ist quality ceramic glazed wall tiles conforming to IS:15622 (thickness to be specified by the manufacturer) of approved make in all colours, shades except burgundy, bottle green, black of any size as approved by Engineer-in-Charge, in skirting, risers of steps and dados over 12mm thick bed of cement Mortar 1:3 (1 cement : 3 coarse sand) and jointing with grey cement slurry @ 3.3kg per sqm including pointing in white cement mixed with pigment of matching shade complete. | sqm | 724.25 | 321.3 |  |  |  | 232701.525 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
13.4 | 12 mm cement plaster of mix | [6 empty] | 0 | 0 | 0 | 0
13.4.1 | 1:4 (1 cement: 4 coarse sand) | sqm | 132.1 | 193.92 |  |  |  | 25616.832 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
13.16 | 6 mm thick cement plaster to ceiling of mix : | [6 empty] | 0 | 0 | 0 | 0
13.16.1 | 1:3 (1 cement :3 fine sand) | sqm | 101 | 44.1 |  |  |  | 4454.1 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
13.41 | Distempering with oil bound washable distemper of approved brand and manufacture to give an even shade | [6 empty] | 0 | 0 | 0 | 0
13.41.1 | New work (two or more coats) over and including water thinnable priming coat with cement primer. | sqm | 66.7 | 706 |  |  |  | 47090.2 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
13.61 | Painting with synthetic enamel paint of approved brand and manufacture to give an even shade : | [6 empty] | 0 | 0 | 0 | 0
13.61.1 | Two or more coats on new work | sqm | 53.85 | 11.59 |  |  |  | 624.1215 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
19.16 | Providing orange colour safety foot rest of minimum 6mm thick plastic encapsulated as per IS:10910 on 12mm dia steel bar conforming to IS:1786 having minimum cross section as 23x25mm and over all minimum length 263mm and width as 165mm with minimum 112mm space between protruded legs having 2mm tread on top surface by ribbing or chequering besides necessary and adequate anchoring projections on tail length on 138mm as per standard drawing and suitable to with stand the bend test and chemical resistance test as per specifications and having manufacture's permanent identification mark to be visible even after fixing, including fixing in manholes with 30x20x15 cm cement concrete block 1:3:6 (1 cement : 3 coarse sand : 6 graded stoen aggregate 20mm nominal size) complete as per design. | each | 256.75 | 48 |  |  |  | 12324 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
19.19 | Providing and fixing in position pre-cast R.C.C. manhole cover and frame of required shape and approved quality | [6 empty] | 0 | 0 | 0 | 0
19.19.3 | HD - 20 | [6 empty] | 0 | 0 | 0 | 0
19.19.3.1 | Circular shape 560 mm internal diameter | each | 1390.25 | 8 |  |  |  | 11122 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
22.5 | Providing & laying water proofing treatment in sunken portion of WCs, bathroom etc., by applying cement slurry mixed with water proofing cement compound consisting of applying : a) First layer of slurry of cement @ 0.488 kg/sqm mixed with water proofing cement compound @ 0.253 kg/sqm. This layer will be allowed to air cure for 4 hours. b) Second layer of slurry of cement @ 0.242 kg/sqm mixed with water proofing cement compound @ 0.126 kg/sqm. This layer will be allowed to air cure for 4 hours followed with water curing for 48 hours. The rate includes preparation of surface, treatment and sealing of all joints, corners, junctions of pipes and masonry with polymer mixed slurry. | sqm | 215.15 | 585 |  |  |  | 125862.75 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
AR | Providing and fixing vent pipe with anti mosquito proof coupling - 0.50 m long | [6 empty] | 0 | 0 | 0 | 0
| 65 mm dia | each | 1137 | 4 |  |  |  | 4548 | 0 | 0 | 0
| 80 mm dia | each | 1467 | 4 |  |  |  | 5868 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
AR/ DSR Based | Providing and fixing in position pipe puddle flanges made of 6mm thick MS plate | [6 empty] | 0 | 0 | 0 | 0
| 50mm dia and 500 mm long | each | 522 | 4 |  |  |  | 2088 | 0 | 0 | 0
| 65mm dia and 500 mm long | each | 630 | 4 |  |  |  | 2520 | 0 | 0 | 0
| 80mm dia and 500 mm long | each | 846 | 4 |  |  |  | 3384 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
22.4 | Providing and Placing in position suitable PVC water stops conforming to IS:12200 for construction/ expansion joints between two RCC members and fixed to the reinforcement with binding wire before pouring concrete etc. complete : | [6 empty] | 0 | 0 | 0 | 0
22.4.2 | Dumb bell with central bulb (180mm wide, 8mm thick). | mtr | 413.85 | 301.9 |  |  |  | 124941.315 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
[8 empty] | 1550827135.3454 | 30050607.6375 | 163485106.2482 | 30513629.6

## Manpower-req
Requirement of Man Power
(FOR NEXT TWO MONTH)
A- | Manpower :
ACTUALLY REQUIRED FOR THE M/O JAN- 2015
S.NO. | CATEGORY | Required Per Day | Available Per- Day | bal Required PER DAY | Required next month
[5 empty] | 2015-01-01 | 2010-03-01 | 2009-12-01
1 | MASON | 30 | 19 | 11 | 900 | 16 | 16
2 | MASON HELPER | 70 | 61 | 9 | 2100 | 600 | 600
3 | UNSKILLED | 50 | 10 | 40 | 1500
4 | CARPENTER | 42 | 53 | -11 | 1260 | 95 | 95
5 | CARPENTER HELPER | 100 | 53 | 47 | 3000 | 80 | 75
6 | BAR BINDER | 60 | 48 | 12 | 1800 | 64 | 64
7 | BAR BINDER HELPER | 144 | 51 | 93 | 4320 | 70 | 65
8 | SCAFFOLDER/ HELPER | 25 | 5 | 20 | 750 | 310 | 310
9 | WELDER | 10 | 4 | 6 | 300
10 | OTHERS | 25 | 11 | 14 | 750
| TOTAL MANPOWER : | 556 | 315 | 241 | 16680 | 1235 | 1225

## material reconcilation
ERA INFRA ENGINEERING LTD (CORPORATE EPC-INFRA-1)
Project : : 2005-IN-SITU REHABILITATION AT A-14
C | RCC Description | AREA OF PLINTH | PCC FOR RAFT (1:5:10) | RCC M25 | RCC M30 |  | REMARK
| TOTAL |  | 151.1472 | 2970.9009 | 739.6782
`
| DETAIL | UNIT | PCC FOR RAFT (1:5:10) | RCC M25 | RCC M30 |  | TOTAL REQUIREMENT |  |  |  | PCC FOR RAFT (1:5:10) | RCC M25 | RCC M30
| TOTAL CEMENT BAGS | BAGS | 392.9827 | 21390.4862 | 5473.6187 |  | 27257.0876 |  |  | 265 | 0 | 0 | 0
| TOTAL ADMIXTURE | KG | 0 | 6535.9819 | 2736.8094 |  | 9272.7913 |  |  | 39.25 | 0 | 0 | 0
| TOTAL COARS SAND | MT | 106.5588 | 2338.099 | 596.1806 |  | 3040.8384 |  |  | 988.68 | 0 | 0 | 0
| TOTAL 40 MM | MT | 163.9947 | 0 | 0 |  | 163.9947 |  |  | 1030.28 | 0 | 0 | 0
| TOTAL 20 MM | MT | 58.0405 | 1898.4057 | 446.7656 |  | 2403.2118 |  |  | 1030.28 | 0 | 0 | 0
| TOTAL 10 MM | MT | 0 | 1259.662 | 315.1029 |  | 1574.7649 |  |  | 1030.28 | 0 | 0 | 0
| INHABITOR SOLUTION | KG |  |  |  |  | 15935.8763 |  |  |  | 0 | 0 | 0
| CEMENT FOR STEEL COATING | BAGS |  |  |  |  | 535.4454
MATERIAL REQUIREMENT January-14
| DETAIL | UNIT | TOTAL REQUIRMENT
| TOTAL CEMENT BAGS | BAGS | 27792.5331 |  |  |  | 27792.5331
| TOTAL ADMIXTURE | KG | 9272.7913 |  |  |  | 9272.7913
| TOTAL COARS SAND | MT | 3040.8384 |  |  |  | 3040.8384
| TOTAL 40 MM | MT | 163.9947 |  |  |  | 163.9947
| TOTAL 20 MM | MT | 2403.2118 |  |  |  | 2403.2118
| TOTAL 10 MM | MT | 1574.7649 |  |  |  | 1574.7649
| INHABITOR SOLUTION | KG | 15935.8763 |  |  |  | 15935.8763
| STEEL REQ DETAIL | MT | 8MM | 10MM | 12MM | 16MM | 20MM | 25MM | TOTAL
CL-4, TOWER-5
| STILT SLAB | MT | 6.002 | 0.34814 | 0.99818 | 1.4008 | 2.4463 | 1.8033 | 12.9987
| 1ST FLOOR COLUMN | MT | 1.882 | 0 | 0 | 0.85221 | 2.9976 | 2.4775 | 8.2092
| 1ST FLOOR SLAB &BEAM | MT | 6.002 | 0.34814 | 0.99818 | 1.4008 | 2.4463 | 1.8033 | 12.9987
| 2ND FLOOR COLUMN | MT | 1.882 | 0 | 0 | 0.85221 | 2.9976 | 2.4775 | 8.2092
CL-4 TOWER-1
| 2ND FLOOR COLUMN | MT | 1.6724 | 0 | 0 | 0.5914 | 2.5799 | 2.3822 | 7.2259
| 2ND FLOOR BEAM &SLAB | MT | 5.6308 | 0.30139 | 0.9288 | 1.1571 | 1.5623 | 2.0456 | 11.6259
| 3RD FLOOR COLUMN | MT | 1.6724 | 0 | 0 | 0.5914 | 2.5799 | 2.3822 | 7.2259
| 3RD FLOOR BEAM SLAB | MT | 5.6308 | 0.30139 | 0.9288 | 1.1571 | 1.5623 | 2.0456 | 11.6259
CL-4 TOWER-2
| 3RD FLOOR SLAB &BEAM | MT | 6.002 | 0.34814 | 0.99818 | 1.4008 | 2.4463 | 1.8033 | 12.9987
| 4TH FLOOR COLUMN | MT | 1.882 | 0 | 0 | 0.85221 | 2.9976 | 2.4775 | 8.2092
| 4TH FLOOR SLAB &BEAM | MT | 6.002 | 0.34814 | 0.99818 | 1.4008 | 2.4463 | 1.8033 | 12.9987
| 5TH FLOOR COLUMN | MT | 1.882 | 0 | 0 | 0.85221 | 2.9976 | 2.4775 | 8.2092
CL-4 TOWER-3
| 1ST FLOOR BEAM&SLAB | MT | 6.7551 | 0.50345 | 1.1113 | 1.8187 | 2.6698 | 3.7897 | 16.648
| 2ND FLOOR COLUMN | MT | 2.5446 | 0 | 0 | 1.1549 | 3.9943 | 3.1127 | 10.8065
| 2ND FLOOR BEAM | MT | 6.7551 | 0.50345 | 1.1113 | 1.8187 | 2.6698 | 3.7897 | 16.648
| 3RD FLOOR COLUMN | MT | 2.5446 | 0 | 0 | 1.1549 | 3.9943 | 3.1127 | 10.8065
CL-4 TOWER-4
| 1ST FLOOR COLUMN | MT | 2.4706 | 0 | 0 | 1.1549 | 3.9176 | 2.7316 | 10.2747
| 1ST FLOOR BEAM&SLAB | MT | 6.5736 | 0.48992 | 1.0815 | 1.7698 | 2.598 | 3.6879 | 16.2008
| 2ND FLOOR COLUMN | MT | 2.4706 | 0 | 0 | 1.1549 | 3.9176 | 2.7316 | 10.2747
| 1ST FLOOR BEAM&SLAB | MT | 6.5736 | 0.48992 | 1.0815 | 1.7698 | 2.598 | 3.6879 | 16.2008
CL-4 TOWER-6
| 2ND FLOOR COLUMN | MT | 1.6724 | 0 | 0 | 0.5914 | 2.5799 | 2.3822 | 7.2259
| 2ND FLOOR SLAB &BEAM | MT | 5.6308 | 0.30139 | 0.9288 | 1.1571 | 1.5623 | 2.0456 | 11.6259
| 3RD FLOOR COLUMN | MT | 1.6724 | 0 | 0 | 0.5914 | 2.5799 | 2.3822 | 7.2259
| 3RD FLOOR SLAB &BEAM | MT | 5.6308 | 0.30139 | 0.9288 | 1.1571 | 1.5623 | 2.0456 | 11.6259
CLUSTER-3
TOWER-1
| 2ND FLOOR BEAM | MT | 1.4573 | 0 | 0.71131 | 1.164 | 1.7088 | 2.4256 | 7.4669
| 2ND FLOOR SLAB | MT | 2.8663 | 0.32223 | 0 | 0 | 0 | 0 | 3.1885
| 2ND FLOOR COLUMN | MT | 1.7198 | 0 | 0 | 0.60814 | 2.6529 | 2.4496 | 7.4304
| 3RD FLOOR BEAM | MT | 1.4573 | 0 | 0.71131 | 1.164 | 1.7088 | 2.4256 | 7.4669
| 3RD FLOOR SLAB | MT | 2.8663 | 0.32223 | 0 | 0 | 0 | 0 | 3.1885
| 3RD FLOOR COLUMN | MT | 1.7198 | 0 | 0 | 0.60814 | 2.6529 | 2.4496 | 7.4304
TOWER-2
| 1ST FLOOR BEAM | MT | 1.0126 | 0 | 0.49429 | 0.80888 | 1.1874 | 1.6855 | 5.1888
| 1ST FLOOR SLAB | MT | 1.9918 | 0.22392 | 0 | 0 | 0 | 0 | 2.2157
| 1ST FLOOR COLUMN | MT | 1.1951 | 0 | 0 | 0.4226 | 1.8435 | 1.7022 | 5.1634
| 2ND FLOOR BEAM | MT | 1.0126 | 0 | 0.49429 | 0.80888 | 1.1874 | 1.6855 | 5.1888
| 2ND FLOOR SLAB | MT | 1.9918 | 0.22392 | 0 | 0 | 0 | 0 | 2.2157
| 2ND FLOOR COLUMN | MT | 1.1951 | 0 | 0 | 0.4226 | 1.8435 | 1.7022 | 5.1634
TOWER-3
| STILT FLOOR BEAM | MT | 1.462 | 0 | 0.71364 | 1.1678 | 1.7144 | 2.4335 | 7.4914
| STILT FLOOR SLAB | MT | 2.8757 | 0.32328 | 0 | 0 | 0 | 0 | 3.1989
| 1ST FLOOR COLUMN | MT | 1.7254 | 0 | 0 | 0.61014 | 2.6616 | 2.4577 | 7.4548
| 1ST FLOOR BEAM | MT | 1.462 | 0 | 0.71364 | 1.1678 | 1.7144 | 2.4335 | 7.4914
| 1ST FLOOR SLAB | MT | 2.8757 | 0.32328 | 0 | 0 | 0 | 0 | 3.1989
| 2ND FLOOR COLUMN | MT | 1.7254 | 0 | 0 | 0.61014 | 2.6616 | 2.4577 | 7.4548
T0WER-4
| 1ST FLOOR BEAM | MT | 1.0126 | 0 | 0.49429 | 0.80888 | 1.1874 | 1.6855 | 5.1888
| 1ST FLOOR SLAB | MT | 1.9918 | 0.22392 | 0 | 0 | 0 | 0 | 2.2157
| 1ST FLOOR COLUMN | MT | 1.1951 | 0 | 0 | 0.4226 | 1.8435 | 1.7022 | 5.1634
| STILT FLOOR BEAM | MT | 1.0126 | 0 | 0.49429 | 0.80888 | 1.1874 | 1.6855 | 5.1888
| STILT FLOOR SLAB | MT | 1.9918 | 0.22392 | 0 | 0 | 0 | 0 | 2.2157
| STILT FLOOR COLUMN | MT | 1.1951 | 0 | 0 | 0.4226 | 1.8435 | 1.7022 | 5.1634
TOWER-5
| STILT FLOOR COLUMN | MT | 1.1951 | 0 | 0 | 0.4226 | 1.8435 | 1.7022 | 5.1634
| STILT FLOOR SLAB | MT | 3.0044 | 0.22392 | 0.49429 | 0.80888 | 1.1874 | 1.6855 | 7.4044
| 1ST FLOOR COLUMN | MT | 1.1951 | 0 | 0 | 0.4226 | 1.8435 | 1.7022 | 5.1634
TOWER-6
| 1ST FLOOR COLUMN | MT | 1.7254 | 0 | 0 | 0.61014 | 2.6616 | 2.4577 | 7.4548
| 1ST FLOOR BEAM | MT | 1.462 | 0 | 0.71364 | 1.1678 | 1.7144 | 2.4335 | 7.4914
| 1ST FLOOR SLAB | MT | 2.8757 | 0.32328 | 0 | 0 | 0 | 0 | 3.1989
| 2ND FLOOR COLUMN | MT | 1.7254 | 0 | 0 | 0.61014 | 2.6616 | 2.4577 | 7.4548
| 2ND FLOOR BEAM | MT | 1.462 | 0 | 0.71364 | 1.1678 | 1.7144 | 2.4335 | 7.4914
| 2ND FLOOR SLAB | MT | 2.8757 | 0.32328 | 0 | 0 | 0 | 0 | 3.1989
CLUSTER-2
TOWER-1
| STILT FLOOR SLAB | MT | 4.3539 | 0.32449 | 0.7163 | 1.1722 | 1.7208 | 2.4426 | 10.7303
| 1ST FLOOR COLUMN | MT | 1.7319 | 0 | 0 | 0.61241 | 2.6715 | 2.4668 | 7.4826
| 1ST FLOOR SLAB | MT | 4.3539 | 0.32449 | 0.7163 | 1.1722 | 1.7208 | 2.4426 | 10.7303
| 2ND FLOOR COLUMN | MT | 1.7319 | 0 | 0 | 0.61241 | 2.6715 | 2.4668 | 7.4826
| RETAINING WALL RAFT | MT | 0 | 3.5257 | 0.25308 | 0 | 0 | 0 | 3.7788
| RETAINING WALL | MT | 0.80712 | 0.77048 | 1.6062 | 0 | 0 | 0 | 3.1838
TOWER-2
| STILT FLOOR SLAB | MT | 4.557 | 0.33963 | 0.74972 | 1.2269 | 1.801 | 2.5566 | 11.2309
| 1ST FLOOR COLUMN | MT | 1.8127 | 0 | 0 | 0.64099 | 2.7962 | 2.5819 | 7.8317
| 1ST FLOOR SLAB | MT | 4.557 | 0.33963 | 0.74972 | 1.2269 | 1.801 | 2.5566 | 11.2309
| 2ND FLOOR COLUMN | MT | 1.8127 | 0 | 0 | 0.64099 | 2.7962 | 2.5819 | 7.8317
CLUSTER-1
TOWER-1
| COLUMN | MT | 4.688 | 0.58245 | 0.28412 | 2.5145 | 5.3557 | 1.2786 | 14.7033
| PLINTH BEAM | MT | 0.97339 | 0 | 1.5058 | 0.33001 | 0.078491 | 0 | 2.8877
TOWER-2
| RAFT | MT | 0.03412 | 0 | 0.66146 | 11.3944 | 0.053073 | 1.4844 | 13.6275
| COLUMN | MT | 4.9753 | 0.61814 | 0.30153 | 2.6686 | 5.6839 | 1.3569 | 15.6043
TOWER-3
| RAFT | MT | 0.037952 | 0 | 0.73575 | 12.6741 | 0.059033 | 1.6512 | 15.158
TOWER-4
| STILT FLOOR COLUMN | MT | 1.5461 | 0 | 0 | 0.54674 | 2.385 | 2.2023 | 6.6802
| STILT FLOOR SLAB | MT | 3.887 | 0.28969 | 0.63949 | 1.0465 | 1.5362 | 2.1807 | 9.5796
| 1ST FLOOR COLUMN | MT | 1.5461 | 0 | 0 | 0.54674 | 2.385 | 2.2023 | 6.6802
TOWER-5
| COLUMN | MT | 3.7286 | 0.46325 | 0.22597 | 1.9999 | 4.2596 | 1.0169 | 11.6942
| PLINTH BEAM | MT | 0.8757 | 0 | 1.3547 | 0.29689 | 0.070614 | 0 | 2.5979
TOWER-6
| RAFT | MT | 0.037952 | 0 | 0.73575 | 12.6741 | 0.059033 | 1.6512 | 15.158
| TOTAL |  | 204.016 | 15.2199 | 30.0781 | 99.0362 | 147.8336 | 144.5546 | 640.7385
|  |  | 204016.0151 | 15219.94 | 30078.0853 | 99036.2148 | 147833.5859 | 144554.6212 | 640738.4624
| BINDING WIRE | KG | 5446.2769

## Material Resource req
REQUIREMENT OF JAN-15
DDA Kalkaji -2005
A- | Material :
S.NO. | Descriptions | Unit | Total required | Available AT SITE | Net Required | Rate | TOTAL material Amount | Net material Amount
1 | Cement | Bag | 27792.5331 | 3103 | 24689.5331 | 265 | 7365021.2665 | 6542726.2665
2 | C/ Sand | MT | 3040.8384 | 300 | 2740.8384 | 988.68 | 3006416.0862 | 2709812.0862
3 | Agg- 10 mm | MT | 1656.7622 | 500 | 1156.7622 | 1030.28 | 1706928.987 | 1191788.987
4 | Agg- 20 mm | MT | 2485.2091 | 600 | 1885.2091 | 1030.28 | 2560461.2825 | 1942293.2825
5 | Agg- 40 mm | MT | 0 |  | 0 | 1030.28 | 0 | 0
6 | Admixture | Kg | 9272.7913 | 2250 | 7022.7913 | 39.25 | 363957.0577 | 275644.5577
7 | Inihabitaor Solution | Kg | 15935.8763 | 6300 | 9635.8763 | 27 | 430268.6588 | 260168.6588
8 | BRICKS 2ND QUALITY | NOS. | 30000 | 7000 | 23000 | 4 | 120000 | 92000 | 2800
9 | TMT Steel | [5 empty] | 0 | 0
10 | TMT STEEL MS 8 MM | KG | 204016.0151 |  | 204016.0151 | 51.119 | 10429094.6768 | 10429094.6768
11 | TMT STEEL MS 10 MM | KG | 15219.94 |  | 15219.94 | 51.119 | 778028.1109 | 778028.1109
12 | TMT STEEL MS 12 MM | KG | 30078.0853 |  | 30078.0853 | 51.119 | 1537561.6426 | 1537561.6426
13 | TMT STEEL MS 16 MM | KG | 99036.2148 |  | 99036.2148 | 51.119 | 5062632.2661 | 5062632.2661
14 | TMT STEEL MS 20 MM | KG | 147833.5859 |  | 147833.5859 | 51.119 | 7557105.0787 | 7557105.0787
15 | TMT STEEL MS 25 MM | KG | 144554.6212 |  | 144554.6212 | 51.119 | 7389487.6822 | 7389487.6822
16 | MS PIPE 40 MM (6 MTR LONG) | NOS. | 200 |  | 200 | 65 | 13000 | 13000
17 | MS ANGLE 50*50*5 FOR COLUMN | KG | 4000 |  | 4000 | 55 | 220000 | 220000
18 | Binding Wire | kg | 5125.9077 |  | 5125.9077 | 65 | 333184.0004 | 333184.0004
18 | GI SHEET | NOS. | 1000 | 0 | 1000 | 750 | 750000 | 750000
[7 empty] | 49623146.7965 | 47084527.2965

## Machinery-req
ERA INFRA ENGINEERING LTD.
MACHINERY & EQUIPMENTS REQUIREMENT
DDA Kalkaji (2005)
A. MAJOR MACHINERY & EQUIPMENTS
A. 1. COMPANY OWNED
S.NO | DETATIL OF MACHINERY & EQUPMENTS | UNIT | BUDGET | AVAILABLE | SHORTFALL/ SURPLUS | NEXT TWO MONTHS BUDGET
[6 empty] | 2014-01-15 | 2014-02-15
1 | Batching plant 30 cum/Hrs with silo | No. | 1 | 1 | 0 | 1 | 1
2 | Concrete pump with pipe line 600 mtrs. | Nos. | 2 | 2 | 0 | 2 | 2
3 | Transit Mixer | Nos. | 4 | 3 | 1 | 4 | 4
4 | Tower Crane | Nos. | 5 | 0 | 5 | 5 | 5
5 | Crane (MTC) | Nos. | 3 | 1 | 2 | 3 | 3
6 | DG Set 125 KVA | Nos. | 3 | 1 | 2 | 3 | 3
7 | DG Set 15 KVA | Nos. | 1 | 1 | 0 | 1 | 1
8 | Builder Hoist | Nos. | 12 | 0 | 12 | 12 | 12
9 | Monkey Host | Nos. | 12 | 0 | 12 | 12 | 12
10 | Tough Rider | No. | 1 | 0 | 1 | 1 | 1
11 | JCB | No. | 1 | 1 | 0 | 1 | 1
12 | Earth compactor | Nos. | 5 | 5 | 0 | 5 | 5
13 | Auto level | Nos. | 3 | 1 | 2 | 3 | 3
14 | Total Station | No. | 1 | 1 | 0 | 1 | 1
15 | Tractor with Trolley | Nos. | 3 | 1 | 2 | 3 | 3
16 | Vehicle for site use(Tata Sumo/ Bolero) | Nos. | 2 | 1 | 1 | 2 | 2
17 | Ambulance | No. | 1 | 0 | 1 | 1 | 1
18 | Mobile toilet (10 seater) | Nos. | 2 | 1 | 1 | 2 | 2
19 | Mixer machine with weigh batcher | Nos. | 3 | 1 | 2 | 3 | 3
20 | Vibrator (Electrical/ Diesel) | Nos. | 12 | 4 | 8 | 12 | 12
21 | Vibrator Nozzle (60/ 40/ 25 MM) | Nos. | 30 | 8 | 22 | 30 | 30
22 | Dewatering pump (5 HP/ 3 HP) | Nos. | 3 | 2 | 1 | 3 | 3
23 | Tullu pump (0.5/ 1 HP) | Nos. | 3 | 1 | 2 | 3 | 3
24 | Submersible Pump (7.5 HP) | Nos. | 6 | 0 | 6 | 6 | 6
25 | Welding set (Trasnformer/ DG) | Nos. | 3 | 2 | 1 | 3 | 3
26 | Gas Cutting set | Nos. | 3 | 0 | 3 | 3 | 3
27 | Pocklain / Excavator | No. | 1 | 1 | 0 | 1 | 1
28 | Compresssor | No. | 1 | 0 | 1 | 1 | 1
29 | Weigh Bridge | No. | 1 | 1 | 0 | 1 | 1
30 | Water tanker with Tractor | Nos. | 4 | 1 | 3 | 4 | 4
31 | Bar Cutting Machine | Nos. | 10 | 4 | 6 | 10 | 10
32 | Bar Bending Machine | Nos. | 10 | 4 | 6 | 10 | 10
A. 2. HIRED MACHINERY
S.NO | DETATIL OF MACHINERY & EQUPMENTS | UNIT | BUDGET | AVAILABLE | SHORTFALL/ SURPLUS | NEXT TWO MONTHS BUDGET
[6 empty] | 2014-01-15 | 2014-02-15
1 | J.C.B | NOS | 1 | 1 | 0 | 1 | 1
2 | hywa | NOS | 1 | 1 |  | 1 | 1
3 | DUMPPER | NOS | 1 | 1 |  | 1 | 1
TOTAL MACHINERIES :

## EMD-Rent
ERA INFRA ENGINEERING LTD.
370-71/2, SAHI HOSPITAL ROAD, JANGPURA, BHOGAL, NEW DELHI-110014.
PROEJCT CODE: 2005 | [11 empty] | Expected
PROJECT NAME: DDA Kalkaji
CERTIFIED RENTAL BILL OF EMD DIVISION FOR THE MONTH OF JAN- 2015
S. No. | EQPT ID | EQUIPMENT | MODEL | CAPACITY | Working Days | Break Down Days | MONTHLY RENTAL CHARGES | ADD | ADD | ADD MANPOWER CHARGES | LESS: B/DOWN DAYS CHRG. | TOTAL EQUIPMENT CHARGES (H+J+K+L)
[8 empty] | HOURS | HOURS
[8 empty] | CLOCKED | CHARGES
1 | [5 empty] | 0 |  |  |  |  | 0
2 | [10 empty] | 0
3 | [10 empty] | 0
4 | [10 empty] | 0
Total: | [11 empty] | 0

## Machine-Hire
ERA INFRA ENGINEERING LIMITED
(CONSTRUCTION & CONTRACTS DIVISION)
Expected
Hire Charges of Machinery
Project Name: DDA KALKAJI | [6 empty] | 2015-01-01
Project Code: 2005
Sl. No. | Agency Name/EIEL/EMD | Machinery Name/Sl. No | Total Availaibility as per WO (Hrs per day) | Total running is a month | Rate/ Hrs | Amount | Overtime
A | CIVIL WORKS
1 | NISH EARTH MOVER | JCB | 10 | 300 | 233.3333 | 69999.9999
2 | CHARANJITH SINGH | HYWA | 10 | 300 | 300 | 90000
3 | CHARANJITH SINGH | DUMPER | 10 | 300 | 200 | 60000
4 | [5 empty] | 0
5 | [5 empty] | 0
[6 empty] | 219999.9999 | 0
TOTAL (A) | [5 empty] | 219999.9999
B | STRUCTURAL WORKS
1
2
[6 empty] | 0 | 0
TOTAL (B) | [5 empty] | 0
GRAND TOTAL (A+B) : | [5 empty] | 219999.9999

## Machinery-Rent
ERA INFRA ENGINEERING LIMITED
370,371/72,SAHI HOSPITAL ROAD,JANGPURA,BHOGAL,NEW DELHI-110014
Expected
MACHINERY RENTAL M/O - JAN- 2015
PROJECT CODE:-2005
PROJECT NAME:-DDA KALKAJI
S.NO | DESCRIPTION | UNIT | QTY | RATE | TOTAL AMOUNT | REMARKS
1 | CUBE TESTING MACHINE 200 TON | EACH | 1 | 600 | 600
2 | CUBE TESTING MACHINE 100 TONNES (1000 KN ) ELECTRICALY CUM | EACH | 1 | 500 | 500
3 | ELECTRONIC TOTAL STATION MACHINE | SET | 1 | 4000 | 4000
4 | CONCRETE MIXER ELECTRIC WITH HOPPER | EACH | 1 | 1500 | 1500
5 | WELDING MACHINE AIR COOLED 350 AMP | EACH | 1 | 200 | 200
6 | WELDING MACHINE AIR COOLED 400 AMP | EACH | 1 | 200 | 200
7 | D G SET 7.5 KVA | EACH | 1 | 500 | 500
8 | D G SET 125 KVA | EACH | 1 | 6770.83 | 6770.83
9 | D G SET 15 KVA | EACH | 1 | 1562.5 | 1562.5
10 | BATCHING PLANT 30 CUM | EACH | 1 | 37500 | 37500
11 | TRACTOR | EACH | 1 | 6000 | 6000
12 | TRACTOR TROLLY HYDRAULIC | EACH | 1 | 2400 | 2400
13 | EARTH COMPACTER ELE | EACH | 5 | 400 | 2000
14 | BAR CUTTING MACHINE | EACH | 5 | 3000 | 15000
15 | BAR BENDING MACHINE | EACH | 4 | 1562.5 | 6250
16 | VIBRATER ORDINERY ELECTRICAL | EACH | 4 |  | 0
17 | MOTOR CYCLE HERO HONDA | EACH | 1 |  | 0
18 | TRANSIT MIXER | EACH | 3 | 26190 | 78570
19 | BOLERO | EACH | 1 | 18000 | 18000
20 | EXCAVATOR | EACH | 1 | 125000 | 125000
21 | CONCRITE PUMP BP 350D | EACH | 2 | 18750 | 37500
TOTAL : |  |  |  |  | 344053.33

## Temp.Str.
ERA INFRA ENGINEERING LIMITED
370-371/2,SAHI HOSPITAL ROAD,JANGPURA,BHOGAL,NEW DELHI-110014
TEMPORARY STRUCTURE M/O -42005
PROJECT CODE:-2005
PROJECT NAME:-DDA KALKAJI
S.NO | DESCRIPTION | UNIT | Qty | RATE | AMOUNT | REMARKS
1 | LABOUR HUTMENT 50 nos | Lumsum | 50 | 3500 | 175000
2 | STAFF QUARTER (WITH WC) | Lumsum | 0 | 0 | 0
3 | OTHERS (REPARING) | Lumsum |  |  | 75000
| TOTAL AMOUNT |  |  |  | 250000

## SEP-13 BUD (hidden)
[8 empty] | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | #REF! | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF!
[9 empty] | SHI-I- (MR.S.LOGANATHAN) | [21 empty] | SHI (MR.C PALNIVEL)
[9 empty] | S.T.L.- MR.S.Loganathan (S.E.) |  | S.T.L.- MR.Abhishek Mishra (A.E.) |  |  |  | S.T.L- PERIYASAMY (G.E.T.) | [7 empty] | S.T.L- MR. ANANDRAJ (A.E.) | [7 empty] | S.T.L- MR. A SENTHIL KUMAR (A.E.) | [9 empty] | S.T.L- MR. C.PALNIVEL (S.E.) | [5 empty] | S.T.L- MR. RAHUL PIPADA
BHEL CHENNAI | [8 empty] | S.T.M. Dharmendra Sharma |  | S.T.M- MR. RAJKUMAR PD YADAV |  |  |  | S.T.M- MR. DEV ANAND YADAV | [7 empty] | S.T.M- MR. RAJESH SHUKLA | [7 empty] | S. T.M. MR. C. SUDHAKAR |  |  |  | S. T.M. MR. Pankaj Roy | [5 empty] | S. T. M. -MR. RAJESH SHUKLA | [5 empty] | S. T. M. -MR. NAVEEN KUMAR PANDEY
SI. No. | Description | Unit | BOQ Rate | BOQ QTY | lab Rate | New Mat Rate | party Rate. | 0 | Service Bldg |  | MPH |  | SG AREA(includes Boiler & Mill) |  | VAC |  | ESP and boiler paving |  | Road |  | ETP |  | TAC |  | FOPH |  | ESP Building |  | Pipe Rack |  | Neut. Pit |  | CPU |  | ASPH |  | DMPH |  | SWITCH GEAR |  | ACWPH/LUBE OIL |  | Door matry Building |  | Transformer Yard /Trans Paving |  | Thurst Block/CW |  | Rail Track |  | GT/UT/Oil collection pit
Earth work
| Total Work Done |  |  |  |  | 0 | 0 |  | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT | QTY | AMOUNT
100 | EARTH WORK IN EXCAVATION, BACKFILLING AND DISPOSAL AS PER SPECIFICATION AND DRAWINGS |  |  | 0 | 0 | 0 | 0
101 | Excavation in all types of soils, soft rock and weathered rock except hard rock which requires blasting either by manual using crow bars, pick axe, etc., or machineries including trimming of excavation bottom, removal of loose materials to receive concrete bed as per std specifications drawings and instructions of the engineer. The rate shall include disposal of excavated materials within an initial lead upto 1KM and initial lift upto 2M, stacking,levelling, grading, etc., complete. |  |  | 0 | 0 | 0 | 0
i) | In all types of soils, soft rock and wethered rock not requiring chiselling, chemical grouting and blasting. | CUM | 148.8 | 65000 | 75 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
102 | Extra over item 101 above, for all types of soil/rock, for additional lifts beyond the initial lift of 2 meters (included in item 1 above) all complete as per specifications, drawings and instructions of the engineer for the following lift. Rate quoted shall be for the quantity specified for particular lift only. |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
i) | In all types of soils, sofrt rock and wethered rock | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
a | beyond 2 m and upto 4 m | CUM | 39.39 | 29000 | 15 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
b | beyond 4 m and upto 7 m | CUM | 74.4 | 5000 | 15 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
c | beyond 7 m and upto 10 m | CUM | 109.41 | 1000 | 30 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
103 | Extra over item No 101 for excavation & other filling works below ground water table by de-watering using well-point/suitable method for lowering of ground water table to maintain dry working conditions for all activities up to filling/testing, water proofing all complete as per specifications, drawings and instructions of the engineer in charge. The payment shall be on the basis of earth work excavation involved in that particular area. | CUM | 124.29 | 35000 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
104 | Extra over item 101 above for Disposal/carriage of all types of excavated materails beyond the initial lead of 1KM as per specifications, drawings and instructions of the engineer for the following leads | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
i) | Carriage beyond an initial lead of 1KM (Rate for every ONE KM) | CUM | 35.01 | 20000 | 10 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
105 | Filling using selected excavated materials in trenches, plinths, sides of foundations and other underground structures, pipes, are levelling etc. in layers not exceeding 250 mm thickness for all leads and all lifts and including loading from stock pile, carting, unloading, filling, watering and compacting/ramming each layer, all complete as per specifications, drawings and as directed by the engineer to achieve the following densities: | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
i) | Ordinary manual compaction | CUM | 100.66 | 2000 | 35 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ii) | 90% Standard Proctor density | CUM | 109.41 | 15000 | 55 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
105A | Filling using selected excavated materials directly from excavation area in trenches, plinths, sides of foundations and other underground structures, pipes, area levelling etc. in layers not exceeding 250 mm thickness including all lifts, filling, watering and compacting/ramming each layer, all complete as per specifications, drawings and as directed by the engineer to achieve the following densities: | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
i) | Ordinary manual compaction | CUM | 52.52 | 1000 | 35 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ii) | 90% Standard Proctor density | CUM | 56.9 | 10000 | 55 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
105B | Filling using selected materials in trenches, plinths, sides of foundations, in the space below the grade level slab and other under ground structures, pipes etc. in layers not exceeding 250 mm in thickness including all lifts and including excavating, loading, unloading, carting, filling, watering and compacting/ramming each layer, all complete as per specifications, drawings and as directed by the engineer for the following works | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
i) | With selected soil brought from borrow areas arranged by contractor, including royalties, fees etc.for all leads and compacted to following densities | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
a) | Ordinary manual compaction | CUM | 560.18 | 500 | 35 | 105 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
b) | 90% Standard Proctor density | CUM | 573.31 | 10000 | 55 | 105 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
106 | Filling with good river sand including royalties and all other statutories and compacting to 85% relative density, etc., for all leads. | CUM | 1032.83 | 1000 | 35 | 1409 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
107 | Filling in trenches, plinths, area paving and other underground structures with stone (63 mm down graded), in layers including breaking of boulders to required sizes, filling the interstices with good river sand, watering and machanical compactoion for all leads and lifts, etc., complete as per instructions of engineer-in-charge. | CUM | 1536.11 | 6000 | 110 | 1074 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
108 | Filling in transformer pits etc. , with clean 40 mm nominal size stone aggregate including all labour, materials, royalities, equipments etc. complete as per instructions of engineer in charge. | CUM | 1282.28 | 500 | 75 | 1074 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
109 | Buldozing earth for grading of ground including removal of vegetation complete including disposal of debris upto 5 kms. | CUM | 78.77 | 1000 | 20 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
116 | Providing, stacking and laying 250mm thick boulder pitching (single stone) on the slopes of earth fill/cut with approved quality of rock fragments including necessary excavation (if any) compaction etc all complete as per specification, drawing and as directed by the engineer. | CUM | 1680.53 | 500 | 150 | 500 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| ANTI TERMITE TREATMENT | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
117 | Providing anti termite treatment in column pits,wall trenches,foundations, under floors etc. with chloropyrifos emulsifiable concentrate (1%) confirming to IS - 8944 as per specifications. | SQM | 61.27 | 25000 |  |  | 25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
200 | PROVIDING AND PLACING CONCRETE WORK INCLUDING COST OF LABOUR, MATERIALS AND EQUIPMENT FOR HANDLING, TRANSPORTATION, BATCHING, MIXING, PLACING, VIBRATING AND CURING INCLUDING COST OF PLASTICIZER CONFORMING TO SPECIFICATIONS FOR STRUCTURAL CONCRETE WHEREVER REQUIRED (EXCLUDING COST OF CENTERING, SHUTTERING AND REINFORCEMENT) COMPLETE AS PER DRAWING AND SPECIFICATIONS UNLESS SPECIFIED OTHERWISE FOR THE FOLLOWING: | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
201 | Concrete of grade 1:3:6 as filling course at any level below finished floor level, under and around foundations/floors, mass dumps etc with 40 mm nominal size graded aggregate. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | CUM | 3334.8 | 500 | 225 | 2163 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
202 | Concrete of grade M15 as levelling course, under and around foundations/floors etc with 40 mm nominal size graded aggregate. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | CUM | 3820.58 | 4000 | 225 | 2540 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
203 | Concrete of grade M20 in foundations, under floors, paving, plinth protection, pipe encasing etc. complete with 20 mm nominal size graded aggregate. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | CUM | 4446.4 | 1000 | 225 | 3234.036 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
203A | Concrete of grade M15 in foundations, under floors, paving, plinth protection, pipe encasing etc. complete with 20 mm nominal size graded aggregate. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | CUM | 3509.86 | 350 | 225 | 2841.3684 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
204 | Concrete of grade M-25 in foundations, under floors, pipe encasement etc complete with 20 mm nominal size graded aggregate. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | CUM | 4647.71 | 10000 | 220 | 3386.7273 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
205 | Concrete of grade M-25 in superstructure above finished floor level complete at all heights with 20 mm nominal size graded aggregate | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | CUM | 4748.38 | 15000 | 580 | 3386.7273 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
206 | Concrete of grade M-30 in Machine foundations / Decks, Sub structure of Machine Foundations etc at all heights from finished floor level supported over vibration isolation system including addition of suitable plasticizer conforming to IS 9103-latest to achieve a slump more than 125mm in concrete as per manufacturer's recommendation with 20 mm nominal size graded aggregate. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | CUM | 5242.9 | 1000 | 340 | 3504.1127 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
206a | Providing and laying Design Mix M35 grade for reinforced concrete works using 20mm graded aggregate in top decks of machine foundations, TG deck etc, at all levels including addition of suitable plastisizers conforming to IS9103 to achieve a slump more than 125 mm in concrete as per manufacturers recomendation, preperation of scheme for concreting, getting it approved by engineer, labour, materials, equipment, handling, batching, transporting, mixing, pumping, placing, leveling, vibrating, compacting, curing, testing, cleaning and rendering the exposed surface with cement sand mortar to give a smooth and even surface, maintaining and submitting records of concreting, petrographic examination and potential reactivity of aggregate etc. all complete as per specification, drawing and instructions of engineer, but excluding formwork, staging, reinforcement, embeddments, UPV test and temperature control of concrete. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | CUM | 5378.57 | 2500 | 340 | 3596.3022 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
207 | Providing and laying Design Mix M40 grade for reinforced concrete works using 20mm graded aggregate in top decks of machine foundations, TG deck etc, at all levels including addition of suitable plastisizers conforming to IS9103 to achieve a slump more than 125 mm in concrete as per manufacturers recomendation, preperation of scheme for concreting, getting it approved by engineer, labour, materials, equipment, handling, batching, transporting, mixing, pumping, placing, leveling, vibrating, compacting, curing, testing, cleaning and rendering the exposed surface with cement sand mortar to give a smooth and even surface, maintaining and submitting records of concreting, petrographic examination and potential reactivity of aggregate etc. all complete as per specification, drawing and instructions of engineer, but excluding formwork, staging, reinforcement, embeddments, UPV test and temperature control of concrete. | CUM | 5518.62 | 1000 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
207a | Extra over item no 206, 206a & 207 above for conducting UPV testing as per IS: 13311 (Part-1). as directed by engineer in charge, including submission of test reports foure copies.Rate to includes all labour charges,staging and other miscellaneous charges etc complete as per specification.If any defect found in UPV test, the same shall be grouted with epoxy pressure grout as directed by the Enginner incharge. , | CUM | 407.01 | 2500 |  |  | 145 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
207b | Extra over It. No. 206, 206a & 207 above, for controlling of temperature of freshly laid concrete to less than 23 degree centigrade using ice, including all related arrangements for providing, storing and mixing of ice with water, cooling of aggregates etc., all complete as per specification, drawing and instruction of engineer in charge. | CUM | 288.84 | 2500 | 10 | 150 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
208 | Screed concrete 1:2:4 conforming to IS 456 with coarse sand and graded hard stone aggregate 12.5mm/6 mm nominal size on the roof, underbed of flooring at any level or thickness complete. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | CUM | 4971.57 | 1600 | 580 | 3231.2715 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
209 | Concrete of grade M-25 in precast works like drain/trench covers, lintels, beams, roof slabs, etc.at all levels in all kinds of work including formwork/moulds, curing, rendering the top exposed surface with cement sand mortar (1:3), handling, storing, transpoting, all leads, erection without damage, setting in position with cement sand mortar (1:3), filling the gaps between adjusant precast units with M30 concrete or cement sand mortar (1:3) and including making of holes for bolts for fixing, welding etc.complete with graded aggregate (20/12.5/10 mm). | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | CUM | 6477.04 | 150 | 225 | 3386.7273 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
212 | Dismantling concrete work for all types of structures at all levels including disposal upto a lead of 1 km, cutting of reinforcement, labour, equipment, safety precautions etc all complete as per drawings, specification and instructions of engineer in charge. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
i) | Plain cement concrete of all grades | CUM | 997.81 | 50 | 350 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ii) | Reinforced cement concrete of all grades | CUM | 1663.02 | 50 | 650 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
212a | Applying Curing Compound of Approved make & Quality to a fresh concrete surface as per standard specification. | SQM | 30.64 | 20000 | 10 | 15 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
213 | Chipping of concrete in reinforced concrete work, cutting pockets, making openings at all levels and according to shapes, disposal of waste materials upto a lead of 1 km as directed by engineer including equipment, safety precautions etc all complete as per specification, drawing, instructions of engineer in charge but excluding cutting of reinforcement | CUDM | 74.4 | 100 | 35 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
214 | Extra over and above St No 213 for cutting of reinforcement, all sizes and types including labour, equipment, return of cut reinforcement to store etc all complete as per specification, drawings and instructions of engineer in charge. | SQM | 6236.34 | 200 | 80 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
300 | SUPPLYING, FIXING AND REMOVING FORMWORK AT ANY ELEVATIONS FOR ALL STRUCTURES, AS PER SPECIFICATIONS AND INCLUDING ALL LABOUR MATERIAL, SCAFFOLDINGS AND CENTEREING COMPLETE INCLUDING POCKETS ETC. FOR THE FOLLOWING: | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
301 | Ordinary form work below finished ground floor level for foundations, footings, bases of columns, walls, columns, pilasters, beams, mass concrete, trenches etc. | SQM | 205.69 | 12000 | 100 | 44 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
302 | Fairface form work below finished ground floor level for foundations, footings, base of columns, walls, columns, pilasters, beams, mass concrete, trenches etc. for exposed concrete works. | SQM | 297.59 | 20000 | 120 | 124 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
303 | Ordinary form work above finished ground floor level for columns, beams, suspended floors, roofs, lintels, cantilevers, staircases, landings, balconies, domes, arches etc. for all heights. | SQM | 288.84 | 15000 | 145 | 44 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
304 | Fairface form work above finished ground floor level for columns, beams, suspended floors, roofs, lintels, cantilevers, staircases, landings, balconies, domes, arches etc. for all heights. | SQM | 385.12 | 25000 | 145 | 124 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
305 | Fairface formwork for Machine foundations/Decks like MDBFP, TDBFP etc at all heights from finished floor level.. | SQM | 1120.35 | 1500 | 320 | 124 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
305 A | Staging and destaging required for all decks like TG & ID etc including submission & approval of design/drawings as per specifications and including all labour, staging materials etc complete. | MT | 10153.2 | 200 | 7000 | 2500 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
305 B | Ornamental/curved shuttering using fairface formwork | SQM | 1190.38 | 1000 | 250 | 124 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
306 | Providing, fixing and removing formwork in block-outs/pockets and openings (below 0.1 sqm contact surface area with concrete) at all elevations including cutting, formation of all shapes and all other operations required for making the required shape and size all complete as per specification, drawing and instruction of engineer in charge. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
i) | Upto 300 mm depth | NOS | 407.01 | 4000 | 60 | 45 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ii) | From 301 mm upto 600 mm depth | NOS | 621.45 | 200 | 60 | 90 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
iii) | From 601 mm upto 1000 mm depth | NOS | 827.14 | 100 | 90 | 149 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
400 | REINFORCEMENTS | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
402 | Straightening, cutting, bending, placing at any level, binding in position high yield strength steel reinforcements in concrete including cost of binding wire, labour,transportation of reinforcement steel from BHEL stores with in the plant boundary to work spot,loading,unloading etc. complete all as per specifications & drawings. | MT | 5426.71 | 2700 | 3300 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
402 a | Extra over item 402 for providing FUSION BONDED EPOXY COATING. The bidder to trasport the steel from BHEL site stores to Vendor plant and bringing back to site and special handling during straightening, cutting, bending, placing and providing PVC coated binding wire. | MT | 9015.34 | 500 |  |  | 8438 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
500 | WATER PROOFING AS PER SPECIFICATIONS. (Contractor has to furnish a guarantee for material and workmanship for a minimum period of 20 years.) | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
501 | Providing and fixing roof water proofing water treatment consisting of nine course of extra heavy duty bitumen felt (type 3 Gr. 1 as per IS:1322 or IS:9918) water proofing. Water proofing will be laid over 100mm thick foam concrete insulation of density 400 kg/cu.m minimum resistivity of 1.17 as per IS:6598 and of required thermal conductivity. This shall be finished with 20mm thick pressed pre-cast concrete tiles on 15mm thick cement sand (1:4) mortar under bed. Rate to include bitumen felt, underbed, foam concrete, finishing layer, material, labour all complete as per specification. | SQM | 1307.67 | 12000 |  | 231 | 1050 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
501b | The membrans used for watering underground structures shall be 7 layered membrane similair to 5 layered roofing membrane, but reinforced with a non-oven polyster mat of minimum 140g/sq.m for additional mechanical strength and covered with additional layer of polymeric asphalt. product to be used shall be MULTIPLAS HYPER or approved equivalent all complete as per specification. | SQM | 704.6 | 1000 |  |  | 550 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
502 | Providing and laying chequered concrete tiles over water proofing of minimum size 200 X 200 and minimum thickness 20 mm confirming to IS 13801 including 15 mm thick cement mortar (1:4) bedding. (water proofing paid else where) | SQM | 542.67 | 500 | 125 | 304 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
503 | Providing two coats of bituminous paint on concrete surfaces in contact with soil in water retaining structures, of grade 85/25 conforming to IS: 702 @ 1.7 kg/sqm for two coats.. | SQM | 161.93 | 6000 | 20 | 90 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
600 | SUPPLYING & INSTALLATION OF JOINT FILLER AND SEALING COMPOUND: | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
601 | Supplying & installation of bitumin impregnated fibre board confirming to IS 1838 as joint filler at joints in concrete including nailing, coating of both faces with coal tar pitch/bitumin, labour, material, equipments etc all complete at all levels as per specification, drawings and instruction of engineer in charge: | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
a | 12mm thick joints. | SQM | 1374.18 | 125 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
b | 20mm thick joints. | SQM | 1689.28 | 10 | 225 | 365 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
c | 25mm thick joints. | SQM | 1877.47 | 65 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
d | 50mm thick joints. | SQM | 2109.41 | 10 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
602 | Supplying and filling in position hot applied bitumin sealing compund(Grade A) confirming to IS 1834 including cleaning, mixing, heating, pouring/injecting sealing copmpound in gaps in joints at all levels including application of primer, labour, material, equipments etc. all complete as per specification/drawing, instruction of engineer in charge. | KGS | 65.65 | 550 | 25 | 45 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
700 | M.S.EMBEDMENTS | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
701 | Supply, fabricating and fixing of embedments MS inserts, pipe sleeves, guide rails, angle pieces, foundation bolts, anchor bolts, rungs of various diameters, plates of dimensions as required including cost of all labour, materials and equipment, transportation, loading, unloading, handling, welding, bolting, cutting, drilling, scaffolding and setting as per specifications and drawings. | MT | 64157.71 | 40 | 15000 | 48300 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
702 | Fixing of embedments, MS inserts, pipe sleeves, rails, guide rails angle pieces, anchor bolts of various diameters, plates of dimensions as required including cost of all labour,materials and equipment for fixing in position,scaffolding and setting in position, transportation from BHEL stores within the plant boundary to work spot, loading, unloading etc. complete as per specifications and drawings.(Only embedments will be provided by BHEL at free of cost) | MT | 23194.81 | 70 | 8500 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
703 | Providing, fabricating, transporting, erecting and installing at all elevations miscellaneous steel/PVC pipes, expansion fasteners in concrete/brickwall, for all kind of works, including the cost of labour, material and equipment, setting material in concrete, layout, scaffoling, handling at site, cutting, forming, grinding, drilling, bolting, welding, jointing, testing etc. all complete as per drawings and specifications and instructions of engineer. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
i | MS pipes of all diameters | KGS | 61.27 | 2000 | 15 | 48.3 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ii | Expansion fasteners (galvanised) of HILTI make or equivalent of safe tension capacity as specified below: | [6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
a | 250 kg | EACH | 166.3 | 125 | 30 | 120 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
b | 500 kg | EACH | 271.34 | 100 | 40 | 200 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
c | 750 kg | EACH | 376.37 | 75 | 50 | 300 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
704 | Supply, fabrication, transportation, delivery at site, erection, installation and allignment of MS foundation bolt (Grade-A of IS:432 & IS:2062) assembly in concrete along with nuts, lock nuts (IS:1363, IS:1364 & IS:3138), anchor plates, stiffner plates, protective tape etc. including labour, materials, euipments, welding, cutting, grinding, threading, drilling, pipe sleeves etc. all complete as per specification, drawing and instruction of the engineer. | MT | 76061.46 | 10 | 15000 | 50000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
705 | Providing all assistance for pre compressing, placing, locking and releasing of vibration isolation system over foundations at all elevations including transportation from BHEL stores, providing necessary staging, platforms,alignment all complete as per drawing and instructions of engineer in charge. | NOS | 621.45 | 20 | 425 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
800 | GROUTING AS PER SPECIFICATION FOR THE FOLLOWING: | [6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
801 | Providing & grouting cement slurry mix at any elevation/depth with pressure pump for water retaining concrete structures, including fixing nozzles, cost of approved cement, admixture, curing, etc all complete as per specification and as directed by the Engineer. | CUM | 1707.67 | 5 | 250 | 1250 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
802 | Providing and grouting of pocket holes, pipe sleeves of any shape and size under base plates after erection of necessary structural steel work, machinery with mix 1:1:2 (one part Cement : 1part Sand : 2 parts of 6mm down graded stone chips) at any elevation including roughening surface, cleaning, ramming, curing etc complete (non-shrink hand grout using approved admixture) as per specification and as directed by the Engineer. | CUM | 10302 | 10 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
803 | Providing & grouting of pocket holes, pipe sleeves of any shape and size under base plates after erection of necessary structural steel work, machinery with mix 1:1( 1 part cement : 1part sand) at any elevation including roughening surface, cleaning, ramming, curing etc complete (non-shrink flowable grout as per specification using approved admixture) as per specification and as directed by the Engineer. | CUM | 12665.24 | 10 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
804 | Providing & grouting of pocket holes, pipe sleeves of any shape and size under base plate after erection and alignment if necessary, structural steel work, machinery at any elevations including roughening surface, cleaning, ramming, curing, etcwith Sika grout-104/ Anchor NSG/CobextraGP-2/CobextraGP-1/Pidigrout10/Pagel or equivalent all complete as per specifications. (Cost of all material and clearning the pocket by compressed air shall be in the scope of the contractor). | CUM | 57164.26 | 10 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
900 | DOORS, WINDOWS, VENTILATORS, LOUVERS, ROOF VENTILATORS, ROLLING SHUTTERS, PARTIONS ETC. COMPLETE AT ALL ELEVATION INCLUDING FRAMING, KICK PLATES, STOPPERS AS PER SPECIFICATION AND DRAWINGS (all steel doors, windows and rolling shutters etc.shall be blast cleaned to near white metal surface (Sa 2 1/2), painted with two coat of red oxide zinc primer and finished with two coats of synthetic enamel paint confirming to IS2074) | [6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
901 | Providing, fitting and fixing solid core flush door shutter as per IS2202 part II, 45 mm thick homogeneous particle board (decorative veneer prelaminated on both sides) bonded with BWP type phenol formaldehyde synthetic resin, particle board core conforming to IS3087 type I, teak wood beading all around including preperation of working drawings, doors frame, shutter, butt hinges, tower bolt, sliding bolt handles, knobs, door stoppers (all fitting shall be anodised aluminium color dyed), screws etc complete as per drawing, specification and instructions of engineer in charge. | SQM | 1978.12 | 100 | 200 | 1985 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
901A | Providing and fixing 12 mm thick particle board, decorative veneer (prelaminated) on both sides, as panels in aluminium framed door shutter, fixed with necessary snap-on-beading (excluding the cost of aluminium works). | SQM | 1461.71 | 100 |  |  | 850 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
902 | Providing and fixing openable/fixed steel windows and ventilators with steel sections as per IS:1361 including wire mesh, painting with minimum 2 coats of synthetic enamel paint on primer complete. | SQM | 2109.41 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 902 |  | 1476.59 | 600 |  | 950 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 902 |  | 632.82 | 600 | 220 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
903 | Providing and fixing steel single or double door shutters. Shutters shall be 45mm thk flush design comprising of two outer sheets of 18 gauge steel sheets rigidly connected and reinforced inside with continuous vertical 20 gauge stiffeners, spot welded in position at not more than 150mm on centers side, top, bottom edges of shutter shall be of pressed steel channels of 1.2mm thk voids to be filled with mineral wool (48 kg/cum density) confirming to IS-1038& IS-4351 including all fittings like tower bolts, handles, stoppers, aldrops etc. and painting with minimum 2 coats of synthetic enamel paint on primer complete. | SQM | 4673.97 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 903 |  | 3271.78 | 310 |  | 3420 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 903 |  | 1402.19 | 310 | 220 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
904 | Providing and fixing fire proof steel doors (single or double shutter) with panic devices shall be 45mm thk flush design comprising of two outer sheets of 18 gauge steel sheets rigidly connected and reinforced inside with continuous vertical 20 gauge stiffeners, spot welded in position at not more than 150mm on centers including all fittings, shop painting with approved post office/signal red color fire resistant paint and mineral wool insulation (64 kg/cum density) complete and shall be fire proof as per IS:3614, TAC requirements and as per specification. Minimum ratings shall be 2 Hrs. | SQM | 9356.7 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 904 |  | 6549.69 | 250 | 0 | 7500 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 904 |  | 2807.01 | 250 | 250 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
905 | Providing and fixing anodised aluminium work for doors, windows, ventillators and partitions etc with extruded standard tubular and other sections including all fittings & fixtures and accessories,swing type or sliding type of approved make conforming to IS733 and IS1285, anodised and electro color dyed to required shade according to IS 1868 (minimum anodic coating of grade AC15), fixed with rawl plugs, expansion fasteners, screws or with fixing clips, including necessary fillinf of gaps at junctions, at top, bottom and sides with required PVC/neoprene felt for bi-mettalic protection etc. | SQM | 301.97 | 2500 |  |  | 2750 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| including preperation of working drawings, aluminium cleat angle, aluminium snap-on-beading for glazing/panelling, stair case tread nosing, with all fittings and fixtures (like tower bolts, handles, door stopper with rubber shoes, 'L' drops, stays, floor springs, hydraulic door closures etc.), CP brass/stailess steel screws, providing and fixing hinges/pivots, and making provision for fixing of fitting wherever required including cost of PVC/neoprene gasket, all complete as per drawing, specification and instructions of engineer in charge (hydraulic door closers, Glazing and panelling shall be paid seperately). | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
906 | Providing and fixing of over head hydraulic door closers confirming to IS-3564 of approved make & quality as directed by Engineer. | NOS | 971.56 | 300 |  |  | 850 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
907 | Providing and fixing floor mounted Hydraulic door closer confirming to IS-3564 of approved make & quality as directed by engineer | NOS | 3299.79 | 20 |  |  | 2450 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
908 | Providing and fixing pressed steel frames fabricated from 18 gauge M.S sheet mortised, reinforced strikes, hold fasts, adjustable floor anchors, floor tiles/weather bars etc. confirming to IS-4351 complete as per specifications. | KGS | 87.53 | 9000 | 15 | 65 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
909 | Providing and fixing in position rolling shutters of approved make as per IS 6248, made of 75 x18g M.S laths interlocked together through their entire length and jointed together at the end by end locks mounted on specially designed pipe shaft with brackets, side guides and arrangements for inside and outside locking with push and pull operation including wire springs top cover, 3coats of approved enamel paint etc., all complete as per specification- Hand operated. | SQM | 2118.17 | 500 | 220 | 1650 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
910 | Providing and fixing in position rolling shutters of approved make as per IS 6248, made of 75 x18g M.S laths interlocked together through their entire length and jointed together at the end by end locks mounted on specially designed pipe shaft with brackets, side guides and arrangements for inside and outside locking with push and pull operation including wire springs top cover, 3coats of approved enamel paint etc., all complete as per specification- Mechanically operated. | SQM | 2328.23 | 100 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 910 |  | 1629.76 | 100 |  | 2050 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 910 |  | 698.47 | 100 | 230 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
911 | Providing and fixing in position rolling shutters of approved make as per IS 6248, made of 75 x18g M.S laths interlocked together through their entire length and jointed together at the end by end locks mounted on specially designed pipe shaft with brackets, side guides and arrangements for inside and outside locking with push and pull operation including wire springs top cover, 3 coats of approved enamel paint etc., all complete as per specification- Electrically operated. | SQM | 4490.16 | 100 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 911 |  | 3143.11 | 100 |  | 4000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 911 |  | 1347.05 | 100 | 250 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
912 | Providing, fabricating and fixing in position window grills as per approved design pattern at all elevations and of all sizes including with or wihtout openings for operating window handles with all labour, material. Handling, equipment complete etc as per specification, drawing and instructions of engineer in charge. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
i) | Made of anodised aluminium sections | SQM | 2194.46 | 150 |  |  | 1200 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
913 | Providing, fitting and fixing of glazing including poly carbonate sheet of superior (selected) quality, first grade class, at various elevations, where required, cleaning after fixing, with all labour and material etc. complete as per specification, drawing and instructions of engineer in charge. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
i) | 4 mm ground/frosted glass | SQM | 367.62 | 300 |  |  | 400 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ii) | 5.5 mm flat transparent sheet glass as per IS:2835 | SQM | 507.66 | 100 |  |  | 450 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
iii) | 5.5 mm clear float glass as per IS:2835 | SQM | 568.93 | 1200 |  |  | 450 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
iv) | 6 mm wired glass as per IS: 5437 | SQM | 621.45 | 1100 |  |  | 550 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
v) | 6 mm thick polycarbonate sheet multi (twin) wall fire retardant and ultra violet resistant with sealed open edges. | SQM | 1759.3 | 200 |  |  | 800 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
vi) | 5.5 mm tinted glass | SQM | 621.45 | 120 |  |  | 700 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
vii) | Two nos. 6 mm thick clear toughened safety glass conforming to IS: 2553 hermetically sealed and seperated by 12 mm thick gap for thermal insulation. | SQM | 2083.16 | 400 |  |  | 2000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
914 | Providing, fitting and fixing heavy duty minimum six lever mortised lock of godrej or equivalent make with handles or knobs to single and double leaf door (wooden/steel/aluminium) with duplicate set of keys and masterkeyed locks, openable from one side by the key and from the other side by the handle etc. all complete as per drawing, specification and instruction of engineer in charge. | EACH | 936.55 | 50 |  |  | 750 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
915 | Providing and fixing PVC doors of sintex or equivalent make including all fitting & fixtures as per specification, drawing and instructions of engineer in charge. | SQM | 2153.18 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 915 |  | 1507.23 | 150 |  | 1800 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 915 |  | 645.95 | 150 | 250 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1000 | BRICKWORK MASONRY INCLUDING SUPPLY OF MATERIAL, COST OF LABOUR ETC. COMPLETE, AS PER SPECIFICATIONS. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
1001 | Providing brick work in cement mortar 1:6 (1 part cement 6 parts coarse sand) in walls, chambers etc. in thickness varying from 230mm to 460mm at all depths, places and positions below plinth including raking out joints, curing, scaffolding etc. complete excluding plastering and painting.(Bricks shall be of class designation 50kg/Sq cm of nominal dimensions as per IS-1077 .) | CUM | 3203.51 | 5000 | 450 | 3654 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1001a | Providing brick work in cement mortar 1:6 (1 part cement 6 parts coarse sand) in walls, chambers etc. in thickness varying from 230mm to 460mm at all depths, places and positions below plinth including raking out joints, curing, scaffolding etc. complete excluding plastering and painting.(Fly ash Bricks shall be of min 50kg/Sq cm of nominal dimensions as per IS-12894.) | CUM | 2914.67 | 500 | 450 | 2850 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1002 | Providing brick work in cement mortar 1:5 (1 cement 5 coarse sand) in walls, chambers etc. in thickness 254mm at all heights, places and position above plinth including raking out joints, curing, scaffolding etc complete excluding plastering and painting. (Bricks shall be of class designation 50kg/Sq cm of nominal dimensions as per IS-1077.) | CUM | 3658.65 | 2000 | 550 | 3654 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1004 | Providing brick work in cement mortar 1:4 (1 cement 4 coarse sand) in partition walls, chambers etc. in thickness 127mm at all heights, places and position above or below plinth/graded level including reinforcing with 2nos 8mm rod at every 4th course, raking out joints, curing, scaffolding etc complete including materials, labour etc, excluding plastering and painting as per specification.(Bricks shall be of class designation 50kg/Sq cm of nominal dimensions as per IS-1077.) | SQM | 564.56 | 1500 | 75 | 420.21 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1004 a | Providing brick work in cement mortar 1:4 (1 cement 4 coarse sand) in partition walls, chambers etc. in thickness 127mm at all heights, places and position above or below plinth/graded level including reinforcing with 2nos 8mm rod at every 4th course, raking out joints, curing, scaffolding etc complete including materials, labour etc, excluding plastering and painting as per specification.(Fly ash Bricks shall be of min 50kg/Sq cm of nominal dimensions as per IS-12894.) | SQM | 529.55 | 500 | 75 | 327.75 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1008 | Breaking of existing brick work with plastering at all levels including plastering, removing the rubbish up to a distance of 1KM including transportation, loading, unloading etc. all complete as directed by the engineer. | CUM | 582.06 | 100 | 200 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1009 | Breaking of existing brick partition wall with plastering at all levels including plastering, cutting of reinforcement, removing the rubbish up to a distance of 1KM including transportation, loading, unloading etc. all complete as directed by the engineer. | SQM | 83.16 | 100 | 46 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1010 | Providing and encasing of structural steel member with masonary work around flanges, webs etc. and filling the gap between steel and masonry by minimum 12mm thick mortar. Encased member shall be wrapped with checken wire mesh with 50mm lap etc. complete as per specification. | CUM | 3859.97 | 100 | 550 | 3654 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1012 | Making openings in existing brick wall or partition wall at all heights including making good the broken edges/surface with cement mortar etc. complete. | CUM | 748.37 | 100 | 500 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1013 | Supply and placing in position mild steel wire fabric/ GI wall ties of square mesh 25 mm/GI wall ties 4mm thick, 50mm wide & 200mm long and wire diameter of 2 mm/GI wall ties for encasing of steel sections/bonding masonry units with concrete or steel columns in concrete including cutting, bending, fixing etc. complete. | SQM | 310.73 | 3000 | 10 | 225 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1014 | Providing and filling brick bats in under plinth protection, soak pits etc. | CUM | 490.15 | 1000 | 100 | 350 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1100 | DAMP PROOF COURSE INCLUDING ALL MATERIALS LABOUR, SHUTTERING, CENTERING, CURING ETC., COMPLETE WITH THICKNESS AS SPECIFIED/SHOWN ON DRAWINGS. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
1101 | Damp Proof Course 50 mm thk. 1:1.5:3concrete (6mm down aggregate) with 2% of approved admixture of water proofing compound. Hot bitumen @ 1.7Kg./sqm shall be applied before & after the DPC as per specification. | SQM | 315.1 | 1000 | 45 | 270 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1200 | CEMENT MORTOR PLASTER INCLUDING ALL MATERIALS SCAFFOLDING, CURING ETC. COMPLETE AS PER SPECIFICATION | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
1201 | Providing 12 mm thick plaster in cement mortar 1:6 on the even side of internal walls, finished to a smooth finish as per specification. | SQM | 105.03 | 25000 | 55 | 39 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1202 | Providing 18 mm thick plaster in cement mortar 1:6 on the uneven side of internal walls, with a smooth finish as per specification. | SQM | 144.43 | 7000 | 79 | 59 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1204 | Providing 20 mm thick plaster in two layers, under layer 14 mm thick in cement mortar 1:6 and top layer 6 mm thick in cement mortar 1:4 with approved water proofing compound on walls finished to a wooden float/smooth/rough finish as per specification. | SQM | 179.44 | 20000 | 72 | 66 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1205 | Providing 6mm thick plaster in cement mortar 1:4 on ceilings finished to a smooth finish as per specification. | SQM | 105.03 | 12000 | 79 | 20 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1206 | Providing and making decorative plaster over existing plastered surface of all types and design on walls, ceilings, arcs, columns with various thickness upto 20 mm including finishing all complete. | SQM | 231.95 | 1100 | 125 | 70 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1207 | Providing Plaster of Paris 2 mm thick punning over finished plaster surface and finished with smooth surface as per specification. | SQM | 52.52 | 1000 |  |  | 60 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1208 | Providing screed/grading plaster of average 20 mm thickness in ratio 1:6 nominal by volume including finishing smooth and even etc. all complete at all levels above or below grade level. | SQM | 135.67 | 15000 | 65 | 66 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1209 | Providing and making decorative interior plaster of heritage finish over existing plastered surface of all types and design on walls, ceilings, arcs, columns including finishing all complete. | SQM | 205.69 | 1000 |  |  | 150 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1210 | Forming groove of uniform size from 12X12 mm upto 20X15 mm in plastered surface as per approved pattern, using wooden battens nailed to the under layer, including removal of wooden battons, repair of the edges of plaster panel and finishing the groove etc. complete as per specification, drawing and the instructions of engineer in charge. | RM | 26.26 | 1000 |  |  | 12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1212 | Providing and laying encasement to box type steel beams at all levels with lath plaster 20 mm nominal thickness with cement plaster (1:4) over galvanised hexagonal chicken wire of 0.9 mm wire diameter and 19 mm mesh size as per IS3150 including all labour, materials, equipment, handling, transporting, mixing, placing, leveling, curing and cleaning, finishing the exposed surfaces etc including centering and shuttering all complete as per specification, drawing and instructions of enginner in charge (rate shall include the cost of GI chicken wire mesh) | SQM | 113.79 | 1000 | 45 | 66 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1300 | FINISHES, PAINTING TO CONCRETE, PLASTERED SURFACES, SURFACE PREPARATION INCLUDING ALL MATERIALS, LABOUR, SCAFFOLDING ETC. ALL COMPLETE | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
1301 | Providing and applying Two or more coats of white wash with lime to give an even shade including a priming coat on ceilings as per specifications. | SQM | 11.38 | 6000 |  |  | 10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1302 | Providing and applying Two or more coats of water bound distemper of approved brand and manufacture to give an even shade including a priming coat on ceilings as per specifications. | SQM | 74.4 | 10000 |  |  | 55 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1303 | Providing and applying two oil bound distemper as per IS 428 of approved brand, shade and manufacture to give smooth, hard, durable & glossy finish over a coat of primer over prepared plaster surface as per manufacturers guideline including plaster of paris punning minimum 2 mm. | SQM | 74.4 | 15000 |  |  | 55 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1306 | Providing and applying two coats of acid/alkali resistant chlorinated rubber paint of approved brand and colour to floors, walls and ceiling including preparation of surface to receive paint, providing and applying bitumen primer confirming to IS 158 complete all as per manufacturer's recommendations and as approved by engineer, at all heights above or below grade level, complete as per specifications. | SQM | 376.37 | 1000 |  |  | 350 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1307 | Providing and applying two coats of fire resistant transparent paint as per IS: 162 over french polish as per IS: 348 on all woodwork as per specifications. | SQM | 407.01 | 750 |  |  | 375 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1308 | Providing and applying Two coats of oil resistant paints epoxy based 150 micron over primer of approved grade and manufacture to give an even shade. | SQM | 407.01 | 1500 |  |  | 375 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1309 | Providing and applying two coats of acrylic emulsion paint as per IS 5411 of approved brand, shade and manufacture to give smooth, hard, durable & glossy finish over a coat of primer over prepared plaster surface as per manufacturers guideline including plaster of paris punning minimum 2 mm. | SQM | 118.17 | 4000 |  |  | 95 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1310 | Providing and fixing terracota tiles of thickness 6 to 8mm over the wall as per approved and of approved size, colour and make as per specification and drawings. | SQM | 376.37 | 300 | 150 | 190.957 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1311 | Providing and applying resin bonded granular textured finish, for external applications shall consist of crushed stone/quartz chips of .5 mm to 2.5 mm size and of approved natural color/shade and bonded with synthetic resins, adhesives and additives altogether in a single pack mix, applied on cured and dried plaster surface with a dry film thickness of minimum 2 mm. The final finish shall have UV resistance, fungus, bacterial resistance properties all complete with grooves filled with poly sulfide sealant of matching color and shade as per specification/drawing/approval of engineer in charge. | SQM | 271.34 | 1500 |  |  | 225 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1312 | Providing and applying three coats of water proof cement paint of approved make and color on exterior surface at all heights including material, labour, scaffolding, curing etc complete as per specification. | SQM | 48.14 | 10000 |  |  | 30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1400 | FLOORING AND SKIRTING INCLUDING ALL MATERIALS, LABOUR, CURING, POLISHING, FINISHING, EXPANSION JOINTS, GROOVES, ETC. COMPLETE IN ALL RESPECTS AS SHOWN ON DRAWINGS AND DESCRIBED IN SPECIFICATIONS. (Under bed to be paid seperately under relevant item) | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
1401 | Providing and laying 50 mm thick granolithic flooring (cement concrete flooring in 1:1:2 ) with non metallic hardener pigmented topping of 12 mm thick in flooring complete as per specification. | SQM | 446.39 | 5000 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % rate of above item 1401 | SQM | 312.47 | 5000 |  | 258.068 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % rate of above item 1401 | SQM | 133.92 | 5000 | 65 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1402 | Providing and laying 25 mm thick granolithic flooring (cement concrete flooring in 1:1:2 ) with non metallic hardener pigmented topping of 10 mm thick in skirting and dado complete as per specification. | SQM | 315.1 | 2000 | 65 | 183.143 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1403 | Providing and laying precast polished heavy duty cement concrete tiles (Carborundum) of size 300X300X25 thick of approved shade as per IS 1237, laid in floors and landings, jointed with neat cement slurry with pigment to match the shade of the tiles including rubbing and polishing complete with laying as per IS 1443. | SQM | 800.88 | 1000 | 150 | 488.4 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1404 | Providing and laying precast polished heavy duty cement concrete tiles (Carborundum) of size 300X300X25 thick of approved shade as per IS 1237, laid in skirting and dado, jointed with neat cement slurry with pigment to match the shade of the tiles including rubbing and polishing complete with laying as per IS 1443. | SQM | 779 | 200 | 150 | 474.064 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1405 | Providing and laying interlocking M30 concrete blocks of thickness 60 mm as paving of approved colour and pattern and should be laid on the subbase and bedding as per specifications and recommendations of manufacturer. | SQM | 582.06 | 500 | 100 | 437.45 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1406 | Providing and laying removable false flooring with fire resistant particle board panels bonded by phenol formaldehyde of size 600x600x35mm with all panel edges finished to a tolerance of +/- 0.2 mm including 2 mm thick anti static PVC top and lipping, supporting arrangement as per specification, drawings and engineer in charge. | SQM | 5102.86 | 1000 |  |  | 3500 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1407 | Providing & fixing chemical resistant (Acid & Alkali) Tiles as per IS 4860 of minimum thickness 38 mm thick in flooring/Dado. The tiles shall be abrasion resistant and durable. The potassium silicate 6 mm thick mortar as per IS 4832 used for setting or for under bed shall be durable strong and chemical resistant epoxy mortar including pointing etc. after laying bitumen primer as per IS 158 and 12 mm thick bitumastic as per IS 9510 and IS 412 complete as per specification. | SQM | 2555.81 | 1200 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1408 | Providing & fixing chemical resistant (Acid & Alkali) Tiles as per IS 4457 of minimum thickness 25 mm thick in flooring/Dado. The tiles shall be abrasion resistant and durable. The potassium silicate as per IS 4832,6 mm thick mortar used for setting or for under bed shall be durable strong and chemical resistant epoxy mortar including pointing etc. after laying bitumen primer as per IS 158 and 12 mm thick bitumastic complete as per IS 9510 and IS 412 and as per specification. | SQM | 2582.06 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 1408 |  | 1807.44 | 500 |  | 1262.8 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 1408 |  | 774.62 | 500 | 541.2 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1409 | Providing & fixing chemical resistant (Acid & Alkali) bricks (75 mm thk) as per IS 4860 in the floor of neutralization pit. Surface on which lining has to be applied shall be prepared in accordance with IS 2395. Bitumen primer as per IS 158 followed by 18 mm thk Bitumuinastic followed by 6 mm thk potassium silicate mortar bedding shall be provided before laying AR bricks. The joints between AR bricks shall be filled with resin type of mortar confirming to IS 4832, Part II. Seal coat of readymade epoxy paint shall be provided on joints to cover up any porosity that may be left in mortar. End ceiling shall be done with bitumastic. A.R. bricks shall be laid with 6 mm wide and 20 mm deep pointing ( epoxy/furane/CNSL ) and acid curing shall be done complete as per specification. | SQM | 3689.29 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 1409 |  | 2582.5 | 500 |  | 1755.6 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 1409 |  | 1106.79 | 500 | 752.4 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1410 | Providing & fixing chemical resistant (Acid & Alkali) bricks (115 mm thk) as per IS 4860 in the walls of neutralization pit. Surface on which lining has to be applied shall be prepared in accordance with IS 2395. Bitumen primer as per IS 158 followed by 18 mm thk Bitumuinastic followed by 6 mm thk potassium silicate mortar bedding shall be provided before laying AR bricks. The joints between AR bricks shall be filled with resin type of mortar confirming to IS 4832, Part II. Seal coat of readymade epoxy paint shall be provided on joints to cover up any porosity that may be left in mortar. End ceiling shall be done with bitumastic. A.R. bricks shall be laid with 6 mm wide and 20 mm deep pointing ( epoxy/furane/CNSL ) and acid curing shall be done complete as per specification. | SQM | 4577.69 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 1410 |  | 3204.38 | 750 |  | 2371.6 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 1410 |  | 1373.31 | 750 | 1016.4 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1412 | Providing and laying polished Kota stone 20 mm thk in flooring. The kota stone slabs/tiles laid over under bed, pressed and tapped down with wooden mallet to the proper level, lifted and pressed again with thick cement slurry spread over the surface with fine joint finished including pigments, curing, grinding, granite polishing etc. complete. | SQM | 866.52 | 500 | 257.5 | 750 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1413 | Providing polished Kota stone 20 mm thk in skirting projecting 6mm from adjacent plaster all complete . | SQM | 897.16 | 100 | 515 | 750 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1414 | Providing and laying polished Granite stone/thandur blue slab of approved color and texture 20 mm thk in flooring. The granite stone slabs laid over under bed, pressed and tapped down with wooden mallet to the proper level, lifted and pressed again with thick cement slurry spread over the surface with fine joint finished including pigments, curing, grinding, granite polishing etc. complete . | SQM | 2678.34 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 1414 |  | 1874.84 | 3000 |  | 1550 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 1414 |  | 803.5 | 3000 | 504.7 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1415 | Providing and laying polished Granite stone/thandur blue slab 20 thk in skirting, facia and dado including pigments, curing, grinding, granite polishing etc. complete. | SQM | 2678.34 | 500 | 504.7 | 1550 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1416 | Providing and laying 7 mm thk Vitrified/heavy duty ceramic tiles of matt finish of size 300x300mm from reputed manufacturer in approved shade and colour, complete as per specification. | SQM | 975 | 1000 | 154.5 | 588.41 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1416 A | Providing and laying 7 mm thk Vitrified/heavy duty ceramic tiles of matt finish of size 600x600mm from reputed manufacturer in approved shade and colour, complete as per specification. | SQM | 1229.77 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 1416A |  | 860.84 | 1200 |  | 678.41 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 1416A |  | 368.93 | 1200 | 154.5 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1417 | Providing and laying min 5 mm thk glazed tiles in dado as per IS: 777 from reputed manufacturer, complete as per specification. | SQM | 485.78 | 1000 | 154.5 | 250.91 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1420 | Providing and laying granite stone slab of 20mm thickness single piece for wash basin slab, wall of black or approved colour with cutting and opening complete. | SQM | 2678.34 | 75 | 504.7 | 1550 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1422 | Providing and laying decorative colored Ceramic Tiles 5mm thick in dado of reputed manufacturer of approved finish shade and colour. | SQM | 582.06 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 1422 |  | 407.44 | 1200 |  | 318.41 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 1422 |  | 174.62 | 1200 | 154.5 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1423 | Providing and laying 50 mm thick granolithic flooring (cement concrete flooring in 1:1:2 ) without hardener complete as per specification. | SQM | 363.24 | 20000 | 65 | 195 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1425 | Providing and laying of PVC floor tiles & skirting of minimum thickness 2 mm anti static flexible tiles as per IS 3462 and IS 5318 including preparation of surface to receive pvc floor tiles. | SQM | 560.18 | 1500 | 125 | 387.5 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1428 | Providing and laying terrazo tiles of size 250x250x20 mm of approved shade with marble chips of sizes upto 6 mm laid in floors, skirtings and landings, jointed with neat cement slurry with pigment to match the shade of tiles including rubbing and polishing complete. | SQM | 643.33 | 1500 | 150 | 363.41 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1429 | Providing and laying 25 mm thick cast in situ terrazo finish consisting of marble chips of size 1 mm to 12 mm nominal size laid in white/grey cement or mixture of both in propotion 1:1.5 (1 part cement, 1.5 parts chips) with marble powder 3:1 (3 parts cement, 1 part marble powder) in propotion mix dry in cement including pigments, rubbing, grinding, polishing etc in floors, skirtings, treads, risers and landings complete. | SQM | 385.12 | 300 | 150 | 206.3 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1430 | Providing and fixing dividing strips in joints of cast in situ floorings at various elevations, finishing, all labour, material etc. complete as per drawing, specification and instructions of engineer in charge. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
i) | Glass strips 40 mm wide and minimum 6 mm thick. | RM | 17.51 | 50 | 2 | 9 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ii) | Aluminium strips 40 mm wide and min 3 mm thick | RM | 78.77 | 50 | 2 | 63 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
iii) | Brass strips 20 mm wide and minimum 4 mm thick. | RM | 56.9 | 250 | 2 | 45 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1500 | PROVIDING AND ERECTING ROOFING/SIDE CLADDING INCLUDING LAPS, SCAFFOLDING HOOKS, WASHERS, CORNER PIECES, ETC. COST OF ALL MATERIAL, LABOUR, EQUIPMENT, CLEATS, SHEETING RUNNER, RAILS MILD STEEL WIND TIES (HORIZONTAL/VERTICAL) AND ANY OTHER STEEL WORKS ETC. COMPLETE FOR THE FOLLOWING: | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
1501 | Designing, providing and fixing permanently color coated galvanised MS troughed metal sheet decking plate with silicon modified polyster paint of DFT 20 micron on the exposed face over roof purlins as per relevant IS code and specification. Thickness of deck plate shall be 0.5 to 0.8mm with minimum trough depth of 38mm to 44mm and shall serve as permanent shuttering to the cast-in-situ roof slab 100mm thick measured over crest of metal decking & shall have adequate strength to support weight of green concrete and imposed loads during construction spanning between purlins as per manufacturer's recommendations/ calculations/ test certificates for approval including fixing of plates to purlins, side lapping, end lapping etc.complete as per engineers approval and specification. | SQM | 945.3 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| (height of trough required as per design should be included in the cost). M.S. Trough decking plate shall be connected to the top surface of the purlin, top chord of truss with self tapping self drilling white zinc plated heat treated high carbon steel screws of min 5.6mm diameter at spacing of 390mm C/c in the trough and sealing it with epoxy sealent including | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| all material, labour, tools, etc complete. Measurement shall be of the plan area of roof covered by MS trough metal decking. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 1501 |  | 661.71 | 6000 |  | 625 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 1501 |  | 283.59 | 6000 | 100 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1502 | Designing, providing and fixing permanently color coated galvanised MS troughed metal sheet decking plate with silicon modified polyster paint of DFT 20 micron on the exposed face over roof purlins as per relevant IS code and specification. Thickness of deck plate shall be 0.8 to 1 mm with minimum trough depth of 38 to 75 mm and shall serve as permanent shuttering to the cast-in-situ intermediate slab 100mm thick measured over crest of metal decking & shall have adequate strength to support weight of green concrete and imposed loads during construction spanning between purlins as per manufacturer's recommendations/ calculations/ test certificates for approval including fixing of plates to purlins, side lapping, end lapping etc.complete as per engineers approval and specification. | SQM | 1164.12 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| (height of trough required as per design should be included in the cost). M.S. Trough decking plate shall be connected to the top surface of the purlin, top chord of truss with self tapping self drilling white zinc plated heat treated high carbon steel screws of min 5.6mm diameter at spacing of 390mm C/c in the trough and sealing it with epoxy sealent including | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| all material, labour, tools, etc complete. Measurement shall be of the plan area of roof covered by MS trough metal decking. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 1502 |  | 814.88 | 1000 |  | 655 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 1502 |  | 349.24 | 1000 | 100 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1503 | Design supply & erection of permanent colour coated thermally insulated sandwitched metal cladding for external walls with troughed galvanised MS sheeting of 0.6mm thickness and 275 g/sqm of galvanisation or Hi tensile steel (550 Mpa) 0.5 mm thick, coated with zinc aluminium alloy @ 150 g/sqm. Outer exposed face shall be permanently colour coated with PVF2 of DFT 20 microns over primer having life span sustenance against weathering action, inner side of external sheeting shall have 7 micron of precoating. sandwitched Insulation of minimum 50mm thick bonded mineral wool blanket conforming to IS 8183 (minimum density of 32 kg/cum for glass wool and 48 kg/cum for rock wool or 40-45 Kg/cum for polyuretene foam(fire retardants and non-toxic) confirming to IS 12436 , Inner sheet shall consist of 0.6 mm thick galvanised, MS permanently colour coated sheet with 20 micron DFT coating of silicone modified polymer paint on exposed face and 7 microns DFT coating on inner face and rate of galvanising as 150 gm/sqm , cladding shall be fixed to | SQM | 1562.37 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| supports/rails by concealed fixing system with corrosion resistant self tapping/self drilling type fasteners provided with suitable cap. Flashing shall have the same material and minimum overlap of 100 mm. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 1503 |  | 1093.66 | 5300 |  | 1150 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 1503 |  | 468.71 | 5300 | 255 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1504 | Design supply & erection of permanent colour coated non insulated metal cladding for external walls with troughed galvanized MS sheeting of 0.6mm thickness and 275 g/sqm of galvanization or Hi tensile steel (550 Mpa) 0.5 mm thick, coated with zinc aluminium alloy @ 150 g/sqm. Outer exposed face shall have PVF2 coating of DFT 20 microns over primer having life span sustenance against weathering action, inner side shall be coated with same paint of minimum DFT 12 microns over primer. Cladding shall be fixed to supports/rails by concealed fixing system with corrosion resistant self tapping/self drilling type fasteners provided with suitable cap. Flashing shall have the same material and minimum overlap of 100 mm. | SQM | 726.48 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 1504 |  | 508.536 | 5600 |  | 580 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 1504 |  | 217.944 | 5600 | 110 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1505 | Providing and installing under deck insulation comprising of 50 thick resin bonded mineral wool insulation mat conforming to IS: 8183. This mat shall be backed with minimum 0.05 mm thick aluminium foil and 24Gx25 mm wire mesh netting. This shall be fixed to ceiling or wall as the case may be with 100x50x6 slotted mild steel plaie welded to MS plate inserts embedded at the soffit of the slab at 600 mm c/c and 14 G steel wire drawn through slots and fixed to wire nettingas per specification, drawing and instructions of engineer in charge. | SQM | 595.19 | 4200 |  |  | 475 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1506 | Providing and laying of Translucent sheeting where required to be fixed on the walls with suitable laps, sealent & leak proof as per specification, drawing and instructions of engineer in charge. | SQM | 1295.41 | 500 |  |  | 800 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1600 | PROVIDING AND FIXING FALSE CEILING INCLUDING SUPPLY OF CEILING MATERIAL, WORKING LAYOUT DRAWINGS AND DETAILS, SUSPENSION SYSTEM AND ALL OTHER MATERIALS REQUIRED FOR THE WORK INCLUDING MAKING RECCESS FOR LIGHT FIXTURES, ALUMINIUM DIFUSERS, FIRE ALARMS ETC., POLISHING/PAINTINGS, LABOUR ETC., ALL COMPLETE AS PER SPECIFICATION. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
1601 | Providing and fixing cement bonded particle board false ceiling system consisting of 600x600x12 mm board with one coat of primer and two coats of acrylic emulsion paint with suspension system consisting of 6 mm dia galvanised steel rods suspended from ceiling supporting aluminium grid of 38x25x1.5 mm and cross tie of 25x25x1.5mm and aluminium angle of 25x25x1.5 mm suspended from RCC slab/structural steel or catwalkway grid above with special height adjustment clips, including preperation of working drawing, providing openings for AC ducts, return air grills, light fixtures etc (but excluding the cost of catwalkway grid) all complete as per drawings, specification and instructions of the engineer. | SQM | 809.63 | 1500 |  |  | 650 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1601-a | with 12mm thick gypsum board and balance specification as per 1601 | SQM | 704.6 | 500 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 70 % Alone for Supply (Item 1601-a) | SQM | 493.22 | 500 |  |  | 385 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 30 % Alone for Fixing (Item 1601-a) | SQM | 211.38 | 500 |  |  | 165 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1602 | Providing and fixing Aluminium false ceiling system comprising of 75mm or 150 mm wide and 12.5 mm deep, 5m panel length closed type plain panels of approved colour, roll formed out of 0.5 mm thick corrosion resistant aluminium alloy AA3005- 131mm wide strip fixed on roll formed carriers, suspended from RCC slab/structural steel or catwalkway steel channel grid above with 4mm (minimum) galvanised wires (rods) with special height adjustment clips, including preperation of working drawings, providing openings for AC ducts, return air grills, light fixtures etc but excluding the cost of catwalkway all complete as per drawings, specifications and instructions of engineer | SQM | 1838.08 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 70 % Alone for Supply (Item 1602) |  | 1286.66 | 3000 |  |  | 840 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 30 % Alone for Fixing (Item 1602) |  | 551.42 | 3000 |  |  | 360 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1700 | PROVIDING AND FIXING RAIN WATER DOWN TAKE PIPES INCLUDING 2 COATS OF APPROVED PAINT OVER A PRIMARY COAT, ALL SPECIALS AND ACCESSORIES ETC. COMPLETE AS PER SPECIFICATION. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
1701 | GI down take pipes conforming to IS1239/IS3589 as per specification of following dia. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
1701-'i) | 100 mm dia | RM | 1019.7 | 50 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Supply alone 70 % for above item 1701 i) |  | 713.79 | 50 |  | 434 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 1701 i) |  | 305.91 | 50 | 201 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
1701-'ii) | 150 mm dia | RM | 1579.88 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 25 % for above item 1701 ii) |  | 395.192 | 75 |  | 701 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 75 % for above item 1701 ii) |  | 1184.688 | 75 | 260 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1701-'iii) | 200 mm dia | RM | 2249.46 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Supply alone 70 % for above item 1701 iii) |  | 1574.62 | 100 |  | 1120 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Fixing alone 30 % for above item 1701 iii) |  | 674.84 | 100 | 300 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1702 | HDPE down take pipes conforming to IS4984 as per specification of following dia. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
i) | 100 mm dia | RM | 389.5 | 150 | 77 | 185 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ii) | 150 mm dia | RM | 564.56 | 4000 | 111 | 245 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
iii) | 200 mm dia | RM | 774.62 | 1500 | 151 | 345 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1800 | MISCELLANEOUS | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
1801 | Providing and fixing PVC water stops 225mm wide, 10 mm thick. | RM | 315.1 | 500 | 25 | 225 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1802 | Supplying and installation of 25mm thick vibration damping, resilient pads around foundation of vibrating equipment and other locations as directed by the Engineer-in-charge including cost of all materials labour equipment etc. complete as per drawing and specifications. | SQM | 17960.66 | 25 |  | 13830 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1803A | Providing 75mm thick anticorrosive layer laid to slope consisting of compacted crushed stone screenings, fine gravel, clean sand or similar material as directed by the Engineer, mixed in hot asphalt 10% by volume and rolled or compacted complete as per drawings and specifications, below fuel oil tanks and at such other places as per specifications and as directed by the Engineer. | CUM | 6382.07 | 500 | 275 | 399.75 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1804 | Providing and fixing G.I strips minimum 1.5mm thk and 150mm wide unless specified otherwise in water retaining structure. Galvanising as per relevant I.S. codes and as per specifications. | RM | 210.07 | 50 | 25 | 125 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1805 | Providing and fixing aluminium strips minimum 18 SWG thk and 300mm wide over expansion joints with minimum lap of 50mm length including aluminium screws, rawl plugs all complete as per specification. | RM | 328.23 | 150 | 25 | 205 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1807 | Transporting from BHEL store, laying and fixing transformer rails including guide rails in concrete including joining of rails. Anchoring lugs etc. complete as per specification.(Only Rails will be supplied by BHEL at free of cost) | MT | 20218.87 | 90 | 15000 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1808 | Laying of earthing mats/rods including transportation from BHEL stores, loading, unloading, cutting to length, welding etc. complete as per specification and as directed by Engineer-in-charge.(only Earth mat rod will be supplied by BHEL at free of cost) | MT | 15334.83 | 200 | 7500 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1810 | Providing and fixing GI rungs in concrete/brick walls at all elevations including @ zinc coating shall not be less than 900 g/sqm all complete. | KGS | 83.16 | 3000 | 25 | 67.5 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1811 | Design, supply, fabrication, erection of stoplog gates/Sluice gates in CW/RW and other Pump houses as per specification including SS liner as per drawing with embedments required, lifting beams, special tools & plants, spare parts for three years, machining, casting, all materials such as structural steel, cast steel, stainless steel, brass used for seals, rubber seals, gears, ball and roller bearing, branch bushings, greasing, bolts, nuts, lugs, threaded fastners etc., cleaning, sand blasting, hot double dip galvanised with minimum coating of zinc 750 gms/sqm., following by an application of etching primer and dipping in black bitumen as per B.S. 3416, erection along with a second stage concreting to true plumb and levels, submission of drawings / fabrication drawings for engineers approval etc., all complete as per specifications and approved drawings. The leakage through rubber seal shall not be more than 5 lit/min/metre length of seal under maximum head.(only weight of structural steel including embedments shall be considered for payment purpose) | MT | 121050.6 | 2 |  |  | 100700 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1812 | Supplying, fabricating, erecting in position including MS liner as per drawing and testing / examining bolted and / or welded structural steel work at all levels for stationary screens made out of rolled sections and / or plates including cutting, straightening if required, edge preparation, bolting / welding of joints, cleaning, sand blasting, hot double dip galvanised with minimum coating of zinc as 750 gms./sqm. followed by application of an etching primer and dipping in black bitumen as per BS 3416, complete as per drawing and directed. | MT | 121291.6 | 1 |  |  | 105000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1814 | Providing and fixing PVC pressure release valve of minimum dia 90mm in water retaining structure including 160 mm dia housing pipe of minimum length 2 m with perforation as per IS4558, nylon jali, perforated end plug, collar, graded filter, excavation, fixing in concrete slab/wall all complete as per specification, drawing and instruction of engineer in charge. | NOS | 5619.27 | 25 | 2000 |  | 5000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1815 | Providing and fixing ms vent pipes with cowls as per specifications, drawings and instructions of engineer in charge | KGS | 78.77 | 50 | 25 | 45 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1816 | Providing and fixing HDPE pipes in cable duct banks, openings in RCC work at all elevations of following sizes including cutting, fixing and levelling in position as per drawings, specifications all complete. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| I) 100 mm dia | RM | 306.35 | 200 | 70 | 137 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| ii) 150 mm dia | RM | 494.54 | 3000 | 105 | 205 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| iii) 200 mm dia | RM | 634.58 | 500 | 142 | 285 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2000 | FENCING AND GATES. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2001 | Supplying and erecting in position 2.4 m high PVC coated gavanised chain linked fencing of minimum 8 gauge (including PVC coating ) of mesh size 75 mm and galvanised concertina. The diameter of the steel wire for chain link fencing excluding PVC coating shall not be less than 12 gauge. GI barbed wire fencing confirming to IS 298 at top of chain link fencing shall be provided with 4 stands of height of 600 mm including all accesories as per specification all complete. | SQM | 516.41 | 2000 | 114 | 237.6 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2002 | Supplying and fixing G.I. barbed wire in fencing including G.I clips etc. complete as per specification | KGS | 113.79 | 3000 | 32.25 | 68.25 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2003 | Supply, fabrication and installing in position and testing galvanised MS Gates out of channels, joists, angles, flats, plates, pipes & sheets including stiffners, bracings, fabricated hinges, MS Aldrops with locking arrangement, tempered steel pivot, guide track of MS Tee, ball bearing arrangements, castor wheels,etc. all complete as per drawing, specification and as directed by Engineer-in-charge with 600mm high GI barbed wire fencing at top all complete. | MT | 87702.63 | 10.25 | 22000 | 68000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2100 | WATER SUPPLY | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2101 | Providing and fixing in position tested heavy duty type chromium plated brass long neck bib cocks including sockets, union, nut etc. complete 15mm nominal bore. | NOS | 485.78 | 100 | 50 | 340 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2102 | Providing and fixing in position heavy duty brass stop cock of approved quality including all specials etc. complete as directed by Engineer 15mm nominal bore. | NOS | 485.78 | 100 | 50 | 340 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2103 | Providing and fixing in position heavy duty brass full way valve with wheel of approved quality 25mm nominal bore. | NOS | 875.28 | 50 | 50 | 620 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2104 | Providing and fixing in position heavy duty brass full way valve with wheel of approved quality 50mm nominal bore. | NOS | 2708.98 | 25 | 50 | 1960 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2105 | Providing and fixing GI pipes complete with GI sockets, unions, elbows, tees, nipples etc. and clamps including cutting and making good the walls etc. complete (internal work) 15 mm nominal bore. | RM | 153.18 | 500 | 40 | 55.45 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2106 | Providing and fixing GI pipes complete with GI fittings a clamps including cutting and making good the walls etc. complete (internal work) 20 mm nominal bore. | RM | 188.19 | 400 | 45 | 69.85 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2107 | Providing and fixing GI pipes complete with GI sockets, unions, elbows, tees, nipples etc. and clamps including cutting and making good the walls etc.complete (internal work) 25 mm nominal bore (N.B). | RM | 253.83 | 200 | 50 | 98.65 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2108 | Providing and fixing GI pipes complete with GI sockets, unions, elbows, tees, nipples etc. including trenching & refilling anti-corrosive paint etc. complete (external work) 15mm nominal bore (N.B). | RM | 153.18 | 300 | 40 | 55.45 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2109 | Providing and fixing GI pipes complete with GI sockets, unions, elbows, tees, nipples etc. including trenching & refilling anti-corrosive paint etc.complete (external work) 20mm nominal bore (N.B). | RM | 188.19 | 300 | 45 | 70 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2110 | Providing and fixing GI pipes complete with GI sockets, unions, elbows, tees, nipples etc. including trenching & refilling anti-corrosive paint etc.complete (external work) 25mm nominal bore (N.B). | RM | 253.83 | 300 | 50 | 100 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2111 | Providing and fixing GI pipes complete with GI sockets, unions, elbows, tees, nipples etc. including trenching & refilling anti-corrosive paint etc.complete (external work) 50mm nominal bore (N.B). | RM | 433.27 | 200 | 65 | 205 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2112 | Providing and fixing 610mmx453mmx6mm thk mirror from reputed mirror manufacturer. Mirror shall be mounted with glass adjustable revolving CP brackets etc. complete with CP screws as per specification. | NOS | 538.3 | 25 | 50 | 360 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2113 | Providing and fixing 610mmx127mmx6mm thk clear glass with C.P Guard rails and mounted on C.P. brackets etc. complete as per specification. | NOS | 730.86 | 25 | 50 | 520 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2114 | Providing and fixing 600x20mm dia stainless steel pipe wall mounted towel rod with stainless steel brackets etc. all complete as per specification. | NOS | 730.86 | 50 | 40 | 520 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2116 | Providing and fixing stainless steel liquid soap dispenser. Dispenser shall be round and easily revolving with removable threaded nozzle and mounted on stainless steel brackets etc.complete as per specification. | NOS | 844.65 | 50 | 30 | 600 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2117 | Providing and fixing glazed vitreous wall mounted paper holder with suitable cover cum cutter fitted with CP screws etc. complete as per specification | NOS | 245.08 | 50 | 30 | 160 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2118 | Providing and fixing chromium plated brass shower rose with 15 or 20 mm inlet all complete. | NOS | 214.45 | 30 | 60 | 140 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2119 | Providing & fixing P.V.C. water tank (Syntex or equivalent) in position of following capacity. The work to including making all necessary inlet & outlet pipes, fixture, ball cocks, valves etc. all complete as per specification at all heights and levels | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
a | 1000 liters | NOS | 5676.17 | 5 | 500 | 4000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
b | 2000 liters | NOS | 11347.96 | 15 | 750 | 8000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
c | 5000 liters | NOS | 28372.07 | 2 | 1000 | 20000 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2200 | SANITARY WORKS | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2201 | Supply and fixing vitreous china wash basin size 600x450 with R.S. or C.I. brackets painted white, 15mm chromium plated piller tap, chromium plated brass chain with rubber pluga and waste of standard pattern, 32mm dia chromium plated brass trap unions, plastic connection pipe with chromium plated nuts, cutting and making good the walls where required etc. complete as per specifications | NOS | 3124.73 | 30 | 250 | 2084 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2202 | Providing and fixing approved vitreous china acid/alkali resistant laboratory sink of size 600x450x200mm with R.S. or C.I. brackets, chromium plated brass chain with rubber plug 40mm, CP brass waste with necessaary union complete including painting the fittings, cutting and making good the wall where required as per specification. | NOS | 4691.48 | 5 | 250 | 3200 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2202A | Providing and fixing approved stainless steel kitchen sink as per IS: 13983 of size 915x460x178 mm with C.I. brackets, stainless steel chain with rubber plug 40mm, CP brass waste trap with necessaary union complete including painting the fittings, cutting and making good the wall where required as per specification. | NOS | 3698.04 | 10 | 250 | 2496 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2203 | Providing and fixing colour European type water closet with siphon, open front solid plastic seat and plastic cover, low level 10 litre PVC water flushing cistern with valveless fittings, necessary C.P connections etc. complete as per specification. | NOS | 3772.44 | 30 | 250 | 2509 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2204 | Providing and fixing glazed vitreous china pan (IWC) with foot rests and high level 10 litre PVC flushing cistern with valveless fittings, necessary C.P connections, foot rests shall be made of white glazed vitreous china with chequered surface all complete with C.I brackets etc. as per specification. | NOS | 3431.08 | 50 | 250 | 2224 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2205 | Providing and fixing wall type glazed vitreous china urinals with photovoltaic control flushing system as per IS:2556 ( part6, sec1) all complete as per specifications. | NOS | 4529.56 | 50 | 300 | 3021.5 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2206 | Supply, laying and jointing 75mm dia heavy duty cast iron pipes including bends, branches and all other necessary fittings, lead cocking, a coat of bitumenous paint, M.S holder bats/clamps, cutting and making good the walls and floors, jointing, testing etc. all complete and as per specifications. | RM | 779 | 250 | 50 | 445 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2207 | Supply, laying and jointing 100mm dia heavy duty cast iron pipes including bends, branches and all other necessary fittings, lead caulking, a coat of bitumenous paint, M.S holder bats/clamps, cutting and making good the walls and floors, jointing, testing etc. all complete and as per specifications. | RM | 940.93 | 300 | 75 | 528 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2208 | Supply, laying and jointing 150mm dia heavy duty cast iron pipes including bends, branches and all other necessary fittings, a coat of bitumenous paint, M.S holder bats/clam lead caulking, a coat of bitumenous paint, M.S holder bats/clamps, cutting and making good the walls and floors, jointing, testing etc. all complete and as per specifications. | RM | 1719.92 | 150 | 100 | 978 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2209 | Providing, laying light duty non pressure NP3 class RCC pipes with collars jointed with stiff mixture of cement mortar 1:2 including testing of joints etc. complete 150mm dia, as per specifications. | RM | 590.82 | 250 | 115 | 214 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2210 | Providing, laying light duty non pressure NP3 class RCC pipes with collars jointed with stiff mixture of cement mortar 1:2 including testing of joints etc. complete 200mm dia, as per specifications. | RM | 687.1 | 300 | 135 | 318 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2211 | Providing, laying light duty non pressure NP3 class RCC pipes with collars jointed with stiff mixture of cement mortar 1:2 including testing of joints etc. complete 250mm dia, as per specifications. | RM | 945.3 | 500 | 160 | 398 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2212 | Providing, laying light duty non pressure NP3 class RCC pipes with collars jointed with stiff mixture of cement mortar 1:2 including testing of joints etc. complete 300mm dia, as per specifications. | RM | 1098.48 | 1500 | 185 | 478 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2213 | Providing, laying light duty non pressure NP3 class RCC pipes with collars jointed with stiff mixture of cement mortar 1:2 including testing of joints etc. complete 500mm dia, as per specifications. | RM | 2122.55 | 50 | 208 | 1096 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2214 | Providing, laying light duty non pressure NP3 class RCC pipes with collars jointed with stiff mixture of cement mortar 1:2 including testing of joints etc. complete 600mm dia, as per specifications. | RM | 2892.79 | 100 | 258 | 1457 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2215 | Providing, laying light duty non pressure NP3 class RCC pipes with collars jointed with stiff mixture of cement mortar 1:2 including testing of joints etc. complete 900mm dia, as per specifications. | RM | 5251.65 | 50 | 308 | 2185 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2216 | Providing, laying light duty non pressure NP2 class RCC pipes with collars jointed with stiff mixture of cement mortar 1:2 including testing of joints etc. as per specifications for dia: | [6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
i) | 150mm | RM | 498.91 | 200 | 115 | 203.36 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ii) | 250mm | RM | 783.38 | 400 | 135 | 365.25 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
iii) | 300mm | RM | 936.55 | 500 | 158 | 447.73 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
iv) | 400mm | RM | 1361.06 | 30 | 208 | 615.95 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
v) | 500mm | RM | 1645.52 | 40 | 258 | 718.325 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
vi) | 600mm | RM | 1842.46 | 20 | 308 | 802.431 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
vii) | 750mm | RM | 2516.42 | 20 | 358 | 1188.04 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2218 | Providing and fixing C.I Manhole cover of size 600mmx450mm including frame from reputed manufacture all completeas per specifications. | NOS | 2161.93 | 30 | 100 | 1440 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2219 | Providing and fixing circular heavy duty man hole cover of 600mm dia with frame all complete as per specification. | NOS | 11566.77 | 50 | 100 | 6800 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2220 | Providing and fixing square mouth S.W Gully trap grade 'A' complete with CI grating, brick masonry chamber and watertight CI grating, brick masonry chamber and water tight CI cover with 300x300mm (inside) the weight of cover to be not less than 4.53 Kg and frame to be not less than 2.72 Kg as per drawing and specifications etc. all complete size 100x100mm P or S Type. | NOS | 1601.75 | 25 | 70 | 1068.43 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2221 | Providing and fixing square mouth S.W Gully trap grade 'A' complete with CI grating, brick masonry chamber and watertight CI grating, brick masonry chamber and water tight CI cover with 300x300mm (inside) the weight of cover to be not less than 4.53 Kg and frame to be not less than 2.72 Kg as per drawing and specifications etc. all complete size 150x100mm P or S Type. | NOS | 1632.39 | 30 | 70 | 1088.43 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2222 | Providing and fixing square mouth S.W Gully trap grade 'A' complete with CI grating, brick masonry chamber and watertight CI grating, brick masonry chamber and water tight CI cover with 300x300mm (inside) the weight of cover to be not less than 4.53 Kg and frame to be not less than 2.72 Kg as per drawing and specifications etc. all complete size 150x150mm P or S Type. | NOS | 1658.65 | 20 | 70 | 1104.43 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2223 | Providing and fixing C.I. floor traps with C.P jalli complete as per specification. | NO | 538.3 | 75 | 75 | 386 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2224 | Providing and installing approved brand single tap water cooler of 80 L cooling capacity complete in all respect. | NOS | 24319.54 | 20 | 500 | 14400 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2225 | Providing and installing approved brand single tap water cooler of 150 L cooling capacity complete in all respect. | NOS | 30805.34 | 10 | 500 | 22400 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2226 | Providing and fixing white viterous urinal partitions all complete as per specification. | NOS | 809.63 | 50 | 150 | 750 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2227 | Providing and fixing eye and face fountain (combined unit with receptacle) conforming to IS:10592 all complete as per specification. | NOS | 809.63 | 5 | 150 | 3500 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2300 | STRUCTURAL STEEL WORKS | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Transporting from BHEL store, fabrication and erection of miscellaneous steel structural works at various elevations,including welding,gas cutting,painting (2 coats with 1 coat primer) etc complete as per drawing and specification.(Only structural steel will be provided by BHEL at free of cost) | MT | 18818.43 | 50 | 15200 | 1500 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2400 | ROAD WORK INCLUDING SUPPLY OF MATERIAL, COST OF LABOUR, MACHINERY ETC ALL COMPLETE AS PER SPECIFICATION, DRAWING, RELEVANT IRC & IS CODES AND AS DIRECTED BY THE ENGINEER-IN-CHARGE FOR THE FOLLOWING. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2401 | Preparation of sub grade by excavating earth to required depth for all types of soil/rock, dressing to camber and consolidating the base including making good the undulation etc. and disposal of surplus earth within plant boundary all complete as per specification. | CUM | 179.44 | 4050 | 75 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2402 | Providing, stacking and laying granular morrum for shoulder including watering, compaction with road roller to required camber etc. complete as per specification. | CUM | 577.68 | 2025 | 45 | 893.343 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2404 | Providing &Laying water bound macadam base course in layers of required thickness with stone aggregate 63mm to 40mm size, stone screening and blinding material including screening sorting, spreading to template and consolidation with road roller including carriage, spreading and consolidation of blinding material moorum etc. including cost of material labour all complete. | CUM | 1820.57 | 1215 | 216.5 | 1084.9 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2405 | Laying water bound macadam base course with stone aggregate 50mm to 20mm size stone screening and binding material including screening, sorting , spreading to template and consolidation with road roller including carriage spreading and consolidation of blinding material moorum etc. Including cost of material labour. All complete. | CUM | 1820.57 | 1215 | 216.5 | 1084.9 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2406 | Providing and applying Tack coat of low viscousity liquid bitumen of a suitable approved grade confirming to IS 73, 217 or 454 as applicable @ 10 kg/10sqm for an untreated WBM surface including scraping, cleaning with compressed air etc. complete. | SQM | 70.02 | 8100 | 15 | 35 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2407 | Providing, mixing and laying of compacted 75 thk. Bituminous Macadam Course. Bitumen shall be of a suitable grade complying with IS 73 and aggregates, binder material as specified in specification including hot mixing, hot laying, rolling all complete. | SQM | 411.38 | 8100 | 50 | 204.63 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2408 | Providing, mixing and laying premix carpet ( as per IRC-14 ) of compacted 25mm thickness in a single course composed of suitable small size aggregate premixed with a bituminous binder on a prepared base. Mixing applying rolling as per IRC specification. | SQM | 210.07 | 8100 | 38 | 91.045 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2409 | Providing and applying liquid seal coat comprising of an application of a layer of bituminous binder at the rate of 9.8kg/10sqm followed by a cover of stone chips at the rate of 0.09 cum/10sqm including rolling as per specification all complete. | SQM | 61.27 | 8100 | 15 | 33.75 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2410 | Supply and laying (400mm x 100mm X 375mm deep) precast concrete kerb stone of grade M15 with 20 mm aggregate and of shape as per detailed drawing including fixing in 13mm thk. cement mortar 1:2 in joints, finishing of joints with neat cement paste, making drainage opening where required etc. complete as per spec. | RM | 301.97 | 3600 | 52.5 | 169.785 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2410a | Providing & laying cement concrete 1:2:4 of 20mm size nominal aggregate in kerbs, edging, dwarf wall etc. including making opening for pipes etc complete excluding the cost of centering and shuttering. | CUM | 5715.55 | 200 | 1000 | 3234 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2411 | Providing and laying 230 mm wide bricks, with crushing strength of 50 kg/cm2, on edge for protection including fixing in 13mm thk. cement mortar 1:6 complete. | RM | 74.4 | 3600 | 25 | 45.34 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2412 | Dismantling of existing road consisting of premix carpet, curb stone/ brick on edge, bitumen macadem course, WBM, prepairing subgrade to receive new WBM including camber consolidation including disposal of debris within a lead of 1 Km etc. complete and as directed by Engineer. | SQM | 748.37 | 300 | 400 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2413 | Providing 25mm thick premix carpet on existing/damaged road surfaces ( as per IRC-14 ) of compacted 25mm thickness in a single course composed of suitable small size aggregate premixed with a bituminous binder on the existing base including tack coat, cleaning of existing surface, mixing applying rolling as per IRC specification. | SQM | 280.09 | 500 | 95 | 95.205 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2414 | Concrete of grade M-30 in roads etc complete with 20 mm nominal size graded aggregate complete as per specification. | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | CUM | 5067.85 | 500 | 245 | 3504 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2415 | Filling below concrete roads with stone (63 mm down graded), in layers not exceeding 200 mm thickness including breaking of boulders to required sizes, filling the interstices with selected sand and compacting to 85 % of original volume of stone stack for all lifts all complete as per instructions of engineer-in-charge. | CUM | 1361.06 | 500 | 75 | 982.5 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | 463960054.3475 |  |  |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF!
[25 empty] | #REF! | [5 empty] | #REF! | [13 empty] | #REF!